## Sheet2
descripcion_ctt | tipo_pyct | codigo_pyt | fecha_ctev | safety_ctev | schelude_ctev | quality_ctev | staffing_ctev | change_ctev | submittals_ctev | campo_ctev | observaciones_ctev
COMFORT SYSTEMS/ BILLONE | S | 13-0252 | 2013-04-01 | 5 | 5 | 4 | 5 | N/A | 4 | 3 | Difficulty in dealing with owners
CEDAR ENTERPRISES | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 13-0252 | 2013-04-01 | 4 | 5 | 4 | 4 | N/A | 5 | 4
DDS ENGINEERS | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0252 | 2013-04-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
FLOWER CITY GLASS | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 13-0252 | 2013-04-01 | 5 | 4 | 5 | 4 | 4 | 4 | 3 | Need to be proactive with them
KENNEDY MECHANICAL P&H INC. | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARK & DAN FRAMERS, INC | S | 13-0252 | 2013-04-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
NEW YORK STATE FENCE, INC | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRIDE FIRE PROTECTION | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QUALITY CARPETS | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAMAR STEEL SALES, INC | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODSTONE EARTH CONSTRUCTION, INC | S | 13-0252 | 2013-04-01 | 4 | 5 | 4 | 4 | 2 | 4 | 5 | Be prepared to argue, they are confrontational; issues with transparency and they will test you; be prepared to bring in team leader and outside consultants; great work execution though
LAKELANDS CONCRETE PRODUCTS | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAMILTON ENTERPRISES | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMI STRUCTURAL SOLUTIONS | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHLER AWNINGS | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
H-S INDUSTRIAL EQUIPMENT | S | 13-0252 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D CALL & SONS EXCAVAT. | S | 12-0243 | 2013-04-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3
AAC CONTRACTING, INC. | S | 12-0243 | 2013-04-01 | 5 | 4 | 3 | 4 | 1 | N/A | 3 | Slow response to RFPs
AIIA CONSTRUCTION COMPANY, INC | S | 12-0243 | 2013-04-01 | 3 | 4 | 4 | 5 | 2 | N/A | 3 | Change management is slow
ACCESS LIFTS & RAMPS | S | 12-0243 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 12-0243 | 2013-04-01 | 3 | 4 | 4 | 4 | 3 | 2 | 3 | Poor computer skills
ART PARTS SIGNS | S | 12-0243 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0243 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 12-0243 | 2013-04-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | Good experience on this job
CEDAR ENTERPRISES | S | 12-0243 | 2013-04-01 | 3 | 2 | 3 | 2 | 3 | 3 | 4 | Understaffed the job
DISCOUNT CARPETS | S | 12-0243 | 2013-04-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
EMPIRE METAL FABRICATORS, INC | S | 12-0243 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINGER LAKES CUSTOM FENCE | S | 12-0243 | 2013-04-01 | 4 | 2 | 4 | 3 | 3 | 2 | 4 | Had some issues meeting schedule targets
FLOWER CITY GLASS | S | 12-0243 | 2013-04-01 | 5 | 3 | 3 | 4 | 2 | 2 | 3
G&G WINDOW REPAIR | S | 12-0243 | 2013-04-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
HAMILTON ENTERPRISES | S | 12-0243 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HENRY ISAACS HOME REMODELING | S | 12-0243 | 2013-04-01 | 2 | 2 | 4 | 2 | 1 | 1 | 1 | This sub requires a lot of babysitting
IMPACT PAINTING LLC | S | 12-0243 | 2013-04-01 | 3 | 3 | 4 | 3 | 2 | 3 | 3
KENNEDY MECHANICAL P&H INC. | S | 12-0243 | 2013-04-01 | 3 | 2 | 4 | 2 | 3 | 2 | 4 | Understaffed the job
MARK & DAN FRAMERS, INC | S | 12-0243 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MCCLAIN ASSOCIATES INC. | S | 12-0243 | 2013-04-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NEW YORK STATE FENCE, INC | S | 12-0243 | 2013-04-01 | 3 | 3 | 3 | 3 | 3 | 2 | 3
PIKE STAINED GLASS STUDIOS, INC | S | 12-0243 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RICHARDSON HARDWOOD FLOORS | S | 12-0243 | 2013-04-01 | 3 | 4 | 5 | 4 | 2 | N/A | 3
ROCHESTER COLONIAL MANUFACTURING | S | 12-0243 | 2013-04-01 | 3 | 3 | 4 | 4 | 3 | 4 | 3
MERIDAN ASSOCIATES | S | 12-0243 | 2013-04-01 | 4 | 3 | 4 | 3 | 3 | 3 | 3
WINDOW ACCENTS INC. | S | 12-0243 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
US CEILING CORP. | S | 12-0243 | 2013-04-01 | 4 | 4 | 3 | 4 | 3 | 3 | 3
VAN PUTTE | S | 12-0243 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ID SIGNSYSTEMS | S | 12-0243 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0243 | 2013-04-01 | N/A | 4 | 4 | N/A | 4 | 3 | 3
MAX T. DOLAND | S | 12-0243 | 2013-04-01 | N/A | 4 | 4 | N/A | 4 | 4 | 3
ARMSTRONG CABINET PRODUCTS | S | 12-0243 | 2013-04-01 | N/A | 2 | 4 | N/A | 3 | 3 | 3
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0243 | 2013-04-01 | N/A | 4 | 4 | N/A | 4 | 3 | 3
ALLIANCE DOOR & HARDWARE | S | 12-0243 | 2013-04-01 | N/A | 2 | 4 | N/A | 1 | 2 | 2
MIG BUILDING SYSTEMS | S | 12-0243 | 2013-04-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3
SOLID SURFACES | S | 12-0243 | 2013-04-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
K&K GUNITE POOL BUILDERS, INC | S | 12-0246 | 2013-04-01 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | Questionable financials; do not hire again
KONE, INC | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRUEGLER CONTRACTING & REMODELING, LLC | S | 12-0246 | 2013-04-01 | 3 | 3 | 3 | 3 | N/A | 3 | 3
MCCLAIN ASSOCIATES INC. | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCLEOD SYSTEMS, INC. | S | 12-0246 | 2013-04-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
OVERHEAD DOOR COMPANY OF ALBANY, INC | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PENTEL DRYWALL | S | 12-0246 | 2013-04-01 | 4 | N/A | N/A | N/A | N/A | 3 | N/A | Just started
PINNACLE ROOFING INC | S | 12-0246 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Good new sub we found
PRO CARPET INC. | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RBM GUARDIAN FIRE PROTECTION INC | S | 12-0246 | 2013-04-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | Long time LCS sub
SHAWNLEE CONSTRUCTION LLC | S | 12-0246 | 2013-04-01 | 4 | 3 | 4 | 3 | 3 | 4 | 4 | Did a good job
TRIPOINT STONE | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDUSEN & STEVES LAND SURVEYORS | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDYKE PAINTING COMPANY | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 12-0246 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Long time LCS sub
BGI INTERIORS | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4 | material supplier
B&L WHOLESALE | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4 | supplier only
ALLIANCE DOOR & HARDWARE | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | 1 | 1 | 1 | Long term sub, but high maintainence
MAX T. DOLAND | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4 | supplier only
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | 3 | 3 | 3 | supplier only
SERWAY BROTHERS INC. | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | 3 | 3 | 3 | material only; Long term LCS sub, high maintainence
SPA DECORATING | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YORK BRIDGE CONCEPTS | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 12-0246 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0250 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BROCCOLO TREE & LAWN CARE | S | 12-0250 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COSTICH ENGINEERING | S | 12-0250 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 12-0250 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HEASTER BUILDING RESTORATION, INC | S | 12-0250 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 12-0250 | 2013-04-01 | 4 | 5 | 4 | 4 | N/A | 2 | 3 | Submittals do not come complete or on time
KENNEDY MECHANICAL P&H INC. | S | 12-0250 | 2013-04-01 | 4 | 3 | 4 | 3 | N/A | 3 | 3 | Just started
LANDMARK ELECTRIC INC | S | 12-0250 | 2013-04-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
MESSNER FLOORING RESOURCE | S | 12-0250 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 12-0250 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 12-0250 | 2013-04-01 | 4 | 3 | 4 | 3 | N/A | 3 | 3
POOLER ENTERPIRSES, INC. | S | 12-0250 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 12-0250 | 2013-04-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RAMAR STEEL SALES, INC | S | 12-0250 | 2013-04-01 | 5 | 5 | 4 | 5 | N/A | 5 | 4
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0250 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 12-0250 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 12-0250 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 12-0250 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 12-0250 | 2013-04-01 | 3 | 4 | 3 | 3 | N/A | 4 | 4
NATIONAL CONSTRUCTION RENTALS | S | 12-0250 | 2013-04-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 12-0250 | 2013-04-01 | 4 | 5 | 5 | 5 | N/A | 4 | 4
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 12-0250 | 2013-04-01 | 4 | 5 | 5 | 5 | N/A | 4 | 4
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0250 | 2013-04-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
JAMES H. MISSELL & ASSOCIATES | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4
MIG BUILDING SYSTEMS | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | Has been difficult from a management standpoint
MCGURK ELECTRIC, INC. | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | 3 | 3 | 4
KOVALSKY CARR | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MECH TECH | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
MESSNER FLOORING RESOURCE | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
ONTARIO EXTERIORS, INC | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 3
PRIDE FIRE PROTECTION | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
RAMAR STEEL SALES, INC | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SCHINDLER ELEVATOR | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
US CEILING CORP. | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
VANDYKE PAINTING COMPANY | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WOODSTONE EARTH CONSTRUCTION, INC | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 3
TRUSSWAY MFG. | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | 3 | 4 | 4
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
VP SUPPLY | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
KELLY BROS. | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | 4 | 2 | 1 | Getting them to react to anything from signing a contract to submittals has been difficult; major problem in concentrating everything with one person
SECOR BUILDING SOLUTIONS | S | 12-0247 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
104 CONTRACTORS INC. | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.R. PIERREPONT CO., INC | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 12-0228 | 2013-04-01 | 5 | 5 | 5 | 5 | 5 | N/A | 5
ACCURATE ACOUSTICAL, INC. | S | 12-0228 | 2013-04-01 | 3 | 3 | 4 | 3 | 4 | 4 | 3
ALPHA IRON WORKS, LLC | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&B MECHANICAL CONTRACTOR, INC | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&L WHOLESALE | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
DRAPERY INDUSTRIES, INC | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
EINSTEIN CONSTRUCTION CORP | S | 12-0228 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EMPIRE METAL FABRICATORS, INC | S | 12-0228 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRESTOP TECHNOLOGIES, INC | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
FRONTIER GLASS INC | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
GUARDIAN FIRE TESTING LABORATORIES | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
MONROE PIPING & SHEET METAL, LLC | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
NEW YORK STATE FENCE, INC | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 12-0228 | 2013-04-01 | 5 | 5 | 5 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 12-0228 | 2013-04-01 | 4 | 3 | 4 | 3 | 4 | 4 | 4
ROCHESTER COLONIAL MANUFACTURING | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SDC CONSTRUCTION SERVICES, INC | S | 12-0228 | 2013-04-01 | N/A | 2 | 3 | N/A | 4 | 2 | 2
SANITAIRE CLEANING CO., INC. | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCACCIA TILE & MARBLE INC. | S | 12-0228 | 2013-04-01 | 3 | 2 | 3 | 2 | 3 | 4 | 2
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
SWAN TILE, INC. | S | 12-0228 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4
ID SIGNSYSTEMS | S | 12-0228 | 2013-04-01 | 4 | 4 | 4 | 4 | N/A | 5 | 4
T.Y. LIN INTERNATIONAL | S | 12-0228 | 2013-04-01 | 5 | 5 | 5 | 5 | 4 | 4 | 4
AUSTIN MASTER SERVICES | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A LISS AND COMPANY | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ADW INC. | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BASEC CORPORATION | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ANTHONY BUFFALMANTE | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C & B PLUMBING & HEATING, INC | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CR CONTRACTING | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COASTAL TILE & MARBLE INC | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL DRAPERIES UNLIMITED | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWN WATERPROOFING | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D&C CONTRACTING | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D&J CONCRETE CORP. | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ELITE FLOORS | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRUNDMAN MECHANICAL SYSTEMS INC | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GUARANTEED CONTRACTING CORP. | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
INPRO CORPORATION | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ISLAND STEEL & DETAILING CORPORATION | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JUST RITE EQUIPMENT NJ | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KONE, INC | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KP ORGANIZATION, INC | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KANE CONTRACTING, INC. | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
M TUCKER | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MJC MASON CONTRACTING INC | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL FIREPROOFING | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SRI FIRE SPRINKLER LLC | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SENTRALE CONSTRUCTION CORP. | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOLAR ELECTRIC SYSTEMS INC. | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPRAY FORCE SYSTEMS | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TEMP-AIR | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VIP CONSTRUCTION | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WARD CARPENTER ENGINEERS INC. | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
M&D DOOR & HARDWARE | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 12-0233 | 2013-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGSTEN CONSTRUCTION | S | 12-0241 | 2013-05-01 | 4 | 4 | 5 | 5 | 5 | 5 | 5
ALEXANDER MITCHELL & SON | S | 12-0241 | 2013-05-01 | N/A | 5 | N/A | N/A | 5 | 5 | 5 | Supplier
B&L WHOLESALE | S | 12-0241 | 2013-05-01 | N/A | 5 | N/A | N/A | N/A | 5 | 5 | Supplier
BPE CONSTRUCTION | S | 12-0241 | 2013-05-01 | 3 | 3 | 3 | 3 | 3 | 4 | 4
BREWER & CO. OF WV, INC. | S | 12-0241 | 2013-05-01 | 4 | 5 | 4 | 5 | N/A | 5 | 4
BUILDERS SERVICES GROUP (DAVENPORT) | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 5 | 4 | Fire Proofing Not On-Site Yet
CME ASSOCIATES | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Consultant
CAPITOL BUSINESS INTERIORS | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | Window Blinds - Not On-Site Yet
CHERRY RIVER CONST LLC | S | 12-0241 | 2013-05-01 | 4 | 4 | 4 | 4 | 3 | 4 | 4
CHANDLER'S PLYWOOD PRODUCTS | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5 | Casework - Not On-Site Yet
CONSTRUCTION AHEAD INC. | S | 12-0241 | 2013-05-01 | 4 | 2 | 4 | 3 | N/A | 5 | 4
CONSTRUCTION SPECIALITIES INC. | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | Supplier
CONSTRUCTION SPECIALITIES INC. | S | 12-0241 | 2013-05-01 | 4 | 3 | 4 | 3 | N/A | 4 | 4
DEMCO NEW YORK CORP. | S | 12-0241 | 2013-05-01 | 5 | 4 | 5 | 4 | 4 | 5 | 5
DESIGN ROOFING LLC | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4 | Shingle Roofing - Not On-Site Yet
DODSON BROS. EXTERMINATING | S | 12-0241 | 2013-05-01 | 5 | 5 | 5 | 5 | N/A | 5 | 5
DOUGLAS EQUIPMENT | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | 3 | 5 | 5 | Kitchen Equipment Not On-Site Yet
DURAFRAME, LLC | S | 12-0241 | 2013-05-01 | N/A | 2 | 4 | 2 | 3 | 4 | 3 | Off-site panel fabricator
FIRESIDE & PATIO SHOP | S | 12-0241 | 2013-05-01 | N/A | 4 | N/A | N/A | N/A | 3 | 3 | Supplier
GYPSUM SYSTEMS, INC. | S | 12-0241 | 2013-05-01 | N/A | 5 | 5 | 5 | N/A | N/A | 5 | Off-site panel fabricator
HARRIS BROS. ROOFING | S | 12-0241 | 2013-05-01 | 5 | 3 | 4 | 4 | 5 | 5 | 5 | EPDM Roofing
HINZMAN CONSTRUCTION | S | 12-0241 | 2013-05-01 | 4 | 4 | 5 | 5 | 5 | 5 | 5
INSTALLED BLDG. PRODUCT LLC | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Insulation Contractor - Not On-Site Yet
J S ARCHER CO., INC. | S | 12-0241 | 2013-05-01 | N/A | 5 | 4 | 5 | 5 | 5 | 5 | Door/frames/hardware Supplier
JACKEL DEVELOPMENT, INC. | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | 4 | 5 | 4 | Trim Supplier & Finish Carpenter - Not On-Site Yet
KING BROTHERS FABRICATION | S | 12-0241 | 2013-05-01 | 5 | 1 | 3 | 2 | 2 | 2 | 2
NETRANOM COMMUNICATIONS | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4 | Low voltage installer - Not On-site Yet
OTIS ELEVATOR, USA | S | 12-0241 | 2013-05-01 | N/A | 1 | N/A | N/A | 4 | 5 | 3 | Elevator - Not On-site yet
PAYNE'S DRYWALL | S | 12-0241 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PHILIPS LIFELINE | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | 4 | 3 | 4 | Door Control & Carepoint System provider - Not On-site yet
PICKERING ASSOCIATES | S | 12-0241 | 2013-05-01 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Safety Consultant
PROBUILD CO. LLC | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | Sheathing Supplier
PROGRESSIVE SYSTEMS, INC. | S | 12-0241 | 2013-05-01 | N/A | 3 | 5 | N/A | 4 | 5 | 5 | Prefabricated Roof Truss - Complete
ROCK BRANCH MECHANICAL | S | 12-0241 | 2013-05-01 | 5 | 4 | 5 | 4 | 5 | 5 | 5
TERRA CARE INC. | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Design Build Landscaping - not on-site yet
WEST VIRGINIA GLASS CO. | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5 | Glass/Mirrors - Not On-site Yet
WHIRLPOOL CORPORATION | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5 | Residential Appliances - Not On-site Yet
WORKMAN & SONS PLBG. LLC | S | 12-0241 | 2013-05-01 | 4 | 4 | 4 | 5 | 5 | 3 | 3
A.M. STERN, INC. | S | 11-0222 | 2013-05-01 | 4 | 4 | 4 | 4 | 2 | 4 | 3
AAC CONTRACTING, INC. | S | 11-0222 | 2013-05-01 | 3 | 4 | 2 | 4 | 2 | N/A | 4
ABSCOPE ENVIRONMENTAL INC. | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AJAY GLASS & MIRROR | S | 11-0222 | 2013-05-01 | 4 | 2 | 4 | 2 | 4 | 2 | 1
ALLIANCE DOOR & HARDWARE | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 11-0222 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ASSA ABLOY ENTRANCE SYSTEMS | S | 11-0222 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BAY TILE MARBLE & TERRAZZO | S | 11-0222 | 2013-05-01 | 4 | 4 | 4 | 4 | 5 | 4 | 4
C.A. REED ASSOCIATES | S | 11-0222 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 11-0222 | 2013-05-01 | 4 | 4 | 4 | 4 | 3 | 4 | 4
CECO CONCRETE CONST. | S | 11-0222 | 2013-05-01 | 4 | 3 | 4 | 4 | 3 | 4 | 4
CONNOR FENCE COMPANY INC. | S | 11-0222 | 2013-05-01 | 4 | 4 | 4 | 4 | 2 | N/A | 2
D.V. BROWN & ASSOCIATES | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DECON STUDRAIL, INC. | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 11-0222 | 2013-05-01 | 3 | 2 | 3 | 2 | 4 | 3 | 2
E.M. PFAFF & SON, INC. | S | 11-0222 | 2013-05-01 | 3 | 3 | 3 | 3 | 4 | 3 | 3
E.S. FIRE SUPPRESSION | S | 11-0222 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ELEVATOR MAINTENANCE OF BUFFALO | S | 11-0222 | 2013-05-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
EMPIRE STATE MECHANICAL | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 11-0222 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 5
FRANK J. MARIANACCI INC. | S | 11-0222 | 2013-05-01 | 3 | 4 | 3 | 4 | 3 | N/A | 2
G&J CONTRACTING INC | S | 11-0222 | 2013-05-01 | 2 | 3 | 4 | 3 | 4 | N/A | 2
GENEVA AWNING & TENT WORKS | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRECO PAINTING | S | 11-0222 | 2013-05-01 | 3 | 3 | 2 | 3 | 3 | 1 | 2
GYPSUM SYSTEMS, INC. | S | 11-0222 | 2013-05-01 | 4 | 3 | 3 | 3 | 3 | 4 | 3
HENRIETTA BUILDING SUPPLIES, INC. | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HERBERT F. DARLING, INC. | S | 11-0222 | 2013-05-01 | 4 | 1 | 4 | 3 | 2 | 2 | 1
HOUTENBRINK'S INC. | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMPERIAL DOOR CONTROLS, INC. | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
INPRO CORPORATION | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | 2
J&R SPECIALTIES | S | 11-0222 | 2013-05-01 | 3 | 4 | 3 | 4 | 4 | 4 | 4 | Good
JOSEPHINE'S CLEANING SERVICE, LLC | S | 11-0222 | 2013-05-01 | 3 | 4 | 4 | 4 | 4 | N/A | 4
KELLY BROS. | S | 11-0222 | 2013-05-01 | N/A | 2 | 3 | N/A | 2 | 2 | 1
KLEIN REINFORCING SERVICES | S | 11-0222 | 2013-05-01 | N/A | 3 | 4 | N/A | 3 | 3 | 3
KOCHER SURVEYING, P.C. | S | 11-0222 | 2013-05-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
LAKEVIEW LAWN & LANDSCAPE | S | 11-0222 | 2013-05-01 | 3 | 3 | 3 | 3 | 4 | 1 | 3
O'CONNELL ELECTRIC COMPANY, INC | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERHEAD DOOR COMPANY OF ALBANY, INC | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 11-0222 | 2013-05-01 | 3 | 3 | 3 | 2 | 1 | 3 | 1
POSTLER & JAECKLE CORP. | S | 11-0222 | 2013-05-01 | 3 | 3 | 3 | 3 | 2 | 4 | 2
PRO CARPET INC. | S | 11-0222 | 2013-05-01 | 3 | 4 | 3 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 11-0222 | 2013-05-01 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | Need push
RAMAR STEEL SALES, INC | S | 11-0222 | 2013-05-01 | 4 | 4 | 5 | 4 | 4 | 4 | 4
SESSLER EXCAVATING | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUTHSIDE PRECAST | S | 11-0222 | 2013-05-01 | N/A | 1 | 3 | N/A | 2 | 3 | 1
STILLWATER ENTERPRISES | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWIFTLIFT INC. | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWISSLOG (TRANSLOGIC CORP.) | S | 11-0222 | 2013-05-01 | 3 | 2 | 3 | 2 | 2 | 1 | 1
T.Y. LIN INTERNATIONAL | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE TRANE COMPANY | S | 11-0222 | 2013-05-01 | 3 | 3 | 3 | 3 | 4 | 3 | 3
THYSSENKRUPP ELEVATOR | S | 11-0222 | 2013-05-01 | N/A | 2 | N/A | N/A | 2 | 1 | 1
TLM EXCAVATING & ASSOCIATES | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
V&B UNDERGROUND UTILITIES INC. | S | 11-0222 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 11-0222 | 2013-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 4
104 CONTRACTORS INC. | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.R. PIERREPONT CO., INC | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 12-0228 | 2013-05-01 | 5 | 5 | 5 | 5 | 5 | N/A | 5
ACCURATE ACOUSTICAL, INC. | S | 12-0228 | 2013-05-01 | 3 | 3 | 4 | 3 | 4 | 4 | 3
ALPHA IRON WORKS, LLC | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&B MECHANICAL CONTRACTOR, INC | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&L WHOLESALE | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
DRAPERY INDUSTRIES, INC | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
EINSTEIN CONSTRUCTION CORP | S | 12-0228 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EMPIRE METAL FABRICATORS, INC | S | 12-0228 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRESTOP TECHNOLOGIES, INC | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
FRONTIER GLASS INC | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
GUARDIAN FIRE TESTING LABORATORIES | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
MONROE PIPING & SHEET METAL, LLC | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
NEW YORK STATE FENCE, INC | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 12-0228 | 2013-05-01 | 5 | 5 | 5 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 12-0228 | 2013-05-01 | 4 | 3 | 4 | 3 | 4 | 4 | 4
ROCHESTER COLONIAL MANUFACTURING | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SDC CONSTRUCTION SERVICES, INC | S | 12-0228 | 2013-05-01 | N/A | 2 | 3 | N/A | 4 | 2 | 2
SANITAIRE CLEANING CO., INC. | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCACCIA TILE & MARBLE INC. | S | 12-0228 | 2013-05-01 | 3 | 2 | 3 | 2 | 3 | 4 | 2
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
SWAN TILE, INC. | S | 12-0228 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4
ID SIGNSYSTEMS | S | 12-0228 | 2013-05-01 | 4 | 4 | 4 | 4 | N/A | 5 | 4
T.Y. LIN INTERNATIONAL | S | 12-0228 | 2013-05-01 | 5 | 5 | 5 | 5 | 4 | 4 | 4
AUSTIN MASTER SERVICES | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A LISS AND COMPANY | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4 | Supplier
ADW INC. | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BASEC CORPORATION | S | 12-0233 | 2013-05-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
ANTHONY BUFFALMANTE | S | 12-0233 | 2013-05-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
C & B PLUMBING & HEATING, INC | S | 12-0233 | 2013-05-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
CR CONTRACTING | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COASTAL TILE & MARBLE INC | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
COMMERCIAL DRAPERIES UNLIMITED | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
CROWN WATERPROOFING | S | 12-0233 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
D&C CONTRACTING | S | 12-0233 | 2013-05-01 | 2 | 2 | 2 | 3 | 1 | 1 | 2
D&J CONCRETE CORP. | S | 12-0233 | 2013-05-01 | 3 | 4 | 3 | 4 | 4 | 3 | 3
ELITE FLOORS | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
GRUNDMAN MECHANICAL SYSTEMS INC | S | 12-0233 | 2013-05-01 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | Failing to manage their subcontractors
GUARANTEED CONTRACTING CORP. | S | 12-0233 | 2013-05-01 | 2 | 3 | 2 | 3 | 4 | 4 | 4
INPRO CORPORATION | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
ISLAND STEEL & DETAILING CORPORATION | S | 12-0233 | 2013-05-01 | 3 | 2 | 3 | 3 | 3 | 3 | 3
JUST RITE EQUIPMENT NJ | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 2
KONE, INC | S | 12-0233 | 2013-05-01 | 4 | 4 | 3 | 4 | N/A | 3 | 1 | 7 months to sign contract
KP ORGANIZATION, INC | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KANE CONTRACTING, INC. | S | 12-0233 | 2013-05-01 | 2 | 3 | 3 | 2 | 2 | 3 | 4 | Overloaded and overscoped this sub
M TUCKER | S | 12-0233 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MJC MASON CONTRACTING INC | S | 12-0233 | 2013-05-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
NATIONAL FIREPROOFING | S | 12-0233 | 2013-05-01 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | Evaluate before hiring again
SRI FIRE SPRINKLER LLC | S | 12-0233 | 2013-05-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
SENTRALE CONSTRUCTION CORP. | S | 12-0233 | 2013-05-01 | 3 | 4 | 4 | 4 | 2 | 3 | 3 | Had serious safety problems at the beginning of the project
SOLAR ELECTRIC SYSTEMS INC. | S | 12-0233 | 2013-05-01 | 3 | 4 | 4 | 4 | 3 | 3 | 3
SPRAY FORCE SYSTEMS | S | 12-0233 | 2013-05-01 | 3 | 4 | 3 | 4 | N/A | N/A | 2 | Hard to get a hold of
TEMP-AIR | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VIP CONSTRUCTION | S | 12-0233 | 2013-05-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
WARD CARPENTER ENGINEERS INC. | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Owner's surveyor
M&D DOOR & HARDWARE | S | 12-0233 | 2013-05-01 | N/A | 2 | N/A | N/A | 3 | 2 | 1 | Do not recommend to hire again
BGI INTERIORS | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | 3 | 4 | 4 | supplier
CONSTRUCTION SPECIALITIES INC. | S | 12-0233 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
A.D CALL & SONS EXCAVAT. | S | 12-0243 | 2013-05-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3
AAC CONTRACTING, INC. | S | 12-0243 | 2013-05-01 | 5 | 4 | 3 | 4 | 1 | N/A | 3 | Slow response to RFPs
AIIA CONSTRUCTION COMPANY, INC | S | 12-0243 | 2013-05-01 | 3 | 4 | 4 | 5 | 2 | N/A | 3 | Change management is slow
ACCESS LIFTS & RAMPS | S | 12-0243 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 12-0243 | 2013-05-01 | 3 | 4 | 4 | 4 | 3 | 2 | 3 | Poor computer skills
ART PARTS SIGNS | S | 12-0243 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0243 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 12-0243 | 2013-05-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | Good experience on this job
CEDAR ENTERPRISES | S | 12-0243 | 2013-05-01 | 3 | 2 | 3 | 2 | 3 | 3 | 4 | Understaffed the job
DISCOUNT CARPETS | S | 12-0243 | 2013-05-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
EMPIRE METAL FABRICATORS, INC | S | 12-0243 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINGER LAKES CUSTOM FENCE | S | 12-0243 | 2013-05-01 | 4 | 2 | 4 | 3 | 3 | 2 | 4 | Had some issues meeting schedule targets
FLOWER CITY GLASS | S | 12-0243 | 2013-05-01 | 5 | 3 | 3 | 4 | 2 | 2 | 3
G&G WINDOW REPAIR | S | 12-0243 | 2013-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
HAMILTON ENTERPRISES | S | 12-0243 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HENRY ISAACS HOME REMODELING | S | 12-0243 | 2013-05-01 | 2 | 2 | 4 | 2 | 1 | 1 | 1 | This sub requires a lot of babysitting
IMPACT PAINTING LLC | S | 12-0243 | 2013-05-01 | 3 | 3 | 4 | 3 | 2 | 3 | 3
KENNEDY MECHANICAL P&H INC. | S | 12-0243 | 2013-05-01 | 3 | 2 | 4 | 2 | 3 | 2 | 4 | Understaffed the job
MARK & DAN FRAMERS, INC | S | 12-0243 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MCCLAIN ASSOCIATES INC. | S | 12-0243 | 2013-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NEW YORK STATE FENCE, INC | S | 12-0243 | 2013-05-01 | 3 | 3 | 3 | 3 | 3 | 2 | 3
PIKE STAINED GLASS STUDIOS, INC | S | 12-0243 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RICHARDSON HARDWOOD FLOORS | S | 12-0243 | 2013-05-01 | 3 | 4 | 5 | 4 | 2 | N/A | 3
ROCHESTER COLONIAL MANUFACTURING | S | 12-0243 | 2013-05-01 | 3 | 3 | 4 | 4 | 3 | 4 | 3
MERIDAN ASSOCIATES | S | 12-0243 | 2013-05-01 | 4 | 3 | 4 | 3 | 3 | 3 | 3
WINDOW ACCENTS INC. | S | 12-0243 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
US CEILING CORP. | S | 12-0243 | 2013-05-01 | 4 | 4 | 3 | 4 | 3 | 3 | 3
VAN PUTTE | S | 12-0243 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ID SIGNSYSTEMS | S | 12-0243 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0243 | 2013-05-01 | N/A | 4 | 4 | N/A | 4 | 3 | 3
MAX T. DOLAND | S | 12-0243 | 2013-05-01 | N/A | 4 | 4 | N/A | 4 | 4 | 3
ARMSTRONG CABINET PRODUCTS | S | 12-0243 | 2013-05-01 | N/A | 2 | 4 | N/A | 3 | 3 | 3
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0243 | 2013-05-01 | N/A | 4 | 4 | N/A | 4 | 3 | 3
ALLIANCE DOOR & HARDWARE | S | 12-0243 | 2013-05-01 | N/A | 2 | 4 | N/A | 1 | 2 | 2
MIG BUILDING SYSTEMS | S | 12-0243 | 2013-05-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3
SOLID SURFACES | S | 12-0243 | 2013-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
A.D.W INC. | S | 12-0246 | 2013-05-01 | 4 | 4 | N/A | 4 | N/A | 5 | 5 | Couldn't provide bond and we are continually evaluating financials
AFSCO FENCE SUPPLY | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B.R. JOHNSON | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 12-0246 | 2013-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 12-0246 | 2013-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
BUILDERS INSTALLED PRODUCTS | S | 12-0246 | 2013-05-01 | 4 | 3 | 4 | 3 | N/A | 1 | 3 | Took a very long time in providing submittals; Darren H on the job
CGM TILE & STONE, INC | S | 12-0246 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CARE CLEAN INC | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 12-0246 | 2013-05-01 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | Had safety violations
EDWARD & THOMAS O'CONNOR INC | S | 12-0246 | 2013-05-01 | 4 | 4 | 4 | 4 | 3 | 4 | 3
L COON | S | 12-0246 | 2013-05-01 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | Good team player and helped launch job in a good way
FLOWER CITY GLASS | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GENSON OVERHEAD DOOR, INC | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
HENRY ISAACS HOME REMODELING | S | 12-0246 | 2013-05-01 | 4 | 3 | 4 | 3 | 3 | 4 | 4
IRV SCHRODER AND SONS | S | 12-0246 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Good team player
JAG I, LLC | S | 12-0246 | 2013-05-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Do not hire again
K&K GUNITE POOL BUILDERS, INC | S | 12-0246 | 2013-05-01 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | Questionable financials; do not hire again
KONE, INC | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRUEGLER CONTRACTING & REMODELING, LLC | S | 12-0246 | 2013-05-01 | 3 | 3 | 3 | 3 | N/A | 3 | 3
MCCLAIN ASSOCIATES INC. | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCLEOD SYSTEMS, INC. | S | 12-0246 | 2013-05-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
OVERHEAD DOOR COMPANY OF ALBANY, INC | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PENTEL DRYWALL | S | 12-0246 | 2013-05-01 | 4 | 2 | 4 | 2 | 3 | 3 | 3 | Just started
PINNACLE ROOFING INC | S | 12-0246 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Good new sub we found
PRO CARPET INC. | S | 12-0246 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 2 | 2
RBM GUARDIAN FIRE PROTECTION INC | S | 12-0246 | 2013-05-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | Long time LCS sub
SHAWNLEE CONSTRUCTION LLC | S | 12-0246 | 2013-05-01 | 4 | 3 | 4 | 3 | 3 | 4 | 4 | Did a good job
TRIPOINT STONE | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDUSEN & STEVES LAND SURVEYORS | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDYKE PAINTING COMPANY | S | 12-0246 | 2013-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | N/A
WHIRLPOOL CORPORATION | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 12-0246 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Long time LCS sub
BGI INTERIORS | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4 | material supplier
B&L WHOLESALE | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4 | supplier only
ALLIANCE DOOR & HARDWARE | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | 1 | 1 | 1 | Long term sub, but high maintainence
MAX T. DOLAND | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4 | supplier only
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | 3 | 3 | 3 | supplier only
SERWAY BROTHERS INC. | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | 3 | 3 | 3 | material only; Long term LCS sub, high maintainence
SPA DECORATING | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YORK BRIDGE CONCEPTS | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 12-0246 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0247 | 2013-05-01 | 5 | 5 | 5 | 5 | N/A | 4 | 4 | Good expierence
AIIA CONSTRUCTION COMPANY, INC | S | 12-0247 | 2013-05-01 | 4 | 5 | 4 | 5 | 4 | N/A | 4
AMERICAN PLUMBING, INC | S | 12-0247 | 2013-05-01 | 4 | 1 | 3 | 1 | 4 | 3 | 4 | Had problems early on with site foreman; new foreman is now adequate
CATENARY CONSTRUCTION CORP. | S | 12-0247 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CEDAR ENTERPRISES | S | 12-0247 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
FLOWER CITY GLASS | S | 12-0247 | 2013-05-01 | 5 | 5 | 5 | 5 | 4 | 4 | 4
HENDERSON-JOHNSON CO.INC. | S | 12-0247 | 2013-05-01 | 5 | 5 | 5 | 5 | N/A | 4 | 4
J&K CONSTRUCTION | S | 12-0247 | 2013-05-01 | 4 | 4 | 4 | 4 | 3 | N/A | 4 | Preformed Well under conditions that were not the best
JAMES H. MISSELL & ASSOCIATES | S | 12-0247 | 2013-05-01 | 5 | 5 | 5 | 5 | N/A | N/A | 4
MIG BUILDING SYSTEMS | S | 12-0247 | 2013-05-01 | 4 | 1 | 1 | 1 | N/A | 2 | 2 | Has been difficult from a management standpoint, late with materials
MCGURK ELECTRIC, INC. | S | 12-0247 | 2013-05-01 | 4 | 3 | 4 | 3 | 3 | 3 | 4
KOVALSKY CARR | S | 12-0247 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MECH TECH | S | 12-0247 | 2013-05-01 | 4 | 4 | 5 | 3 | 4 | 4 | 4
MESSNER FLOORING RESOURCE | S | 12-0247 | 2013-05-01 | 3 | 1 | 3 | 1 | 3 | 4 | 4 | This job was a disapointment in the past they have preformed well
ONTARIO EXTERIORS, INC | S | 12-0247 | 2013-05-01 | 2 | 3 | 3 | 4 | 4 | 4 | 3
PRIDE FIRE PROTECTION | S | 12-0247 | 2013-05-01 | 5 | 5 | 5 | 5 | N/A | 4 | 4 | Highly recommended
RAMAR STEEL SALES, INC | S | 12-0247 | 2013-05-01 | 5 | 5 | 5 | 5 | N/A | 4 | 4
SCHINDLER ELEVATOR | S | 12-0247 | 2013-05-01 | 5 | 4 | 5 | 5 | 4 | 4 | 4
US CEILING CORP. | S | 12-0247 | 2013-05-01 | 3 | 4 | 5 | 4 | 4 | 4 | 4 | Team Player
VANDYKE PAINTING COMPANY | S | 12-0247 | 2013-05-01 | 4 | 5 | 5 | 5 | N/A | 4 | 4
WOODSTONE EARTH CONSTRUCTION, INC | S | 12-0247 | 2013-05-01 | 4 | 3 | 3 | 2 | 4 | 4 | 3 | Not a team player
TRUSSWAY MFG. | S | 12-0247 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0247 | 2013-05-01 | N/A | N/A | N/A | N/A | 3 | 4 | 4
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0247 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
VP SUPPLY | S | 12-0247 | 2013-05-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0247 | 2013-05-01 | 5 | 1 | 4 | 1 | N/A | 4 | 4 | Diffcult coordinating and getting onsite when needed
KELLY BROS. | S | 12-0247 | 2013-05-01 | N/A | 1 | 2 | N/A | 4 | 2 | 1 | Getting them to react to anything from signing a contract to submittals has been difficult, delivery; major problem in concentrating everything with one person
SECOR BUILDING SOLUTIONS | S | 12-0247 | 2013-05-01 | 5 | 5 | 5 | 5 | N/A | 5 | 5
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0250 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BROCCOLO TREE & LAWN CARE | S | 12-0250 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COSTICH ENGINEERING | S | 12-0250 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 12-0250 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HEASTER BUILDING RESTORATION, INC | S | 12-0250 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 12-0250 | 2013-05-01 | 4 | 5 | 4 | 4 | N/A | 2 | 3 | Submittals do not come complete or on time
KENNEDY MECHANICAL P&H INC. | S | 12-0250 | 2013-05-01 | 4 | 3 | 4 | 3 | N/A | 3 | 3 | Just started
LANDMARK ELECTRIC INC | S | 12-0250 | 2013-05-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
MESSNER FLOORING RESOURCE | S | 12-0250 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 12-0250 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 12-0250 | 2013-05-01 | 4 | 3 | 4 | 3 | N/A | 3 | 3
POOLER ENTERPIRSES, INC. | S | 12-0250 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 12-0250 | 2013-05-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RAMAR STEEL SALES, INC | S | 12-0250 | 2013-05-01 | 5 | 5 | 4 | 5 | N/A | 5 | 4
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0250 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 12-0250 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 12-0250 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 12-0250 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 12-0250 | 2013-05-01 | 3 | 4 | 3 | 3 | N/A | 4 | 4
NATIONAL CONSTRUCTION RENTALS | S | 12-0250 | 2013-05-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 12-0250 | 2013-05-01 | 4 | 5 | 5 | 5 | N/A | 4 | 4
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 12-0250 | 2013-05-01 | 4 | 5 | 5 | 5 | N/A | 4 | 4
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0250 | 2013-05-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
COMFORT SYSTEMS/ BILLONE | S | 13-0252 | 2013-05-01 | 5 | 5 | 4 | 5 | N/A | 4 | 3 | Difficulty in dealing with owners
CEDAR ENTERPRISES | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 13-0252 | 2013-05-01 | 4 | 5 | 4 | 4 | N/A | 5 | 4
DDS ENGINEERS | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0252 | 2013-05-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
FLOWER CITY GLASS | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 13-0252 | 2013-05-01 | 5 | 4 | 5 | 4 | 4 | 4 | 3 | Need to be proactive with them
KENNEDY MECHANICAL P&H INC. | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCGURK ELECTRIC, INC. | S | 13-0252 | 2013-05-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
NEW YORK STATE FENCE, INC | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRIDE FIRE PROTECTION | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QUALITY CARPETS | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAMAR STEEL SALES, INC | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODSTONE EARTH CONSTRUCTION, INC | S | 13-0252 | 2013-05-01 | 4 | 5 | 4 | 4 | 2 | 4 | 5 | Be prepared to argue, they are confrontational; issues with transparency and they will test you; be prepared to bring in team leader and outside consultants; great work execution though
LAKELANDS CONCRETE PRODUCTS | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAMILTON ENTERPRISES | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMI STRUCTURAL SOLUTIONS | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHLER AWNINGS | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
H-S INDUSTRIAL EQUIPMENT | S | 13-0252 | 2013-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.M. STERN, INC. | S | 11-0222 | 2013-06-01 | 4 | 4 | 4 | 4 | 2 | 4 | 3
AAC CONTRACTING, INC. | S | 11-0222 | 2013-06-01 | 3 | 4 | 2 | 4 | 2 | N/A | 4
AJAY GLASS & MIRROR | S | 11-0222 | 2013-06-01 | 4 | 2 | 4 | 2 | 4 | 2 | 1
ASSA ABLOY ENTRANCE SYSTEMS | S | 11-0222 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ABSCOPE ENVIRONMENTAL INC. | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 11-0222 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BAY TILE MARBLE & TERRAZZO | S | 11-0222 | 2013-06-01 | 4 | 4 | 4 | 4 | 5 | 4 | 4
C.A. REED ASSOCIATES | S | 11-0222 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 11-0222 | 2013-06-01 | 4 | 4 | 4 | 4 | 3 | 4 | 4
CECO CONCRETE CONST. | S | 11-0222 | 2013-06-01 | 4 | 3 | 4 | 4 | 3 | 4 | 4
DECON STUDRAIL, INC. | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 11-0222 | 2013-06-01 | 3 | 2 | 3 | 2 | 4 | 3 | 2
CONNOR FENCE COMPANY INC. | S | 11-0222 | 2013-06-01 | 4 | 4 | 4 | 4 | 2 | N/A | 2
E.S. FIRE SUPPRESSION | S | 11-0222 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ELEVATOR MAINTENANCE OF BUFFALO | S | 11-0222 | 2013-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
EMPIRE STATE MECHANICAL | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 11-0222 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 5
FRANK J. MARIANACCI INC. | S | 11-0222 | 2013-06-01 | 3 | 4 | 3 | 4 | 3 | N/A | 2
G&J CONTRACTING INC | S | 11-0222 | 2013-06-01 | 2 | 3 | 4 | 3 | 4 | N/A | 2
GENEVA AWNING & TENT WORKS | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRECO PAINTING | S | 11-0222 | 2013-06-01 | 3 | 3 | 2 | 3 | 3 | 1 | 2
GYPSUM SYSTEMS, INC. | S | 11-0222 | 2013-06-01 | 4 | 3 | 3 | 3 | 3 | 4 | 3
HENRIETTA BUILDING SUPPLIES, INC. | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HERBERT F. DARLING, INC. | S | 11-0222 | 2013-06-01 | 4 | 1 | 4 | 3 | 2 | 2 | 1
HOUTENBRINK'S INC. | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMPERIAL DOOR CONTROLS, INC. | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 11-0222 | 2013-06-01 | 3 | 4 | 3 | 4 | 4 | 4 | 4 | Good
JOSEPHINE'S CLEANING SERVICE, LLC | S | 11-0222 | 2013-06-01 | 3 | 4 | 4 | 4 | 4 | N/A | 4
KLEIN REINFORCING SERVICES | S | 11-0222 | 2013-06-01 | N/A | 3 | 4 | N/A | 3 | 3 | 3
KOCHER SURVEYING, P.C. | S | 11-0222 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
LAKEVIEW LAWN & LANDSCAPE | S | 11-0222 | 2013-06-01 | 3 | 3 | 3 | 3 | 4 | 1 | 3
SESSLER EXCAVATING | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
O'CONNELL ELECTRIC COMPANY, INC | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERHEAD DOOR COMPANY OF ALBANY, INC | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 11-0222 | 2013-06-01 | 3 | 3 | 3 | 2 | 1 | 3 | 1
POSTLER & JAECKLE CORP. | S | 11-0222 | 2013-06-01 | 3 | 3 | 3 | 3 | 2 | 4 | 2
PRO CARPET INC. | S | 11-0222 | 2013-06-01 | 3 | 4 | 3 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 11-0222 | 2013-06-01 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | Need push
RAMAR STEEL SALES, INC | S | 11-0222 | 2013-06-01 | 4 | 4 | 5 | 4 | 4 | 4 | 4
STILLWATER ENTERPRISES | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWIFTLIFT INC. | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWISSLOG (TRANSLOGIC CORP.) | S | 11-0222 | 2013-06-01 | 3 | 2 | 3 | 2 | 2 | 1 | 1
TLM EXCAVATING & ASSOCIATES | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE TRANE COMPANY | S | 11-0222 | 2013-06-01 | 3 | 3 | 3 | 3 | 4 | 3 | 3
THYSSENKRUPP ELEVATOR | S | 11-0222 | 2013-06-01 | N/A | 2 | N/A | N/A | 2 | 1 | 1
UPSTATE ROOFING & PAINTING, INC. | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
V&B UNDERGROUND UTILITIES INC. | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 11-0222 | 2013-06-01 | 3 | 3 | 3 | 3 | 3 | 3 | 4
D.V. BROWN & ASSOCIATES | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E.M. PFAFF & SON, INC. | S | 11-0222 | 2013-06-01 | 3 | 3 | 3 | 3 | 4 | 3 | 3
INPRO CORPORATION | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | 2
KELLY BROS. | S | 11-0222 | 2013-06-01 | N/A | 2 | 3 | N/A | 2 | 2 | 1
SOUTHSIDE PRECAST | S | 11-0222 | 2013-06-01 | N/A | 1 | 3 | N/A | 2 | 3 | 1
T.Y. LIN INTERNATIONAL | S | 11-0222 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALUMINA RAILING PRODUCTS, INC. | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
ASSOCIATED DRYWALL PARTNERS | S | 12-0235 | 2013-06-01 | 4 | 2 | 4 | 2 | 2 | 4 | 4
BGI INTERIORS | S | 12-0235 | 2013-06-01 | N/A | 4 | 5 | N/A | 4 | 5 | 4 | Material only
BECKER LANDSCAPE CONTRACTORS INC. | S | 12-0235 | 2013-06-01 | 5 | 4 | 4 | 3 | 4 | 4 | 4 | Just started
BEST RESTAURANT EQUIPMENT & DESIGN, INC. | S | 12-0235 | 2013-06-01 | 5 | 4 | 4 | 3 | 3 | 4 | 4
BLAKLEY CORPORATION | S | 12-0235 | 2013-06-01 | 4 | 4 | 4 | 4 | 3 | 4 | 4
C.E. REEVE ROOFING LLC | S | 12-0235 | 2013-06-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
CAIN CORPORATION | S | 12-0235 | 2013-06-01 | 4 | 3 | 4 | 3 | 4 | 3 | 3
CARBIDE INDUSTRIES | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
CIRCLE B CONSTRUCTION SYSTEMS, LLC | S | 12-0235 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CLARK SALES & SERVICE INC. | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | 3 | 4 | 4 | Not on site
DEALERS WHOLESALE | S | 12-0235 | 2013-06-01 | 4 | 3 | 4 | 4 | 4 | 3 | 3
DEL-MONDE, INC. | S | 12-0235 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ELBRECHT INVESTMENTS LLC DBA ELBRECHT CONCRETE | S | 12-0235 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINAL CLEAN CORP. | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
GAYLOR, INC. | S | 12-0235 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
GLENMARK CONSTRUCTION | S | 12-0235 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HALL ALUMINUM | S | 12-0235 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HOOSIER PRESTRESS, INC. | S | 12-0235 | 2013-06-01 | 4 | 3 | 4 | 3 | 3 | 3 | 3
INDIANA STEEL FABRICATING, INC. | S | 12-0235 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
K & K FENCE, INC. | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
LEE SUPPLY CORPORATION | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
LIGHT-CRETE PRODUCTS & SERVICES, INC. | S | 12-0235 | 2013-06-01 | 4 | 5 | 4 | 4 | 4 | 4 | 4
MOMPER INSULATION | S | 12-0235 | 2013-06-01 | 5 | 5 | 5 | 4 | 4 | 4 | 4
OTIS ELEVATOR, USA | S | 12-0235 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OVERHEAD DOOR COMPANY OF ALBANY, INC | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
OYLER CONSTRUCTION | S | 12-0235 | 2013-06-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4
PROBUILD CO. LLC | S | 12-0235 | 2013-06-01 | 4 | 3 | 4 | 2 | 3 | 3 | 3
QUALITECK LLC | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Just started
ROBERT HAINES CO. | S | 12-0235 | 2013-06-01 | 5 | 2 | 4 | 2 | 3 | 3 | 3
ROGER WARD ENGINEERING, INC. | S | 12-0235 | 2013-06-01 | 5 | 2 | 3 | 2 | 3 | 3 | 2
SPD TEXTILE & DRAPERY, INC. | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
STEELCORE CONSTRUCTION CO. INC. | S | 12-0235 | 2013-06-01 | 4 | 2 | 4 | 2 | 3 | 3 | 2
TP MECHANICAL CONTRACTORS | S | 12-0235 | 2013-06-01 | 5 | 3 | 4 | 3 | 3 | 4 | 3
US AUTOMATIC FIRE & SECURITY | S | 12-0235 | 2013-06-01 | 4 | 3 | 4 | 2 | 3 | 4 | 4
VALENTI HELD, INC. | S | 12-0235 | 2013-06-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
VISION PAINTING | S | 12-0235 | 2013-06-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
WAGLER CUSTOM HOMES LLC | S | 12-0235 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WILSON-PARTENHEIMER, INC. | S | 12-0235 | 2013-06-01 | 4 | 3 | 4 | 3 | 3 | 4 | 4
MAX T. DOLAND | S | 12-0235 | 2013-06-01 | N/A | 5 | 5 | N/A | 4 | 5 | 4
ALLIANCE DOOR & HARDWARE | S | 12-0235 | 2013-06-01 | N/A | 4 | 5 | N/A | 4 | 4 | 4
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0235 | 2013-06-01 | N/A | 5 | 5 | N/A | 4 | 4 | 4
NATIONAL CONSTRUCTION RENTALS | S | 12-0235 | 2013-06-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
TRUSSWAY MFG. | S | 12-0235 | 2013-06-01 | N/A | 5 | 5 | N/A | 4 | 4 | 4
LAUNDRY CITY EQUIPMENT | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | Not on site
SYR BEAUTY | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
LOOMIS BROS. EQUIPMENT | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARK & DAN FRAMERS, INC | S | 12-0235 | 2013-06-01 | 5 | 4 | 4 | 4 | 4 | N/A | 4 | Procurement on this project
RUNYON EQUIPMENT | S | 12-0235 | 2013-06-01 | 5 | 5 | 5 | 5 | 4 | N/A | 5
RICHARDS BUILDING SUPPLY | S | 12-0235 | 2013-06-01 | N/A | 1 | 4 | N/A | 3 | 3 | 3
GEMINI ELECTRONIC | S | 12-0235 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
MOBILE AIR | S | 12-0235 | 2013-06-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4
KENNEDY MECHANICAL P&H INC. | S | 12-0239 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCGURK ELECTRIC, INC. | S | 12-0239 | 2013-06-01 | 4 | 5 | 4 | N/A | 1 | 1 | 1 | Slow office
POOLER ENTERPIRSES, INC. | S | 12-0239 | 2013-06-01 | 4 | 1 | 3 | 3 | 1 | 2 | 2 | Too much work and they are overwhelmed and under-staffed
FLOWER CITY GLASS | S | 12-0239 | 2013-06-01 | N/A | 3 | 3 | 3 | 3 | 3 | 3
MARK & DAN FRAMERS, INC | S | 12-0239 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 12-0239 | 2013-06-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4
RAMAR STEEL SALES, INC | S | 12-0239 | 2013-06-01 | N/A | 4 | N/A | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 12-0239 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGSTEN CONSTRUCTION | S | 12-0241 | 2013-06-01 | 4 | 3 | 4 | 4 | N/A | N/A | N/A
BPE CONSTRUCTION | S | 12-0241 | 2013-06-01 | 3 | 3 | 3 | 4 | N/A | N/A | N/A
BREWER & CO. OF WV, INC. | S | 12-0241 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
BUILDERS SERVICES GROUP (DAVENPORT) | S | 12-0241 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
CAPITOL BUSINESS INTERIORS | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHERRY RIVER CONST LLC | S | 12-0241 | 2013-06-01 | 4 | 3 | 3 | 3 | N/A | N/A | N/A
CONSTRUCTION AHEAD INC. | S | 12-0241 | 2013-06-01 | 4 | 3 | 4 | 3 | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 12-0241 | 2013-06-01 | 4 | 3 | 4 | 3 | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 12-0241 | 2013-06-01 | 5 | 5 | 5 | 4 | N/A | N/A | N/A
DESIGN ROOFING LLC | S | 12-0241 | 2013-06-01 | 3 | 2 | 3 | 4 | N/A | N/A | N/A
DODSON BROS. EXTERMINATING | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DOUGLAS EQUIPMENT | S | 12-0241 | 2013-06-01 | 4 | 3 | 4 | 4 | N/A | N/A | N/A
FAMILY CARPET OUTLET INC. | S | 12-0241 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
FIRESIDE & PATIO SHOP | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HARRIS BROS. ROOFING | S | 12-0241 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
HINZMAN CONSTRUCTION | S | 12-0241 | 2013-06-01 | 5 | 5 | 4 | 4 | N/A | N/A | N/A
JACKEL DEVELOPMENT, INC. | S | 12-0241 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
KING BROTHERS FABRICATION | S | 12-0241 | 2013-06-01 | 3 | 2 | 3 | 2 | N/A | N/A | N/A
NETRANOM COMMUNICATIONS | S | 12-0241 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PAYNE'S DRYWALL | S | 12-0241 | 2013-06-01 | 3 | 2 | 3 | 3 | N/A | N/A | N/A
PHILIPS LIFELINE | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PICKERING ASSOCIATES | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCK BRANCH MECHANICAL | S | 12-0241 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
TERRA CARE INC. | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WORKMAN & SONS PLBG. LLC | S | 12-0241 | 2013-06-01 | 3 | 4 | 3 | 3 | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL STATE INTERIORS | S | 12-0241 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
ARJOHUNTLEIGH INC. | S | 12-0241 | 2013-06-01 | 4 | 3 | 4 | 4 | N/A | N/A | N/A
B&L WHOLESALE | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRAGGS FRESH CONSTRUCTION | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CME ASSOCIATES | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CENTRAL GLASS CO. OF CHARLESTON | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHANDLER'S PLYWOOD PRODUCTS | S | 12-0241 | 2013-06-01 | N/A | 4 | 4 | 4 | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DURAFRAME, LLC | S | 12-0241 | 2013-06-01 | N/A | 3 | 3 | 3 | N/A | N/A | N/A
GYPSUM SYSTEMS, INC. | S | 12-0241 | 2013-06-01 | N/A | 3 | 3 | 3 | N/A | N/A | N/A
INSTALLED BLDG. PRODUCT LLC | S | 12-0241 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
J S ARCHER CO., INC. | S | 12-0241 | 2013-06-01 | N/A | 3 | 4 | N/A | N/A | N/A | N/A
PROBUILD CO. LLC | S | 12-0241 | 2013-06-01 | N/A | 3 | N/A | N/A | N/A | N/A | N/A
PROGRESSIVE SYSTEMS, INC. | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WEST VIRGINIA GLASS CO. | S | 12-0241 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D CALL & SONS EXCAVAT. | S | 12-0243 | 2013-06-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3
AAC CONTRACTING, INC. | S | 12-0243 | 2013-06-01 | 5 | 4 | 3 | 4 | 1 | N/A | 3 | Slow response to RFPs
AIIA CONSTRUCTION COMPANY, INC | S | 12-0243 | 2013-06-01 | 3 | 4 | 4 | 5 | 2 | N/A | 3 | Change management is slow
ACCESS LIFTS & RAMPS | S | 12-0243 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 12-0243 | 2013-06-01 | 3 | 4 | 4 | 4 | 3 | 2 | 3 | Poor computer skills
ART PARTS SIGNS | S | 12-0243 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0243 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 12-0243 | 2013-06-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | Good experience on this job
CEDAR ENTERPRISES | S | 12-0243 | 2013-06-01 | 3 | 2 | 3 | 2 | 3 | 3 | 4 | Understaffed the job
DISCOUNT CARPETS | S | 12-0243 | 2013-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
EMPIRE METAL FABRICATORS, INC | S | 12-0243 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINGER LAKES CUSTOM FENCE | S | 12-0243 | 2013-06-01 | 4 | 2 | 4 | 3 | 3 | 2 | 4 | Had some issues meeting schedule targets
FLOWER CITY GLASS | S | 12-0243 | 2013-06-01 | 5 | 3 | 3 | 4 | 2 | 2 | 3
G&G WINDOW REPAIR | S | 12-0243 | 2013-06-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
HAMILTON ENTERPRISES | S | 12-0243 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HENRY ISAACS HOME REMODELING | S | 12-0243 | 2013-06-01 | 2 | 2 | 4 | 2 | 1 | 1 | 1 | This sub requires a lot of babysitting
IMPACT PAINTING LLC | S | 12-0243 | 2013-06-01 | 3 | 3 | 4 | 3 | 2 | 3 | 3
KENNEDY MECHANICAL P&H INC. | S | 12-0243 | 2013-06-01 | 3 | 2 | 4 | 2 | 3 | 2 | 4 | Understaffed the job
MARK & DAN FRAMERS, INC | S | 12-0243 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MCCLAIN ASSOCIATES INC. | S | 12-0243 | 2013-06-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NEW YORK STATE FENCE, INC | S | 12-0243 | 2013-06-01 | 3 | 3 | 3 | 3 | 3 | 2 | 3
PIKE STAINED GLASS STUDIOS, INC | S | 12-0243 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RICHARDSON HARDWOOD FLOORS | S | 12-0243 | 2013-06-01 | 3 | 4 | 5 | 4 | 2 | N/A | 3
ROCHESTER COLONIAL MANUFACTURING | S | 12-0243 | 2013-06-01 | 3 | 3 | 4 | 4 | 3 | 4 | 3
MERIDAN ASSOCIATES | S | 12-0243 | 2013-06-01 | 4 | 3 | 4 | 3 | 3 | 3 | 3
WINDOW ACCENTS INC. | S | 12-0243 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
US CEILING CORP. | S | 12-0243 | 2013-06-01 | 4 | 4 | 3 | 4 | 3 | 3 | 3
VAN PUTTE | S | 12-0243 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ID SIGNSYSTEMS | S | 12-0243 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0243 | 2013-06-01 | N/A | 4 | 4 | N/A | 4 | 3 | 3
MAX T. DOLAND | S | 12-0243 | 2013-06-01 | N/A | 4 | 4 | N/A | 4 | 4 | 3
ARMSTRONG CABINET PRODUCTS | S | 12-0243 | 2013-06-01 | N/A | 2 | 4 | N/A | 3 | 3 | 3
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0243 | 2013-06-01 | N/A | 4 | 4 | N/A | 4 | 3 | 3
ALLIANCE DOOR & HARDWARE | S | 12-0243 | 2013-06-01 | N/A | 2 | 4 | N/A | 1 | 2 | 2
MIG BUILDING SYSTEMS | S | 12-0243 | 2013-06-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3
SOLID SURFACES | S | 12-0243 | 2013-06-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0250 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BROCCOLO TREE & LAWN CARE | S | 12-0250 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COSTICH ENGINEERING | S | 12-0250 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 12-0250 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HEASTER BUILDING RESTORATION, INC | S | 12-0250 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 12-0250 | 2013-06-01 | 4 | 5 | 4 | 4 | N/A | 2 | 3 | Submittals do not come complete or on time
KENNEDY MECHANICAL P&H INC. | S | 12-0250 | 2013-06-01 | 4 | 3 | 4 | 3 | N/A | 3 | 3 | Just started
LANDMARK ELECTRIC INC | S | 12-0250 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
MESSNER FLOORING RESOURCE | S | 12-0250 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 12-0250 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 12-0250 | 2013-06-01 | 4 | 3 | 4 | 3 | N/A | 3 | 3
POOLER ENTERPIRSES, INC. | S | 12-0250 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 12-0250 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RAMAR STEEL SALES, INC | S | 12-0250 | 2013-06-01 | 5 | 5 | 4 | 5 | N/A | 5 | 4
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0250 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 12-0250 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 12-0250 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 12-0250 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 12-0250 | 2013-06-01 | 3 | 4 | 3 | 3 | N/A | 4 | 4
NATIONAL CONSTRUCTION RENTALS | S | 12-0250 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 12-0250 | 2013-06-01 | 4 | 5 | 5 | 5 | N/A | 4 | 4
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 12-0250 | 2013-06-01 | 4 | 5 | 5 | 5 | N/A | 4 | 4
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0250 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
COMFORT SYSTEMS/ BILLONE | S | 13-0252 | 2013-06-01 | 5 | 5 | 4 | 5 | N/A | 4 | 3 | Difficulty in dealing with owners
CEDAR ENTERPRISES | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 13-0252 | 2013-06-01 | 4 | 5 | 4 | 4 | N/A | 5 | 4
DDS ENGINEERS | S | 13-0252 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0252 | 2013-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
FLOWER CITY GLASS | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 13-0252 | 2013-06-01 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | Need to be proactive with them
KENNEDY MECHANICAL P&H INC. | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCGURK ELECTRIC, INC. | S | 13-0252 | 2013-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
NEW YORK STATE FENCE, INC | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRIDE FIRE PROTECTION | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QUALITY CARPETS | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAMAR STEEL SALES, INC | S | 13-0252 | 2013-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
SCHINDLER ELEVATOR | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODSTONE EARTH CONSTRUCTION, INC | S | 13-0252 | 2013-06-01 | 4 | 5 | 4 | 4 | 2 | 4 | 5 | Be prepared to argue, they are confrontational; issues with transparency and they will test you; be prepared to bring in team leader and outside consultants; great work execution though
LAKELANDS CONCRETE PRODUCTS | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAMILTON ENTERPRISES | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMI STRUCTURAL SOLUTIONS | S | 13-0252 | 2013-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
ALEXANDER MITCHELL & SON | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHLER AWNINGS | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
H-S INDUSTRIAL EQUIPMENT | S | 13-0252 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D CALL & SONS EXCAVAT. | S | 13-0262 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | Submittals have been late
ES SYSTEMS, INC | S | 13-0262 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&K CONSTRUCTION | S | 13-0262 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MADGE LAND SURVEYING P.C. | S | 13-0262 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MCGURK ELECTRIC, INC. | S | 13-0262 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PRECISION CONCRETE AND MASONRY | S | 13-0262 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | 1 | 2 | Responsiveness is poor from this sub
104 CONTRACTORS INC. | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.R. PIERREPONT CO., INC | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 12-0228 | 2013-06-01 | 5 | 5 | 5 | 5 | 5 | N/A | 5
ACCURATE ACOUSTICAL, INC. | S | 12-0228 | 2013-06-01 | 3 | 3 | 4 | 3 | 4 | 4 | 3
ALPHA IRON WORKS, LLC | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&B MECHANICAL CONTRACTOR, INC | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&L WHOLESALE | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
DRAPERY INDUSTRIES, INC | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
EINSTEIN CONSTRUCTION CORP | S | 12-0228 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EMPIRE METAL FABRICATORS, INC | S | 12-0228 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRESTOP TECHNOLOGIES, INC | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
FRONTIER GLASS INC | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
GUARDIAN FIRE TESTING LABORATORIES | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
MONROE PIPING & SHEET METAL, LLC | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
NEW YORK STATE FENCE, INC | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 12-0228 | 2013-06-01 | 5 | 5 | 5 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 12-0228 | 2013-06-01 | 4 | 3 | 4 | 3 | 4 | 4 | 4
ROCHESTER COLONIAL MANUFACTURING | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SDC CONSTRUCTION SERVICES, INC | S | 12-0228 | 2013-06-01 | N/A | 2 | 3 | N/A | 4 | 2 | 2
SANITAIRE CLEANING CO., INC. | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCACCIA TILE & MARBLE INC. | S | 12-0228 | 2013-06-01 | 3 | 2 | 3 | 2 | 3 | 4 | 2
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
SWAN TILE, INC. | S | 12-0228 | 2013-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4
ID SIGNSYSTEMS | S | 12-0228 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | 5 | 4
T.Y. LIN INTERNATIONAL | S | 12-0228 | 2013-06-01 | 5 | 5 | 5 | 5 | 4 | 4 | 4
ALUMINA RAILING PRODUCTS, INC. | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
ASSOCIATED DRYWALL PARTNERS | S | 12-0235 | 2013-07-01 | 4 | 2 | 4 | 2 | 2 | 4 | 4
BGI INTERIORS | S | 12-0235 | 2013-07-01 | N/A | 4 | 5 | N/A | 4 | 5 | 4 | Material only
BECKER LANDSCAPE CONTRACTORS INC. | S | 12-0235 | 2013-07-01 | 5 | 4 | 4 | 3 | 4 | 4 | 4 | Just started
BEST RESTAURANT EQUIPMENT & DESIGN, INC. | S | 12-0235 | 2013-07-01 | 5 | 4 | 4 | 3 | 3 | 4 | 4
BLAKLEY CORPORATION | S | 12-0235 | 2013-07-01 | 4 | 4 | 4 | 4 | 3 | 4 | 4
C.E. REEVE ROOFING LLC | S | 12-0235 | 2013-07-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
CAIN CORPORATION | S | 12-0235 | 2013-07-01 | 4 | 3 | 4 | 3 | 4 | 3 | 3
CARBIDE INDUSTRIES | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
CIRCLE B CONSTRUCTION SYSTEMS, LLC | S | 12-0235 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CLARK SALES & SERVICE INC. | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | 3 | 4 | 4 | Not on site
DEALERS WHOLESALE | S | 12-0235 | 2013-07-01 | 4 | 3 | 4 | 4 | 4 | 3 | 3
DEL-MONDE, INC. | S | 12-0235 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ELBRECHT INVESTMENTS LLC DBA ELBRECHT CONCRETE | S | 12-0235 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINAL CLEAN CORP. | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
GAYLOR, INC. | S | 12-0235 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
GLENMARK CONSTRUCTION | S | 12-0235 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HALL ALUMINUM | S | 12-0235 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HOOSIER PRESTRESS, INC. | S | 12-0235 | 2013-07-01 | 4 | 3 | 4 | 3 | 3 | 3 | 3
INDIANA STEEL FABRICATING, INC. | S | 12-0235 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
K & K FENCE, INC. | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
LEE SUPPLY CORPORATION | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
LIGHT-CRETE PRODUCTS & SERVICES, INC. | S | 12-0235 | 2013-07-01 | 4 | 5 | 4 | 4 | 4 | 4 | 4
MOMPER INSULATION | S | 12-0235 | 2013-07-01 | 5 | 5 | 5 | 4 | 4 | 4 | 4
OTIS ELEVATOR, USA | S | 12-0235 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OVERHEAD DOOR COMPANY OF ALBANY, INC | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
OYLER CONSTRUCTION | S | 12-0235 | 2013-07-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4
PROBUILD CO. LLC | S | 12-0235 | 2013-07-01 | 4 | 3 | 4 | 2 | 3 | 3 | 3
QUALITECK LLC | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Just started
ROBERT HAINES CO. | S | 12-0235 | 2013-07-01 | 5 | 2 | 4 | 2 | 3 | 3 | 3
ROGER WARD ENGINEERING, INC. | S | 12-0235 | 2013-07-01 | 5 | 2 | 3 | 2 | 3 | 3 | 2
SPD TEXTILE & DRAPERY, INC. | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
STEELCORE CONSTRUCTION CO. INC. | S | 12-0235 | 2013-07-01 | 4 | 2 | 4 | 2 | 3 | 3 | 2
TP MECHANICAL CONTRACTORS | S | 12-0235 | 2013-07-01 | 5 | 3 | 4 | 3 | 3 | 4 | 3
US AUTOMATIC FIRE & SECURITY | S | 12-0235 | 2013-07-01 | 4 | 3 | 4 | 2 | 3 | 4 | 4
VALENTI HELD, INC. | S | 12-0235 | 2013-07-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
VISION PAINTING | S | 12-0235 | 2013-07-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
WAGLER CUSTOM HOMES LLC | S | 12-0235 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WILSON-PARTENHEIMER, INC. | S | 12-0235 | 2013-07-01 | 4 | 3 | 4 | 3 | 3 | 4 | 4
MAX T. DOLAND | S | 12-0235 | 2013-07-01 | N/A | 5 | 5 | N/A | 4 | 5 | 4
ALLIANCE DOOR & HARDWARE | S | 12-0235 | 2013-07-01 | N/A | 4 | 5 | N/A | 4 | 4 | 4
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0235 | 2013-07-01 | N/A | 5 | 5 | N/A | 4 | 4 | 4
NATIONAL CONSTRUCTION RENTALS | S | 12-0235 | 2013-07-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
TRUSSWAY MFG. | S | 12-0235 | 2013-07-01 | N/A | 5 | 5 | N/A | 4 | 4 | 4
LAUNDRY CITY EQUIPMENT | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | Not on site
SYR BEAUTY | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
LOOMIS BROS. EQUIPMENT | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARK & DAN FRAMERS, INC | S | 12-0235 | 2013-07-01 | 5 | 4 | 4 | 4 | 4 | N/A | 4 | Procurement on this project
RUNYON EQUIPMENT | S | 12-0235 | 2013-07-01 | 5 | 5 | 5 | 5 | 4 | N/A | 5
RICHARDS BUILDING SUPPLY | S | 12-0235 | 2013-07-01 | N/A | 1 | 4 | N/A | 3 | 3 | 3
GEMINI ELECTRONIC | S | 12-0235 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
MOBILE AIR | S | 12-0235 | 2013-07-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4
BLOCH INDUSTRIES LLC | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E.S. FIRE SUPPRESSION | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINGER LAKES SERVICE GROUP, INC. | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL P&H INC. | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCGURK ELECTRIC, INC. | S | 12-0239 | 2013-07-01 | 4 | 5 | 4 | N/A | 1 | 1 | 1 | Slow office
O'CONNELL ELECTRIC COMPANY, INC | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ONTARIO EXTERIORS, INC | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 12-0239 | 2013-07-01 | 4 | 1 | 3 | 3 | 1 | 2 | 2 | Too much work and they are overwhelmed and under-staffed
STATEWIDE CONSTRUCTION INC | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINGER LAKES CUSTOM FENCE | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 12-0239 | 2013-07-01 | N/A | 3 | 3 | 3 | 3 | 3 | 3
HOCKENBERGS EQPT. & SUPPLY | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARK & DAN FRAMERS, INC | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 12-0239 | 2013-07-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4
RAMAR STEEL SALES, INC | S | 12-0239 | 2013-07-01 | N/A | 4 | N/A | 4 | 4 | 4 | 4
ROCHESTER COLONIAL MANUFACTURING | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUTHSIDE PRECAST | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WON-DOOR CORP. | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 12-0239 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGSTEN CONSTRUCTION | S | 12-0241 | 2013-07-01 | 4 | 3 | 4 | 4 | N/A | N/A | N/A
BPE CONSTRUCTION | S | 12-0241 | 2013-07-01 | 3 | 3 | 3 | 4 | N/A | N/A | N/A
BREWER & CO. OF WV, INC. | S | 12-0241 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
BUILDERS SERVICES GROUP (DAVENPORT) | S | 12-0241 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
CAPITOL BUSINESS INTERIORS | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHERRY RIVER CONST LLC | S | 12-0241 | 2013-07-01 | 4 | 3 | 3 | 3 | N/A | N/A | N/A
CONSTRUCTION AHEAD INC. | S | 12-0241 | 2013-07-01 | 4 | 3 | 4 | 3 | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 12-0241 | 2013-07-01 | 4 | 3 | 4 | 3 | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 12-0241 | 2013-07-01 | 5 | 5 | 5 | 4 | N/A | N/A | N/A
DESIGN ROOFING LLC | S | 12-0241 | 2013-07-01 | 3 | 2 | 3 | 4 | N/A | N/A | N/A
DODSON BROS. EXTERMINATING | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DOUGLAS EQUIPMENT | S | 12-0241 | 2013-07-01 | 4 | 3 | 4 | 4 | N/A | N/A | N/A
FAMILY CARPET OUTLET INC. | S | 12-0241 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
FIRESIDE & PATIO SHOP | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HARRIS BROS. ROOFING | S | 12-0241 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
HINZMAN CONSTRUCTION | S | 12-0241 | 2013-07-01 | 5 | 5 | 4 | 4 | N/A | N/A | N/A
JACKEL DEVELOPMENT, INC. | S | 12-0241 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
KING BROTHERS FABRICATION | S | 12-0241 | 2013-07-01 | 3 | 2 | 3 | 2 | N/A | N/A | N/A
NETRANOM COMMUNICATIONS | S | 12-0241 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PAYNE'S DRYWALL | S | 12-0241 | 2013-07-01 | 3 | 2 | 3 | 3 | N/A | N/A | N/A
PHILIPS LIFELINE | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PICKERING ASSOCIATES | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCK BRANCH MECHANICAL | S | 12-0241 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
TERRA CARE INC. | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D.W INC. | S | 13-0271 | 2013-12-01 | 5 | 3 | 4 | 4 | 4 | 4 | N/A | Works well with team
WHIRLPOOL CORPORATION | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WORKMAN & SONS PLBG. LLC | S | 12-0241 | 2013-07-01 | 3 | 4 | 3 | 3 | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL STATE INTERIORS | S | 12-0241 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
ARJOHUNTLEIGH INC. | S | 12-0241 | 2013-07-01 | 4 | 3 | 4 | 4 | N/A | N/A | N/A
B&L WHOLESALE | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRAGGS FRESH CONSTRUCTION | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CME ASSOCIATES | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CENTRAL GLASS CO. OF CHARLESTON | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHANDLER'S PLYWOOD PRODUCTS | S | 12-0241 | 2013-07-01 | N/A | 4 | 4 | 4 | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DURAFRAME, LLC | S | 12-0241 | 2013-07-01 | N/A | 3 | 3 | 3 | N/A | N/A | N/A
GYPSUM SYSTEMS, INC. | S | 12-0241 | 2013-07-01 | N/A | 3 | 3 | 3 | N/A | N/A | N/A
INSTALLED BLDG. PRODUCT LLC | S | 12-0241 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
J S ARCHER CO., INC. | S | 12-0241 | 2013-07-01 | N/A | 3 | 4 | N/A | N/A | N/A | N/A
PROBUILD CO. LLC | S | 12-0241 | 2013-07-01 | N/A | 3 | N/A | N/A | N/A | N/A | N/A
PROGRESSIVE SYSTEMS, INC. | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WEST VIRGINIA GLASS CO. | S | 12-0241 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D.W INC. | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | Couldn't provide bond and we are continually evaluating financials
AFSCO FENCE SUPPLY | S | 12-0246 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0246 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 12-0246 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B.R. JOHNSON | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
BUILDERS INSTALLED PRODUCTS | S | 12-0246 | 2013-07-01 | 4 | 3 | 3 | 3 | 3 | 1 | 3 | Took a very long time in providing submittals; Darren H on the job
CGM TILE & STONE, INC | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CARE CLEAN INC | S | 12-0246 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | Had safety violations
EDWARD & THOMAS O'CONNOR INC | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 3
L COON | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | Good team player and helped launch job in a good way
FLOWER CITY GLASS | S | 12-0246 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GENSON OVERHEAD DOOR, INC | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
HENRY ISAACS HOME REMODELING | S | 12-0246 | 2013-07-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
IRV SCHRODER AND SONS | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Good team player
JAG I, LLC | S | 12-0246 | 2013-07-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Do not hire again
K&K GUNITE POOL BUILDERS, INC | S | 12-0246 | 2013-07-01 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | Questionable financials; do not hire again
KONE, INC | S | 12-0246 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRUEGLER CONTRACTING & REMODELING, LLC | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3
MCCLAIN ASSOCIATES INC. | S | 12-0246 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCLEOD SYSTEMS, INC. | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OVERHEAD DOOR COMPANY OF ALBANY, INC | S | 12-0246 | 2013-07-01 | 4 | 3 | 4 | 4 | 4 | N/A | N/A
PENTEL DRYWALL | S | 12-0246 | 2013-07-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Needs improvement in all phases; Jason and Edin working closely
PINNACLE ROOFING INC | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Good new sub we found
PRO CARPET INC. | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 2 | 2
RBM GUARDIAN FIRE PROTECTION INC | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | Long time LCS sub
SHAWNLEE CONSTRUCTION LLC | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Did a good job
TRIPOINT STONE | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
VANDUSEN & STEVES LAND SURVEYORS | S | 12-0246 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDYKE PAINTING COMPANY | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 3 | N/A
WHIRLPOOL CORPORATION | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 12-0246 | 2013-07-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | Long time LCS sub
BGI INTERIORS | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | material supplier
B&L WHOLESALE | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier only
ALLIANCE DOOR & HARDWARE | S | 12-0246 | 2013-07-01 | 4 | 3 | 4 | 4 | 4 | 1 | 1 | Long term sub, but high maintainence
MAX T. DOLAND | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier only
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0246 | 2013-07-01 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | supplier only
SERWAY BROTHERS INC. | S | 12-0246 | 2013-07-01 | N/A | N/A | N/A | N/A | 3 | 3 | 3 | material only; Long term LCS sub, high maintainence
SPA DECORATING | S | 12-0246 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YORK BRIDGE CONCEPTS | S | 12-0246 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 12-0246 | 2013-07-01 | 4 | 3 | 4 | 3 | 4 | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0250 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BROCCOLO TREE & LAWN CARE | S | 12-0250 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COSTICH ENGINEERING | S | 12-0250 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 12-0250 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HEASTER BUILDING RESTORATION, INC | S | 12-0250 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 12-0250 | 2013-07-01 | 4 | 5 | 4 | 4 | N/A | 2 | 3 | Submittals do not come complete or on time
KENNEDY MECHANICAL P&H INC. | S | 12-0250 | 2013-07-01 | 4 | 3 | 4 | 3 | N/A | 3 | 3 | Just started
LANDMARK ELECTRIC INC | S | 12-0250 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
MESSNER FLOORING RESOURCE | S | 12-0250 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 12-0250 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 12-0250 | 2013-07-01 | 4 | 3 | 4 | 3 | N/A | 3 | 3
POOLER ENTERPIRSES, INC. | S | 12-0250 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 12-0250 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RAMAR STEEL SALES, INC | S | 12-0250 | 2013-07-01 | 5 | 5 | 4 | 5 | N/A | 5 | 4
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0250 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 12-0250 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 12-0250 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 12-0250 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 12-0250 | 2013-07-01 | 3 | 4 | 3 | 3 | N/A | 4 | 4
NATIONAL CONSTRUCTION RENTALS | S | 12-0250 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 12-0250 | 2013-07-01 | 4 | 5 | 5 | 5 | N/A | 4 | 4
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 12-0250 | 2013-07-01 | 4 | 5 | 5 | 5 | N/A | 4 | 4
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0250 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
COMFORT SYSTEMS/ BILLONE | S | 13-0252 | 2013-07-01 | 5 | 5 | 4 | 5 | N/A | 4 | 3 | Difficulty in dealing with owners
CEDAR ENTERPRISES | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS ENGINEERS | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0252 | 2013-07-01 | 5 | 5 | 5 | 4 | 5 | 5 | 5
FLOWER CITY GLASS | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 13-0252 | 2013-07-01 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | Need to be proactive with them
KENNEDY MECHANICAL P&H INC. | S | 13-0252 | 2013-07-01 | 5 | 5 | 5 | 5 | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCGURK ELECTRIC, INC. | S | 13-0252 | 2013-07-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
NEW YORK STATE FENCE, INC | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRIDE FIRE PROTECTION | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QUALITY CARPETS | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAMAR STEEL SALES, INC | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODSTONE EARTH CONSTRUCTION, INC | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Be prepared to argue, they are confrontational; issues with transparency and they will test you; be prepared to bring in team leader and outside consultants; great work execution though
LAKELANDS CONCRETE PRODUCTS | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAMILTON ENTERPRISES | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMI STRUCTURAL SOLUTIONS | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHLER AWNINGS | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
H-S INDUSTRIAL EQUIPMENT | S | 13-0252 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D CALL & SONS EXCAVAT. | S | 13-0262 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | Submittals have been late
CATENARY CONSTRUCTION CORP. | S | 13-0262 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
ES SYSTEMS, INC | S | 13-0262 | 2013-07-01 | 4 | N/A | N/A | N/A | N/A | 2 | 2 | Having trouble with this sub that is trying to submit products that don't match the specs; went to the day with getting the insurances in and execution of contract was not good
J&K CONSTRUCTION | S | 13-0262 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MADGE LAND SURVEYING P.C. | S | 13-0262 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MCGURK ELECTRIC, INC. | S | 13-0262 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 2 | 4
PRECISION CONCRETE AND MASONRY | S | 13-0262 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | 1 | 2 | Do not hire again
BILLONE MECHANICAL CONTRACTORS | S | 13-0264 | 2013-07-01 | 4 | 5 | 5 | 5 | 5 | 5 | 5
MJ MECHANICAL SERVICES, INC. | S | 13-0264 | 2013-07-01 | 4 | 5 | 5 | 5 | 5 | 5 | 5
MESSNER FLOORING RESOURCE | S | 13-0264 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 13-0264 | 2013-07-01 | 4 | 5 | 5 | 5 | 5 | 5 | 5
STATEWIDE CONSTRUCTION INC | S | 13-0264 | 2013-07-01 | 3 | 5 | 5 | 5 | 5 | 5 | 5
STILLWATER ENTERPRISES | S | 13-0264 | 2013-07-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
UPSTATE ROOFING & PAINTING, INC. | S | 13-0264 | 2013-07-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CONLEY CASEWORKS | S | 13-0264 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 13-0264 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE GLASSMAN, INC. | S | 13-0264 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM B. MORSE LUMBER- DOORS & FRAMES | S | 13-0264 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 CONTRACTORS INC. | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.R. PIERREPONT CO., INC | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 12-0228 | 2013-07-01 | 5 | 5 | 5 | 5 | 5 | N/A | 5
ACCURATE ACOUSTICAL, INC. | S | 12-0228 | 2013-07-01 | 3 | 3 | 4 | 3 | 4 | 4 | 3
ALPHA IRON WORKS, LLC | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&B MECHANICAL CONTRACTOR, INC | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&L WHOLESALE | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
DRAPERY INDUSTRIES, INC | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
EINSTEIN CONSTRUCTION CORP | S | 12-0228 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EMPIRE METAL FABRICATORS, INC | S | 12-0228 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRESTOP TECHNOLOGIES, INC | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
FRONTIER GLASS INC | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
GUARDIAN FIRE TESTING LABORATORIES | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
MONROE PIPING & SHEET METAL, LLC | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
NEW YORK STATE FENCE, INC | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 12-0228 | 2013-07-01 | 5 | 5 | 5 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 12-0228 | 2013-07-01 | 4 | 3 | 4 | 3 | 4 | 4 | 4
ROCHESTER COLONIAL MANUFACTURING | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SDC CONSTRUCTION SERVICES, INC | S | 12-0228 | 2013-07-01 | N/A | 2 | 3 | N/A | 4 | 2 | 2
SANITAIRE CLEANING CO., INC. | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCACCIA TILE & MARBLE INC. | S | 12-0228 | 2013-07-01 | 3 | 2 | 3 | 2 | 3 | 4 | 2
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
SWAN TILE, INC. | S | 12-0228 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4
ID SIGNSYSTEMS | S | 12-0228 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | 5 | 4
T.Y. LIN INTERNATIONAL | S | 12-0228 | 2013-07-01 | 5 | 5 | 5 | 5 | 4 | 4 | 4
COMFORT SYSTEMS/ BILLONE | S | 13-0252 | 2013-08-01 | 5 | 5 | 4 | 5 | N/A | 4 | 3 | Difficulty in dealing with owners
CEDAR ENTERPRISES | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS ENGINEERS | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0252 | 2013-08-01 | 5 | 5 | 5 | 4 | 5 | 5 | 5
FLOWER CITY GLASS | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 13-0252 | 2013-08-01 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | Need to be proactive with them
KENNEDY MECHANICAL P&H INC. | S | 13-0252 | 2013-08-01 | 4 | 3 | 5 | 3 | 3 | 3 | 3
LAKEVIEW LAWN & LANDSCAPE | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0252 | 2013-08-01 | 5 | 1 | 5 | 1 | 4 | 4 | 4 | Schedule with Keith
MCGURK ELECTRIC, INC. | S | 13-0252 | 2013-08-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
NEW YORK STATE FENCE, INC | S | 13-0252 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRIDE FIRE PROTECTION | S | 13-0252 | 2013-08-01 | 5 | 5 | 4 | 4 | 4 | 3 | 4
QUALITY CARPETS | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
RAMAR STEEL SALES, INC | S | 13-0252 | 2013-08-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
SCHINDLER ELEVATOR | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0252 | 2013-08-01 | 3 | 4 | 5 | 3 | 2 | 1 | 2 | They are over-extended.
WOODSTONE EARTH CONSTRUCTION, INC | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Be prepared to argue, they are confrontational; issues with transparency and they will test you; be prepared to bring in team leader and outside consultants; great work execution though
LAKELANDS CONCRETE PRODUCTS | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
HAMILTON ENTERPRISES | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMI STRUCTURAL SOLUTIONS | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHLER AWNINGS | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
H-S INDUSTRIAL EQUIPMENT | S | 13-0252 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D.W INC. | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | Couldn't provide bond and we are continually evaluating financials
AFSCO FENCE SUPPLY | S | 12-0246 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0246 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 12-0246 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B.R. JOHNSON | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
BUILDERS INSTALLED PRODUCTS | S | 12-0246 | 2013-08-01 | 4 | 3 | 3 | 3 | 3 | 1 | 3 | Took a very long time in providing submittals; Darren H on the job
CGM TILE & STONE, INC | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CARE CLEAN INC | S | 12-0246 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | Had safety violations
EDWARD & THOMAS O'CONNOR INC | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 3
L COON | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | Good team player and helped launch job in a good way
FLOWER CITY GLASS | S | 12-0246 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GENSON OVERHEAD DOOR, INC | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
HENRY ISAACS HOME REMODELING | S | 12-0246 | 2013-08-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
IRV SCHRODER AND SONS | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Good team player
JAG I, LLC | S | 12-0246 | 2013-08-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Do not hire again
K&K GUNITE POOL BUILDERS, INC | S | 12-0246 | 2013-08-01 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | Questionable financials; do not hire again
KONE, INC | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
KRUEGLER CONTRACTING & REMODELING, LLC | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3
MCCLAIN ASSOCIATES INC. | S | 12-0246 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCLEOD SYSTEMS, INC. | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OVERHEAD DOOR COMPANY OF ALBANY, INC | S | 12-0246 | 2013-08-01 | 4 | 3 | 4 | 4 | 4 | N/A | N/A
PENTEL DRYWALL | S | 12-0246 | 2013-08-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Needs improvement in all phases; Jason and Edin working closely
PINNACLE ROOFING INC | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Good new sub we found
PRO CARPET INC. | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 2 | 2
RBM GUARDIAN FIRE PROTECTION INC | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | Long time LCS sub
SHAWNLEE CONSTRUCTION LLC | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Did a good job
TRIPOINT STONE | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
BAST HATFIELD CONSTRUCTION, LLC (STONE) | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 3 | 3
VANDUSEN & STEVES LAND SURVEYORS | S | 12-0246 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDYKE PAINTING COMPANY | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 3 | N/A
WHIRLPOOL CORPORATION | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 12-0246 | 2013-08-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | Long time LCS sub
BGI INTERIORS | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | material supplier
B&L WHOLESALE | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier only
ALLIANCE DOOR & HARDWARE | S | 12-0246 | 2013-08-01 | 4 | 3 | 4 | 4 | 4 | 1 | 1 | Long term sub, but high maintainence
MAX T. DOLAND | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier only
WM B. MORSE LUMBER- DOORS & FRAMES | S | 12-0246 | 2013-08-01 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | supplier only
SERWAY BROTHERS INC. | S | 12-0246 | 2013-08-01 | N/A | N/A | N/A | N/A | 3 | 3 | 3 | material only; Long term LCS sub, high maintainence
SPA DECORATING | S | 12-0246 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YORK BRIDGE CONCEPTS | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SHEPARDVILLE | S | 12-0246 | 2013-08-01 | 4 | 3 | 4 | 3 | 4 | N/A | N/A
A.D CALL & SONS EXCAVAT. | S | 13-0262 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | Submittals have been late
AGAPE WHOLESALE FURNITURE | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BROCCOLO TREE & LAWN CARE | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 13-0262 | 2013-08-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
ES SYSTEMS, INC | S | 13-0262 | 2013-08-01 | 4 | N/A | N/A | N/A | N/A | 2 | 2 | Having trouble with this sub that is trying to submit products that don't match the specs; went to the day with getting the insurances in and execution of contract was not good
HENRY ISAACS HOME REMODELING | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&K CONSTRUCTION | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MADGE LAND SURVEYING P.C. | S | 13-0262 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MCGURK ELECTRIC, INC. | S | 13-0262 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 2 | 4
NEW YORK STATE FENCE, INC | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRECISION CONCRETE AND MASONRY | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | 1 | 2 | Do not hire again
ROCHESTER FLOORING RESOURCE | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDYKE PAINTING COMPANY | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORANDEX INC. | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURAIN IRIGATION SYSTEMS | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BROCCOLO TREE & LAWN CARE | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BROCCOLO TREE & LAWN CARE | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COSTICH ENGINEERING | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENVIRONMENTAL SERVICES UNLIMITED | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRESTOP SOLUTIONS, INC. | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HEASTER BUILDING RESTORATION, INC | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 12-0250 | 2013-08-14 | 4 | 5 | 4 | 4 | N/A | 2 | 3 | Submittals do not come complete or on time
KENNEDY MECHANICAL P&H INC. | S | 12-0250 | 2013-08-14 | 4 | 3 | 4 | 3 | N/A | 3 | 3 | Just started
LANDMARK ELECTRIC INC | S | 12-0250 | 2013-08-14 | 4 | 4 | 4 | 4 | N/A | 4 | 4
MESSNER FLOORING RESOURCE | S | 12-0250 | 2013-08-14 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NEW YORK STATE FENCE, INC | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAST HATFIELD CONSTRUCTION, LLC (STONE) | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 3 | 3
RAMAR STEEL SALES, INC | S | 12-0250 | 2013-08-14 | 5 | 5 | 4 | 5 | N/A | 5 | 4
STILLWATER ENTERPRISES | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0250 | 2013-08-14 | 4 | 1 | 3 | 3 | 4 | 4 | 1
US CEILING CORP. | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 12-0250 | 2013-08-14 | 4 | 4 | 4 | 4 | N/A | N/A | 4
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 12-0250 | 2013-08-14 | 4 | 5 | 5 | 5 | N/A | 4 | 4
WECKESSER BRICK | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 12-0250 | 2013-08-14 | 4 | 4 | 4 | 4 | N/A | 4 | 4
COMFORT SYSTEMS/ BILLONE | S | 13-0252 | 2013-08-14 | 5 | 5 | 4 | 5 | N/A | 4 | 3 | Difficulty in dealing with owners
CEDAR ENTERPRISES | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS ENGINEERS | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0252 | 2013-08-14 | 5 | 5 | 5 | 4 | 5 | 5 | 5
FLOWER CITY GLASS | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 13-0252 | 2013-08-14 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | Need to be proactive with them
KENNEDY MECHANICAL P&H INC. | S | 13-0252 | 2013-08-14 | 4 | 3 | 5 | 3 | 3 | 3 | 3
LAKEVIEW LAWN & LANDSCAPE | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0252 | 2013-08-14 | 5 | 1 | 5 | 1 | 4 | 4 | 4 | Schedule with Keith
MCGURK ELECTRIC, INC. | S | 13-0252 | 2013-08-14 | 5 | 5 | 5 | 5 | 5 | 5 | 5
NEW YORK STATE FENCE, INC | S | 13-0252 | 2013-08-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRIDE FIRE PROTECTION | S | 13-0252 | 2013-08-14 | 5 | 5 | 4 | 4 | 4 | 3 | 4
QUALITY CARPETS | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | 3 | 3
RAMAR STEEL SALES, INC | S | 13-0252 | 2013-08-14 | 5 | 5 | 5 | 5 | 5 | 5 | 5
SCHINDLER ELEVATOR | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0252 | 2013-08-14 | 3 | 4 | 5 | 3 | 2 | 1 | 2 | They are over-extended.
WOODSTONE EARTH CONSTRUCTION, INC | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Be prepared to argue, they are confrontational; issues with transparency and they will test you; be prepared to bring in team leader and outside consultants; great work execution though
LAKELANDS CONCRETE PRODUCTS | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAMILTON ENTERPRISES | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMI STRUCTURAL SOLUTIONS | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHLER AWNINGS | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
H-S INDUSTRIAL EQUIPMENT | S | 13-0252 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BLOCH INDUSTRIES LLC | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E.S. FIRE SUPPRESSION | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINGER LAKES SERVICE GROUP, INC. | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOCKENBERGS EQPT. & SUPPLY | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL P&H INC. | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARK & DAN FRAMERS, INC | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCCLAIN ASSOCIATES INC. | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCGURK ELECTRIC, INC. | S | 12-0239 | 2013-08-07 | 4 | 5 | 4 | N/A | 1 | 1 | 1 | Slow office
O'CONNELL ELECTRIC COMPANY, INC | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ONTARIO EXTERIORS, INC | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 12-0239 | 2013-08-07 | 4 | 1 | 3 | 3 | 1 | 2 | 2 | Too much work and they are overwhelmed and under-staffed
PRO CARPET INC. | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SANITAIRE CLEANING CO., INC. | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCACCIA TILE & MARBLE INC. | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STATEWIDE CONSTRUCTION INC | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WON-DOOR CORP. | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CRICKET ON THE HEARTH | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINGER LAKES CUSTOM FENCE | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 12-0239 | 2013-08-07 | N/A | 3 | 3 | 3 | 3 | 3 | 3
FORMATRON LTD. | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 12-0239 | 2013-08-07 | N/A | 4 | 4 | 4 | 4 | 4 | 4
RAMAR STEEL SALES, INC | S | 12-0239 | 2013-08-07 | N/A | 4 | N/A | 4 | 4 | 4 | 4
ROCHESTER COLONIAL MANUFACTURING | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUTHSIDE PRECAST | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 12-0239 | 2013-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D.W INC. | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | Couldn't provide bond and we are continually evaluating financials
AFSCO FENCE SUPPLY | S | 12-0246 | 2013-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0246 | 2013-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 12-0246 | 2013-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B.R. JOHNSON | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 3 | 3
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
BUILDERS INSTALLED PRODUCTS | S | 12-0246 | 2013-08-08 | 4 | 3 | 3 | 3 | 3 | 1 | 3 | Took a very long time in providing submittals; Darren H on the job
CGM TILE & STONE, INC | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CARE CLEAN INC | S | 12-0246 | 2013-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | Had safety violations
EDWARD & THOMAS O'CONNOR INC | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | 3
L COON | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | Good team player and helped launch job in a good way
FLOWER CITY GLASS | S | 12-0246 | 2013-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GENSON OVERHEAD DOOR, INC | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
HENRY ISAACS HOME REMODELING | S | 12-0246 | 2013-08-08 | 4 | 3 | 4 | 4 | 4 | 4 | 4
IRV SCHRODER AND SONS | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Good team player
JAG I, LLC | S | 12-0246 | 2013-08-08 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Do not hire again
K&K GUNITE POOL BUILDERS, INC | S | 12-0246 | 2013-08-08 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | Questionable financials; do not hire again
KONE, INC | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4
KRUEGLER CONTRACTING & REMODELING, LLC | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 3 | 3
MCCLAIN ASSOCIATES INC. | S | 12-0246 | 2013-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCLEOD SYSTEMS, INC. | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OVERHEAD DOOR COMPANY OF ALBANY, INC | S | 12-0246 | 2013-08-08 | 4 | 3 | 4 | 4 | 4 | N/A | N/A
PENTEL DRYWALL | S | 12-0246 | 2013-08-08 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Needs improvement in all phases; Jason and Edin working closely
PINNACLE ROOFING INC | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Good new sub we found
PRO CARPET INC. | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 2 | 2
RBM GUARDIAN FIRE PROTECTION INC | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | Long time LCS sub
SHAWNLEE CONSTRUCTION LLC | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Did a good job
TRIPOINT STONE | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
VANDUSEN & STEVES LAND SURVEYORS | S | 12-0246 | 2013-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDYKE PAINTING COMPANY | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 3 | N/A
WHIRLPOOL CORPORATION | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 12-0246 | 2013-08-08 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | Long time LCS sub
BGI INTERIORS | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | material supplier
B&L WHOLESALE | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier only
ALLIANCE DOOR & HARDWARE | S | 12-0246 | 2013-08-08 | 4 | 3 | 4 | 4 | 4 | 1 | 1 | Long term sub, but high maintainence
MAX T. DOLAND | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier only
WM. B. MORSE LUMBER CO. | S | 12-0246 | 2013-08-08 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | supplier only
SERWAY BROTHERS INC. | S | 12-0246 | 2013-08-08 | N/A | N/A | N/A | N/A | 3 | 3 | 3 | material only; Long term LCS sub, high maintainence
SPA DECORATING | S | 12-0246 | 2013-08-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YORK BRIDGE CONCEPTS | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SHEPARDVILLE | S | 12-0246 | 2013-08-08 | 4 | 3 | 4 | 3 | 4 | N/A | N/A
104 CONTRACTORS INC. | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.R. PIERREPONT CO., INC | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 12-0228 | 2013-08-14 | 5 | 5 | 5 | 5 | 4 | N/A | 5
DIVAL SAFETY EQUIPMENT | S | 12-0228 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE DUKE COMPANY | S | 12-0228 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNGBLOOD DISPOSAL | S | 12-0228 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 12-0228 | 2013-08-14 | 3 | 3 | 4 | 3 | 4 | 4 | 3
ALPHA IRON WORKS, LLC | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&B MECHANICAL CONTRACTOR, INC | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&L WHOLESALE | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
DRAPERY INDUSTRIES, INC | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
EINSTEIN CONSTRUCTION CORP | S | 12-0228 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EMPIRE METAL FABRICATORS, INC | S | 12-0228 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRESTOP TECHNOLOGIES, INC | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
FRONTIER GLASS INC | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
GUARDIAN FIRE TESTING LABORATORIES | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
MONROE PIPING & SHEET METAL, LLC | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
COMMERICAL PIPE & SUPPLY | S | 12-0228 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FERGUSON ENTERPRISES | S | 12-0228 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TYCO FIRE PROTECTION PRODUCTS | S | 12-0228 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 12-0228 | 2013-08-14 | 5 | 5 | 5 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 12-0228 | 2013-08-14 | 4 | 3 | 4 | 3 | 4 | 4 | 4
GC FLOORING | S | 12-0228 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCHESTER COLONIAL MANUFACTURING | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SDC CONSTRUCTION SERVICES, INC | S | 12-0228 | 2013-08-14 | N/A | 2 | 3 | N/A | 4 | 2 | 2
SANITAIRE CLEANING CO., INC. | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCACCIA TILE & MARBLE INC. | S | 12-0228 | 2013-08-14 | 3 | 2 | 3 | 2 | 3 | 4 | 3
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SWAN TILE, INC. | S | 12-0228 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | 4
ID SIGNSYSTEMS | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | N/A | 5 | 4
T.Y. LIN INTERNATIONAL | S | 12-0228 | 2013-08-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.D CALL & SONS EXCAVAT. | S | 13-0262 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | Submittals have been late
AGAPE WHOLESALE FURNITURE | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BROCCOLO TREE & LAWN CARE | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 13-0262 | 2013-08-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
ES SYSTEMS, INC | S | 13-0262 | 2013-08-01 | 4 | N/A | N/A | N/A | N/A | 2 | 2 | Having trouble with this sub that is trying to submit products that don't match the specs; went to the day with getting the insurances in and execution of contract was not good
HENRY ISAACS HOME REMODELING | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&K CONSTRUCTION | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MADGE LAND SURVEYING P.C. | S | 13-0262 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MCGURK ELECTRIC, INC. | S | 13-0262 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 2 | 4
NEW YORK STATE FENCE, INC | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRECISION CONCRETE AND MASONRY | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | 1 | 2 | Do not hire again
ROCHESTER FLOORING RESOURCE | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDYKE PAINTING COMPANY | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORANDEX INC. | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM B. MORSE LUMBER (LUMBER/HOUSE WRAP) | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRIDGEWATER INTERNATIONAL | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM B MORSE LUMBER (FINISH CARPENTRY) | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.R. PIERREPONT CO., INC | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 12-0228 | 2013-08-28 | 5 | 5 | 5 | 5 | 4 | N/A | 5
DIVAL SAFETY EQUIPMENT | S | 12-0228 | 2013-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE DUKE COMPANY | S | 12-0228 | 2013-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNGBLOOD DISPOSAL | S | 12-0228 | 2013-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 12-0228 | 2013-08-28 | 3 | 3 | 4 | 3 | 4 | 4 | 3
ALPHA IRON WORKS, LLC | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&B MECHANICAL CONTRACTOR, INC | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&L WHOLESALE | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
DRAPERY INDUSTRIES, INC | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
EINSTEIN CONSTRUCTION CORP | S | 12-0228 | 2013-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EMPIRE METAL FABRICATORS, INC | S | 12-0228 | 2013-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRESTOP TECHNOLOGIES, INC | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
FRONTIER GLASS INC | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
GUARDIAN FIRE TESTING LABORATORIES | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
MONROE PIPING & SHEET METAL, LLC | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
COMMERICAL PIPE & SUPPLY | S | 12-0228 | 2013-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FERGUSON ENTERPRISES | S | 12-0228 | 2013-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TYCO FIRE PROTECTION PRODUCTS | S | 12-0228 | 2013-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 12-0228 | 2013-08-28 | 5 | 5 | 5 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 12-0228 | 2013-08-28 | 4 | 3 | 4 | 3 | 4 | 4 | 4
GC FLOORING | S | 12-0228 | 2013-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCHESTER COLONIAL MANUFACTURING | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SDC CONSTRUCTION SERVICES, INC | S | 12-0228 | 2013-08-28 | N/A | 2 | 3 | N/A | 4 | 2 | 2
SANITAIRE CLEANING CO., INC. | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCACCIA TILE & MARBLE INC. | S | 12-0228 | 2013-08-28 | 2 | 2 | 3 | 2 | 3 | 4 | 1 | Always needs money; difficult sub to work with; doesn't provide promised man power
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SWAN TILE, INC. | S | 12-0228 | 2013-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | 4
ID SIGNSYSTEMS | S | 12-0228 | 2013-08-28 | 4 | 2 | 3 | 4 | N/A | 5 | 2 | Difficult time getting responses about scheduling and manpower
T.Y. LIN INTERNATIONAL | S | 12-0228 | 2013-08-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
COMFORT SYSTEMS/ BILLONE | S | 13-0252 | 2013-09-04 | 5 | 5 | 4 | 5 | N/A | 4 | 5 | Difficulty in dealing with owners
CEDAR ENTERPRISES | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS ENGINEERS | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0252 | 2013-09-04 | 5 | 5 | 5 | 4 | 5 | 5 | 5
FLOWER CITY GLASS | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 13-0252 | 2013-09-04 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | Need to be proactive with them
KENNEDY MECHANICAL P&H INC. | S | 13-0252 | 2013-09-04 | 4 | 1 | 1 | 2 | 3 | 3 | 3 | They have not acted like a partner and they are not professional; they work attitude spreads to other subs and workers; they has zero communication between field and office so when their workers showed up they were not preapred to work and have caused schedule delays
LAKEVIEW LAWN & LANDSCAPE | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0252 | 2013-09-04 | 5 | 1 | 5 | 1 | 4 | 4 | 4 | Schedule with Keith
MCGURK ELECTRIC, INC. | S | 13-0252 | 2013-09-04 | 5 | 5 | 5 | 5 | 5 | 5 | 5
NEW YORK STATE FENCE, INC | S | 13-0252 | 2013-09-04 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRIDE FIRE PROTECTION | S | 13-0252 | 2013-09-04 | 5 | 5 | 4 | 4 | 4 | 3 | 4
QUALITY CARPETS | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | 3 | 3
RAMAR STEEL SALES, INC | S | 13-0252 | 2013-09-04 | 5 | 5 | 5 | 5 | 5 | 5 | 5
SCHINDLER ELEVATOR | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0252 | 2013-09-04 | 3 | 4 | 5 | 3 | 2 | 1 | 2 | They care about their work, but are over-extended.
WOODSTONE EARTH CONSTRUCTION, INC | S | 13-0252 | 2013-09-04 | 4 | 3 | 3 | 3 | N/A | 4 | 4 | Be prepared to argue, they are confrontational; issues with transparency and they will test you; be prepared to bring in team leader and outside consultants; great work execution though
LAKELANDS CONCRETE PRODUCTS | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAMILTON ENTERPRISES | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMI STRUCTURAL SOLUTIONS | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHLER AWNINGS | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
H-S INDUSTRIAL EQUIPMENT | S | 13-0252 | 2013-09-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.M. STERN, INC. | S | 11-0222 | 2013-09-05 | 4 | 4 | 4 | 4 | 2 | 4 | 3
AAC CONTRACTING, INC. | S | 11-0222 | 2013-09-05 | 3 | 4 | 2 | 4 | 2 | N/A | 4
AJAY GLASS & MIRROR | S | 11-0222 | 2013-09-05 | 4 | 2 | 4 | 2 | 4 | 2 | 1
ASSA ABLOY ENTRANCE SYSTEMS | S | 11-0222 | 2013-09-05 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ABSCOPE ENVIRONMENTAL INC. | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 11-0222 | 2013-09-05 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BAY TILE MARBLE & TERRAZZO | S | 11-0222 | 2013-09-05 | 4 | 4 | 4 | 4 | 5 | 4 | 4
C.A. REED ASSOCIATES | S | 11-0222 | 2013-09-05 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 11-0222 | 2013-09-05 | 4 | 4 | 4 | 4 | 3 | 4 | 4
CECO CONCRETE CONST. | S | 11-0222 | 2013-09-05 | 4 | 3 | 4 | 4 | 3 | 4 | 4
DECON STUDRAIL, INC. | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 11-0222 | 2013-09-05 | 3 | 2 | 3 | 2 | 4 | 3 | 2
CONNOR FENCE COMPANY INC. | S | 11-0222 | 2013-09-05 | 4 | 4 | 4 | 4 | 2 | N/A | 2
E.S. FIRE SUPPRESSION | S | 11-0222 | 2013-09-05 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ELEVATOR MAINTENANCE OF BUFFALO | S | 11-0222 | 2013-09-05 | 5 | 5 | 5 | 5 | 5 | 5 | 5
EMPIRE STATE MECHANICAL | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 11-0222 | 2013-09-05 | 4 | 4 | 4 | 4 | 4 | 4 | 5
FRANK J. MARIANACCI INC. | S | 11-0222 | 2013-09-05 | 3 | 4 | 3 | 4 | 3 | N/A | 2
G&J CONTRACTING INC | S | 11-0222 | 2013-09-05 | 2 | 3 | 4 | 3 | 4 | N/A | 2
GENEVA AWNING & TENT WORKS | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRECO PAINTING | S | 11-0222 | 2013-09-05 | 3 | 3 | 2 | 3 | 3 | 1 | 2
GYPSUM SYSTEMS, INC. | S | 11-0222 | 2013-09-05 | 4 | 3 | 3 | 3 | 3 | 4 | 3
HENRIETTA BUILDING SUPPLIES, INC. | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HERBERT F. DARLING, INC. | S | 11-0222 | 2013-09-05 | 4 | 1 | 4 | 3 | 2 | 2 | 1
HOUTENBRINK'S INC. | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMPERIAL DOOR CONTROLS, INC. | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 11-0222 | 2013-09-05 | 3 | 4 | 3 | 4 | 4 | 4 | 4 | Good
JOSEPHINE'S CLEANING SERVICE, LLC | S | 11-0222 | 2013-09-05 | 3 | 4 | 4 | 4 | 4 | N/A | 4
KLEIN REINFORCING SERVICES | S | 11-0222 | 2013-09-05 | N/A | 3 | 4 | N/A | 3 | 3 | 3
KOCHER SURVEYING, P.C. | S | 11-0222 | 2013-09-05 | 4 | 4 | 4 | 4 | N/A | N/A | 4
LAKEVIEW LAWN & LANDSCAPE | S | 11-0222 | 2013-09-05 | 3 | 3 | 3 | 3 | 4 | 1 | 3
SESSLER EXCAVATING | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
O'CONNELL ELECTRIC COMPANY, INC | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERHEAD DOOR COMPANY OF ALBANY, INC | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 11-0222 | 2013-09-05 | 3 | 3 | 3 | 2 | 1 | 3 | 1
POSTLER & JAECKLE CORP. | S | 11-0222 | 2013-09-05 | 3 | 3 | 3 | 3 | 2 | 4 | 2
PRO CARPET INC. | S | 11-0222 | 2013-09-05 | 3 | 4 | 3 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 11-0222 | 2013-09-05 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | Need push
RAMAR STEEL SALES, INC | S | 11-0222 | 2013-09-05 | 4 | 4 | 5 | 4 | 4 | 4 | 4
STILLWATER ENTERPRISES | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWIFTLIFT INC. | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWISSLOG (TRANSLOGIC CORP.) | S | 11-0222 | 2013-09-05 | 3 | 2 | 3 | 2 | 2 | 1 | 1
TLM EXCAVATING & ASSOCIATES | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE TRANE COMPANY | S | 11-0222 | 2013-09-05 | 3 | 3 | 3 | 3 | 4 | 3 | 3
THYSSENKRUPP ELEVATOR | S | 11-0222 | 2013-09-05 | N/A | 2 | N/A | N/A | 2 | 1 | 1
UPSTATE ROOFING & PAINTING, INC. | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
V&B UNDERGROUND UTILITIES INC. | S | 11-0222 | 2013-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 11-0222 | 2013-09-05 | 3 | 3 | 3 | 3 | 3 | 3 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BLOCH INDUSTRIES LLC | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 1 | 3 | Submittals took too long and were poor quality
E.S. FIRE SUPPRESSION | S | 12-0239 | 2013-09-06 | 4 | 2 | 4 | 1 | 4 | 4 | 4 | Not providing enough manpower
FORMATRON LTD. | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINGER LAKES SERVICE GROUP, INC. | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOCKENBERGS EQPT. & SUPPLY | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4
JACHLES IMPERIAL LTD | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | 4
KENNEDY MECHANICAL PLUMBING DIV. | S | 12-0239 | 2013-09-06 | 4 | 4 | 4 | 4 | 4 | 1 | 4
KENNEDY HVAC | S | 12-0239 | 2013-09-06 | 4 | 3 | 3 | 4 | 4 | 3 | 4
LAKEVIEW LAWN & LANDSCAPE | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 12-0239 | 2013-09-06 | 3 | 3 | 3 | 3 | 3 | 3 | 3
MARK & DAN FRAMERS, INC | S | 12-0239 | 2013-09-06 | 4 | 3 | 4 | 3 | 3 | N/A | N/A
MCCLAIN ASSOCIATES INC. | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCGURK ELECTRIC, INC. | S | 12-0239 | 2013-09-06 | 4 | 3 | 4 | 4 | 3 | 1 | 1 | Slow office, overloaded
ONTARIO EXTERIORS, INC | S | 12-0239 | 2013-09-06 | 3 | N/A | N/A | 4 | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 12-0239 | 2013-09-06 | 4 | 1 | 3 | 3 | 1 | 3 | 2 | Difficult to get them here when we need them
SANITAIRE CLEANING CO., INC. | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCACCIA TILE & MARBLE INC. | S | 12-0239 | 2013-09-06 | N/A | 2 | N/A | 3 | N/A | 2 | 2 | Difficult to contact, must hold hand
STATEWIDE CONSTRUCTION INC | S | 12-0239 | 2013-09-06 | 3 | 3 | 3 | 3 | 5 | 4 | 4
CRICKET ON THE HEARTH | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4
FINGER LAKES CUSTOM FENCE | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 12-0239 | 2013-09-06 | N/A | 4 | 3 | 3 | 3 | 3 | 3
MONTGOMERY TRUSS | S | 12-0239 | 2013-09-06 | N/A | 4 | 5 | 4 | 4 | 4 | 4
RAMAR STEEL SALES, INC | S | 12-0239 | 2013-09-06 | N/A | 4 | N/A | 4 | 4 | 4 | 4
ROCHESTER COLONIAL MANUFACTURING | S | 12-0239 | 2013-09-06 | N/A | 1 | N/A | 2 | 2 | 1 | 2 | Inter office communication is poor; have not met schedule and is difficult to get pricing from them for an ASI
SOUTHSIDE PRECAST | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 3
WM. B. MORSE LUMBER CO. | S | 12-0239 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4
A.D CALL & SONS EXCAVAT. | S | 13-0262 | 2013-09-06 | 4 | 4 | 4 | 4 | 1 | 2 | 4 | Submittals have been late
AGAPE WHOLESALE FURNITURE | S | 13-0262 | 2013-09-06 | 4 | 4 | 4 | 4 | 4 | 3 | 4
BROCCOLO TREE & LAWN CARE | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | They are inexperienced with submittals and paperwork and insurances, however their workmanship is supposed to be very good
CATENARY CONSTRUCTION CORP. | S | 13-0262 | 2013-09-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ES SYSTEMS, INC | S | 13-0262 | 2013-09-06 | 4 | 2 | 4 | 1 | 3 | 2 | 3 | Having trouble with this sub that is trying to submit products that don't match the specs; went to the day with getting the insurances in and execution of contract was not good; constantly under-staffed
HENRY ISAACS HOME REMODELING | S | 13-0262 | 2013-09-06 | 4 | 4 | 4 | 4 | 4 | 4 | 3
J&K CONSTRUCTION | S | 13-0262 | 2013-09-06 | 4 | 5 | 4 | 4 | 4 | 4 | 4
J&R SPECIALTIES | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 3 | 4
JOSEPHINE'S CLEANING SERVICE, LLC | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 3 | 4
MADGE LAND SURVEYING P.C. | S | 13-0262 | 2013-09-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MCGURK ELECTRIC, INC. | S | 13-0262 | 2013-09-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
NEW YORK STATE FENCE, INC | S | 13-0262 | 2013-09-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRECISION CONCRETE AND MASONRY | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 1 | 2 | This company is not suited to perform the type of work we do
ROCHESTER FLOORING RESOURCE | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | Submitted products that did not meet the spec; we had to bring them in because their submittal for sheet vinyl was going to hold up the job; office is not responsive
SCHINDLER ELEVATOR | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 3
US CEILING CORP. | S | 13-0262 | 2013-09-06 | 4 | 4 | 4 | 4 | 4 | 4 | 5
US CEILING CORP. | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDYKE PAINTING COMPANY | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 3 | 3
WINDOW ACCENTS INC. | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
MAX T. DOLAND | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
MONTGOMERY TRUSS | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
NORANDEX INC. | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
SERWAY BROTHERS INC. | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
WM B. MORSE LUMBER (LUMBER/HOUSE WRAP) | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
WM B MORSE LUMBER (FINISH CARPENTRY) | S | 13-0262 | 2013-09-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
A.D.W INC. | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | Couldn't provide bond and we are continually evaluating financials
AFSCO FENCE SUPPLY | S | 12-0246 | 2013-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0246 | 2013-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 12-0246 | 2013-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B.R. JOHNSON | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
BRIDGEWATER INTERNATIONAL | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 3 | 3
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
BUILDERS INSTALLED PRODUCTS | S | 12-0246 | 2013-09-12 | 4 | 3 | 3 | 3 | 3 | 1 | 3 | Took a very long time in providing submittals; Darren H on the job
CGM TILE & STONE, INC | S | 12-0246 | 2013-09-12 | 4 | 2 | 4 | 2 | 4 | 4 | 4 | Have experienced manpower issues with this sub
CARE CLEAN INC | S | 12-0246 | 2013-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | Had safety violations
EDWARD & THOMAS O'CONNOR INC | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | 3
L COON | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | Good team player and helped launch job in a good way
FLOWER CITY GLASS | S | 12-0246 | 2013-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GENSON OVERHEAD DOOR, INC | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
HENRY ISAACS HOME REMODELING | S | 12-0246 | 2013-09-12 | 4 | 3 | 3 | 3 | 4 | 4 | 3
IRV SCHRODER AND SONS | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Good team player
JAG I, LLC | S | 12-0246 | 2013-09-12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Left the site and created a $60K liability; this sub does not meet Lecesse standards
K&K GUNITE POOL BUILDERS, INC | S | 12-0246 | 2013-09-12 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | Questionable financials; this sub does not meet Lecesse standards
KONE, INC | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | 4
KRUEGLER CONTRACTING & REMODELING, LLC | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 3 | 3
MCCLAIN ASSOCIATES INC. | S | 12-0246 | 2013-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCLEOD SYSTEMS, INC. | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OVERHEAD DOOR COMPANY OF ALBANY, INC | S | 12-0246 | 2013-09-12 | 4 | 3 | 4 | 4 | 4 | N/A | N/A
PENTEL DRYWALL | S | 12-0246 | 2013-09-12 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Needs improvement in all phases; Jason and Edin working closely
PINNACLE ROOFING INC | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Good new sub we found
PRO CARPET INC. | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 2 | 2
RBM GUARDIAN FIRE PROTECTION INC | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | Long time LCS sub
SHAWNLEE CONSTRUCTION LLC | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Did a good job
TRIPOINT STONE | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
VANDUSEN & STEVES LAND SURVEYORS | S | 12-0246 | 2013-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDYKE PAINTING COMPANY | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 3 | N/A
WHIRLPOOL CORPORATION | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 12-0246 | 2013-09-12 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | Long time LCS sub
BGI INTERIORS | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | material supplier
B&L WHOLESALE | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier only
ALLIANCE DOOR & HARDWARE | S | 12-0246 | 2013-09-12 | 4 | 3 | 4 | 4 | 4 | 1 | 1 | Long term sub, but high maintainence
MAX T. DOLAND | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier only
WM. B. MORSE LUMBER CO. | S | 12-0246 | 2013-09-12 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | supplier only
SERWAY BROTHERS INC. | S | 12-0246 | 2013-09-12 | N/A | N/A | N/A | N/A | 3 | 3 | 3 | material only; Long term LCS sub, high maintainence
SPA DECORATING | S | 12-0246 | 2013-09-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YORK BRIDGE CONCEPTS | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SHEPARDVILLE | S | 12-0246 | 2013-09-12 | 4 | 3 | 4 | 3 | 4 | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0250 | 2013-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURAIN IRIGATION SYSTEMS | S | 12-0250 | 2013-09-11 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 12-0250 | 2013-09-11 | 4 | 4 | 4 | 4 | 3 | 4 | N/A
BROCCOLO TREE & LAWN CARE | S | 12-0250 | 2013-09-11 | 4 | 4 | 4 | 4 | N/A | 4 | 4
BROCCOLO TREE & LAWN CARE | S | 12-0250 | 2013-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COSTICH ENGINEERING | S | 12-0250 | 2013-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENVIRONMENTAL SERVICES UNLIMITED | S | 12-0250 | 2013-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRESTOP SOLUTIONS, INC. | S | 12-0250 | 2013-09-11 | 3 | 3 | 3 | 3 | N/A | 4 | 3
FLOWER CITY GLASS | S | 12-0250 | 2013-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HEASTER BUILDING RESTORATION, INC | S | 12-0250 | 2013-09-11 | 4 | 4 | 4 | 4 | N/A | 3 | 2
HENRY ISAACS HOME REMODELING | S | 12-0250 | 2013-09-11 | 4 | 5 | 4 | 4 | N/A | 2 | 3 | Submittals do not come complete or on time
KENNEDY MECHANICAL P&H INC. | S | 12-0250 | 2013-09-11 | 4 | 3 | 4 | 3 | N/A | 3 | 3 | Just started
LANDMARK ELECTRIC INC | S | 12-0250 | 2013-09-11 | 4 | 4 | 4 | 4 | N/A | 4 | 4
MESSNER FLOORING RESOURCE | S | 12-0250 | 2013-09-11 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NEW YORK STATE FENCE, INC | S | 12-0250 | 2013-09-11 | 3 | 3 | 3 | 3 | N/A | 3 | 3
OTIS ELEVATOR, USA | S | 12-0250 | 2013-09-11 | 4 | 3 | 4 | 3 | N/A | 4 | 4
UNICO FINISHING SYSTEMS | S | 12-0246 | 2013-04-01 | 4 | N/A | N/A | N/A | N/A | 3 | 3 | Long time LCS sub
UNICO FINISHING SYSTEMS | S | 12-0241 | 2013-05-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5 | Painting/Wallcovering - Not on-site yet
UNICO FINISHING SYSTEMS | S | 12-0246 | 2013-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Long time LCS sub
RAMAR STEEL SALES, INC | S | 12-0250 | 2013-09-11 | 5 | 5 | 4 | 5 | N/A | 5 | 4
STILLWATER ENTERPRISES | S | 12-0250 | 2013-09-11 | 4 | 4 | 4 | 4 | N/A | N/A | 3
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0250 | 2013-09-11 | 4 | 1 | 3 | 3 | 4 | 4 | 1 | Behind schedule, need more man power. Noone is receptive to e-mails and phone calls
US CEILING CORP. | S | 12-0250 | 2013-09-11 | 4 | 5 | 4 | 4 | 4 | 4 | N/A
US CEILING CORP. | S | 12-0250 | 2013-09-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 12-0250 | 2013-09-11 | 3 | 3 | 3 | 3 | 3 | 3 | 3
UNICO FINISHING SYSTEMS | S | 12-0241 | 2013-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 12-0250 | 2013-09-11 | 4 | 4 | 4 | 4 | N/A | N/A | 4
MONTGOMERY TRUSS & PANEL (FLOOR AND ROOF) | S | 12-0250 | 2013-09-11 | 4 | 5 | 5 | 5 | N/A | 4 | 4
UNICO FINISHING SYSTEMS | S | 12-0241 | 2013-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
WECKESSER BRICK | S | 12-0250 | 2013-09-11 | 2 | 3 | 3 | 3 | N/A | 3 | 2
WM. B. MORSE LUMBER CO. | S | 12-0250 | 2013-09-11 | 4 | 4 | 4 | 4 | N/A | 4 | 4
104 CONTRACTORS INC. | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.R. PIERREPONT CO., INC | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 12-0228 | 2013-09-28 | 5 | 5 | 5 | 5 | 4 | N/A | 5
DIVAL SAFETY EQUIPMENT | S | 12-0228 | 2013-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE DUKE COMPANY | S | 12-0228 | 2013-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNGBLOOD DISPOSAL | S | 12-0228 | 2013-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 12-0228 | 2013-09-28 | 3 | 3 | 4 | 3 | 4 | 4 | 3
ALPHA IRON WORKS, LLC | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&B MECHANICAL CONTRACTOR, INC | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&L WHOLESALE | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
DRAPERY INDUSTRIES, INC | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
EINSTEIN CONSTRUCTION CORP | S | 12-0228 | 2013-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EMPIRE METAL FABRICATORS, INC | S | 12-0228 | 2013-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRESTOP TECHNOLOGIES, INC | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
FRONTIER GLASS INC | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
GUARDIAN FIRE TESTING LABORATORIES | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
MONROE PIPING & SHEET METAL, LLC | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
COMMERICAL PIPE & SUPPLY | S | 12-0228 | 2013-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FERGUSON ENTERPRISES | S | 12-0228 | 2013-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TYCO FIRE PROTECTION PRODUCTS | S | 12-0228 | 2013-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 12-0228 | 2013-09-28 | 5 | 5 | 5 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 12-0228 | 2013-09-28 | 4 | 3 | 4 | 3 | 4 | 4 | 4
GC FLOORING | S | 12-0228 | 2013-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCHESTER COLONIAL MANUFACTURING | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SDC CONSTRUCTION SERVICES, INC | S | 12-0228 | 2013-09-28 | N/A | 2 | 3 | N/A | 4 | 2 | 2
SANITAIRE CLEANING CO., INC. | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCACCIA TILE & MARBLE INC. | S | 12-0228 | 2013-09-28 | 2 | 2 | 3 | 2 | 3 | 4 | 1 | Always needs money; difficult sub to work with; doesn't provide promised man power
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SWAN TILE, INC. | S | 12-0228 | 2013-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | 4
ID SIGNSYSTEMS | S | 12-0228 | 2013-09-28 | 4 | 2 | 3 | 4 | N/A | 5 | 2 | Difficult time getting responses about scheduling and manpower
T.Y. LIN INTERNATIONAL | S | 12-0228 | 2013-09-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.M. STERN, INC. | S | 11-0222 | 2013-10-10 | 4 | 4 | 4 | 4 | 2 | 4 | 3
AAC CONTRACTING, INC. | S | 11-0222 | 2013-10-10 | 3 | 4 | 2 | 4 | 2 | N/A | 4
AJAY GLASS & MIRROR | S | 11-0222 | 2013-10-10 | 4 | 2 | 4 | 2 | 4 | 2 | 1
ASSA ABLOY ENTRANCE SYSTEMS | S | 11-0222 | 2013-10-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ABSCOPE ENVIRONMENTAL INC. | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 11-0222 | 2013-10-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BAY TILE MARBLE & TERRAZZO | S | 11-0222 | 2013-10-10 | 4 | 4 | 4 | 4 | 5 | 4 | 4
C.A. REED ASSOCIATES | S | 11-0222 | 2013-10-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 11-0222 | 2013-10-10 | 4 | 4 | 4 | 4 | 3 | 4 | 4
CECO CONCRETE CONST. | S | 11-0222 | 2013-10-10 | 4 | 3 | 4 | 4 | 3 | 4 | 4
DECON STUDRAIL, INC. | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 11-0222 | 2013-10-10 | 3 | 2 | 3 | 2 | 4 | 3 | 2
CONNOR FENCE COMPANY INC. | S | 11-0222 | 2013-10-10 | 4 | 4 | 4 | 4 | 2 | N/A | 2
E.S. FIRE SUPPRESSION | S | 11-0222 | 2013-10-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ELEVATOR MAINTENANCE OF BUFFALO | S | 11-0222 | 2013-10-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
EMPIRE STATE MECHANICAL | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 11-0222 | 2013-10-10 | 4 | 4 | 4 | 4 | 4 | 4 | 5
FRANK J. MARIANACCI INC. | S | 11-0222 | 2013-10-10 | 3 | 4 | 3 | 4 | 3 | N/A | 2
G&J CONTRACTING INC | S | 11-0222 | 2013-10-10 | 2 | 3 | 4 | 3 | 4 | N/A | 2
GENEVA AWNING & TENT WORKS | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRECO PAINTING | S | 11-0222 | 2013-10-10 | 3 | 3 | 2 | 3 | 3 | 1 | 2
GYPSUM SYSTEMS, INC. | S | 11-0222 | 2013-10-10 | 4 | 3 | 3 | 3 | 3 | 4 | 3
HENRIETTA BUILDING SUPPLIES, INC. | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HERBERT F. DARLING, INC. | S | 11-0222 | 2013-10-10 | 4 | 1 | 4 | 3 | 2 | 2 | 1
HOUTENBRINK'S INC. | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMPERIAL DOOR CONTROLS, INC. | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 11-0222 | 2013-10-10 | 3 | 4 | 3 | 4 | 4 | 4 | 4 | Good
JOSEPHINE'S CLEANING SERVICE, LLC | S | 11-0222 | 2013-10-10 | 3 | 4 | 4 | 4 | 4 | N/A | 4
KLEIN REINFORCING SERVICES | S | 11-0222 | 2013-10-10 | N/A | 3 | 4 | N/A | 3 | 3 | 3
KOCHER SURVEYING, P.C. | S | 11-0222 | 2013-10-10 | 4 | 4 | 4 | 4 | N/A | N/A | 4
LAKEVIEW LAWN & LANDSCAPE | S | 11-0222 | 2013-10-10 | 3 | 3 | 3 | 3 | 4 | 1 | 3
SESSLER EXCAVATING | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
O'CONNELL ELECTRIC COMPANY, INC | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERHEAD DOOR COMPANY OF ALBANY, INC | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 11-0222 | 2013-10-10 | 3 | 3 | 3 | 2 | 1 | 3 | 1
POSTLER & JAECKLE CORP. | S | 11-0222 | 2013-10-10 | 3 | 3 | 3 | 3 | 2 | 4 | 2
PRO CARPET INC. | S | 11-0222 | 2013-10-10 | 3 | 4 | 3 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 11-0222 | 2013-10-10 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | Need push
RAMAR STEEL SALES, INC | S | 11-0222 | 2013-10-10 | 4 | 4 | 5 | 4 | 4 | 4 | 4
STILLWATER ENTERPRISES | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWIFTLIFT INC. | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWISSLOG (TRANSLOGIC CORP.) | S | 11-0222 | 2013-10-10 | 3 | 2 | 3 | 2 | 2 | 1 | 1
TLM EXCAVATING & ASSOCIATES | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE TRANE COMPANY | S | 11-0222 | 2013-10-10 | 3 | 3 | 3 | 3 | 4 | 3 | 3
THYSSENKRUPP ELEVATOR | S | 11-0222 | 2013-10-10 | N/A | 2 | N/A | N/A | 2 | 1 | 1
UPSTATE ROOFING & PAINTING, INC. | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
V&B UNDERGROUND UTILITIES INC. | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 11-0222 | 2013-10-10 | 3 | 3 | 3 | 3 | 3 | 3 | 4
D.V. BROWN & ASSOCIATES | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E.M. PFAFF & SON, INC. | S | 11-0222 | 2013-10-10 | 3 | 3 | 3 | 3 | 4 | 3 | 3
INPRO CORPORATION | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 2
KELLEY BROS. LLC | S | 11-0222 | 2013-10-10 | N/A | 2 | 3 | N/A | 2 | 2 | 1
SOUTHSIDE PRECAST PRODUCTS | S | 11-0222 | 2013-10-10 | N/A | 1 | 3 | N/A | 2 | 3 | 1
T.Y. LIN INTERNATIONAL | S | 11-0222 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D CALL & SONS EXCAVAT. | S | 13-0262 | 2013-10-10 | N/A | 4 | 4 | 4 | 4 | 1 | 2 | Submittals have been late
AGAPE WHOLESALE FURNITURE | S | 13-0262 | 2013-10-10 | N/A | 4 | 4 | 4 | 4 | 4 | 3
BROCCOLO TREE & LAWN CARE | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 2 | They are inexperienced with submittals and paperwork and insurances, however their workmanship is supposed to be very good
CATENARY CONSTRUCTION CORP. | S | 13-0262 | 2013-10-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4
ES SYSTEMS, INC | S | 13-0262 | 2013-10-10 | N/A | 4 | 4 | 3 | 3 | 3 | 2 | Having trouble with this sub that is trying to submit products that don't match the specs; went to the day with getting the insurances in and execution of contract was not good; constantly under-staffed
HENRY ISAACS HOME REMODELING | S | 13-0262 | 2013-10-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4
J&K CONSTRUCTION | S | 13-0262 | 2013-10-10 | N/A | 4 | 4 | 5 | 4 | 4 | 4
J&R SPECIALTIES | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 3
JOSEPHINE'S CLEANING SERVICE, LLC | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 3
MADGE LAND SURVEYING P.C. | S | 13-0262 | 2013-10-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4
MCGURK ELECTRIC, INC. | S | 13-0262 | 2013-10-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4
NEW YORK STATE FENCE, INC | S | 13-0262 | 2013-10-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4
PRECISION CONCRETE AND MASONRY | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | This company is not suited to perform the type of work we do
ROCHESTER FLOORING RESOURCE | S | 13-0262 | 2013-10-10 | N/A | 4 | 4 | 4 | 4 | N/A | 2 | Submitted products that did not meet the spec; we had to bring them in because their submittal for sheet vinyl was going to hold up the job; office is not responsive. Also has not filled out his material release voucher
SCHINDLER ELEVATOR | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4
US CEILING CORP. | S | 13-0262 | 2013-10-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4
US CEILING CORP. | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDYKE PAINTING COMPANY | S | 13-0262 | 2013-10-10 | N/A | 4 | 4 | 4 | 4 | N/A | 3
WINDOW ACCENTS INC. | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4
ALLIANCE DOOR & HARDWARE | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4 | supplier
MAX T. DOLAND | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4 | supplier
MONTGOMERY TRUSS | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4 | supplier
NORANDEX INC. | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4 | supplier
SERWAY BROTHERS INC. | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4 | supplier
WM B. MORSE LUMBER (LUMBER/HOUSE WRAP) | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4 | supplier
WM B MORSE LUMBER (FINISH CARPENTRY) | S | 13-0262 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4 | supplier
COMFORT SYSTEMS/ BILLONE | S | 13-0252 | 2013-10-10 | 5 | 5 | 4 | 5 | N/A | 4 | 5 | Difficulty in dealing with owners
CEDAR ENTERPRISES | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS ENGINEERS | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0252 | 2013-10-10 | 5 | 5 | 5 | 4 | 5 | 5 | 5
FLOWER CITY GLASS | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 13-0252 | 2013-10-10 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | Need to be proactive with them
KENNEDY MECHANICAL P&H INC. | S | 13-0252 | 2013-10-10 | 4 | 1 | 1 | 2 | 3 | 3 | 3 | They have not acted like a partner and they are not professional; they work attitude spreads to other subs and workers; they has zero communication between field and office so when their workers showed up they were not preapred to work and have caused schedule delays
LAKEVIEW LAWN & LANDSCAPE | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0252 | 2013-10-10 | 5 | 1 | 5 | 1 | 4 | 4 | 4 | Schedule with Keith
MCGURK ELECTRIC, INC. | S | 13-0252 | 2013-10-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
NEW YORK STATE FENCE, INC | S | 13-0252 | 2013-10-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRIDE FIRE PROTECTION | S | 13-0252 | 2013-10-10 | 5 | 5 | 4 | 4 | 4 | 3 | 4
QUALITY CARPETS | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | 3 | 3
RAMAR STEEL SALES, INC | S | 13-0252 | 2013-10-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
SCHINDLER ELEVATOR | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0252 | 2013-10-10 | 3 | 4 | 5 | 3 | 2 | 1 | 2 | They care about their work, but are over-extended.
WOODSTONE EARTH CONSTRUCTION, INC | S | 13-0252 | 2013-10-10 | 4 | 3 | 3 | 3 | N/A | 4 | 4 | Be prepared to argue, they are confrontational; issues with transparency and they will test you; be prepared to bring in team leader and outside consultants; great work execution though
LAKELANDS CONCRETE PRODUCTS | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAMILTON ENTERPRISES | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMI STRUCTURAL SOLUTIONS | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHLER AWNINGS | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
H-S INDUSTRIAL EQUIPMENT | S | 13-0252 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BLOCH INDUSTRIES LLC | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | 1 | 1 | Submittals took too long and were poor quality. Lack of advance planning resulting in changes.
E.S. FIRE SUPPRESSION | S | 12-0239 | 2013-10-10 | N/A | 4 | 4 | 2 | 1 | 4 | 4 | Not providing enough manpower
FORMATRON LTD. | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | 3 | 4 | N/A | N/A
FINGER LAKES SERVICE GROUP, INC. | S | 12-0239 | 2013-10-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4
HOCKENBERGS EQPT. & SUPPLY | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4
JACHLES IMPERIAL LTD | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 12-0239 | 2013-10-10 | N/A | 4 | 4 | 4 | 4 | 4 | 1
KENNEDY HVAC | S | 12-0239 | 2013-10-10 | N/A | 3 | 4 | 3 | 4 | 4 | 3 | Rob Frace great Foreman
LAKEVIEW LAWN & LANDSCAPE | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 12-0239 | 2013-10-10 | N/A | 3 | 3 | 3 | 3 | 3 | 3
MARK & DAN FRAMERS, INC | S | 12-0239 | 2013-10-10 | N/A | 4 | 4 | 3 | 3 | 3 | N/A
MCCLAIN ASSOCIATES INC. | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4
MCGURK ELECTRIC, INC. | S | 12-0239 | 2013-10-10 | N/A | 4 | 4 | 3 | 4 | 2 | 1 | Slow office, overloaded.
ONTARIO EXTERIORS, INC | S | 12-0239 | 2013-10-10 | N/A | 4 | 3 | 3 | 3 | 4 | 4
POOLER ENTERPIRSES, INC. | S | 12-0239 | 2013-10-10 | N/A | 3 | 3 | 1 | 3 | 1 | 3 | Difficult to get them here when we need them
SANITAIRE CLEANING CO., INC. | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCACCIA TILE & MARBLE INC. | S | 12-0239 | 2013-10-10 | N/A | 3 | 3 | 2 | 3 | 3 | 2 | Difficult to contact, must hold hand
STATEWIDE CONSTRUCTION INC | S | 12-0239 | 2013-10-10 | N/A | 4 | 3 | 4 | 4 | 5 | 4
CRICKET ON THE HEARTH | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4
FLOWER CITY GLASS | S | 12-0239 | 2013-10-10 | N/A | 3 | N/A | 4 | 3 | 3 | 3
MONTGOMERY TRUSS | S | 12-0239 | 2013-10-10 | N/A | 4 | N/A | 4 | 4 | 4 | 4
RAMAR STEEL SALES, INC | S | 12-0239 | 2013-10-10 | N/A | 5 | N/A | 5 | 4 | 4 | 4 | Highly Recommended
ROCHESTER COLONIAL MANUFACTURING | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | 1 | 2 | 2 | 1 | Inter office communication is poor; have not met schedule and is difficult to get pricing from them for an ASI
SOUTHSIDE PRECAST | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | 1 | N/A | N/A | 4 | Difficult to get schedule commitment
WM. B. MORSE LUMBER CO. | S | 12-0239 | 2013-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | 4 | Tod Cymmermin Highly Recommended
ABJ FIRE PROTECTION CO. | S | 13-0259 | 2013-10-18 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BAY TILE MARBLE & TERRAZZO | S | 13-0259 | 2013-10-18 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ES SYSTEMS, INC | S | 13-0259 | 2013-10-18 | 4 | 3 | 4 | 3 | 3 | 4 | 4 | Not consistent w/man power; under-staffed; late changes
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 13-0259 | 2013-10-18 | 4 | 3 | 3 | 3 | 3 | 4 | 4 | Need to be more diligent in office
GYPSUM SYSTEMS, INC. | S | 13-0259 | 2013-10-18 | 3 | 2 | 4 | 2 | 3 | 4 | 2 | Communication and man power are poor
PRO CARPET INC. | S | 13-0259 | 2013-10-18 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 13-0259 | 2013-10-18 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | Unresponsive PM for this job
SANITAIRE CLEANING CO., INC. | S | 13-0259 | 2013-10-18 | N/A | N/A | N/A | N/A | N/A | N/A | 4
STILLWATER ENTERPRISES | S | 13-0259 | 2013-10-18 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 13-0259 | 2013-10-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
T.Y. LIN INTERNATIONAL | S | 13-0259 | 2013-10-18 | 4 | 4 | 3 | 4 | 4 | N/A | 4 | More diligent on inspections the first time around
HENRIETTA BUILDING SUPPLIES, INC. | S | 13-0259 | 2013-10-18 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BGI INTERIORS | S | 13-0259 | 2013-10-18 | N/A | 1 | 4 | N/A | 3 | 4 | 3 | Doesn't keep promises; ships 75% of order
104 CONTRACTORS INC. | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.R. PIERREPONT CO., INC | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 12-0228 | 2013-10-25 | 5 | 5 | 5 | 5 | 4 | N/A | 5
DIVAL SAFETY EQUIPMENT | S | 12-0228 | 2013-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE DUKE COMPANY | S | 12-0228 | 2013-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNGBLOOD DISPOSAL | S | 12-0228 | 2013-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 12-0228 | 2013-10-25 | 3 | 3 | 4 | 3 | 4 | 4 | 3
ALPHA IRON WORKS, LLC | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Out of man hours
B&B MECHANICAL CONTRACTOR, INC | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | 4 | 4 | 4
B&L WHOLESALE | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 3 | N/A | 4 | N/A | Out of man hours
DRAPERY INDUSTRIES, INC | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | 4 | 4 | 4
EINSTEIN CONSTRUCTION CORP | S | 12-0228 | 2013-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EMPIRE METAL FABRICATORS, INC | S | 12-0228 | 2013-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRESTOP TECHNOLOGIES, INC | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
FRONTIER GLASS INC | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
GUARDIAN FIRE TESTING LABORATORIES | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | 4 | N/A | N/A
MONROE PIPING & SHEET METAL, LLC | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | 4 | 4 | 4
COMMERICAL PIPE & SUPPLY | S | 12-0228 | 2013-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FERGUSON ENTERPRISES | S | 12-0228 | 2013-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TYCO FIRE PROTECTION PRODUCTS | S | 12-0228 | 2013-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | 4 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 12-0228 | 2013-10-25 | 5 | 5 | 5 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 12-0228 | 2013-10-25 | 4 | 3 | 4 | 3 | 4 | 4 | 4 | Out of man hours
GC FLOORING | S | 12-0228 | 2013-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCHESTER COLONIAL MANUFACTURING | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SDC CONSTRUCTION SERVICES, INC | S | 12-0228 | 2013-10-25 | N/A | 2 | 3 | N/A | 4 | 2 | 2
SANITAIRE CLEANING CO., INC. | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCACCIA TILE & MARBLE INC. | S | 12-0228 | 2013-10-25 | 2 | 2 | 3 | 2 | 3 | 4 | 1 | Always needs money; difficult sub to work with; doesn't provide promised man power
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SWAN TILE, INC. | S | 12-0228 | 2013-10-25 | N/A | N/A | N/A | N/A | N/A | N/A | 4
ID SIGNSYSTEMS | S | 12-0228 | 2013-10-25 | 4 | 2 | 3 | 4 | N/A | 5 | 2 | Difficult time getting responses about scheduling and manpower
T.Y. LIN INTERNATIONAL | S | 12-0228 | 2013-10-25 | 4 | 4 | 4 | 4 | 4 | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 13-0259 | 2013-10-18 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNICO FINISHING SYSTEMS | S | 12-0246 | 2013-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Long time LCS sub
UNICO FINISHING SYSTEMS | S | 13-0264 | 2013-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 13-0270 | 2013-10-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2013-10-01 | 4 | 5 | 5 | 5 | 4 | N/A | 4
FISHER ASSOCIATES | S | 13-0270 | 2013-10-01 | 4 | 4 | 1 | 4 | N/A | N/A | 3 | Major Errors
GARAGE DOORS UNLIMITED | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | 5 | N/A
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2013-10-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMPACT PAINTING LLC | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&K CONSTRUCTION | S | 13-0270 | 2013-10-01 | 4 | 5 | 4 | 5 | N/A | N/A | 5
JACHLES IMPERIAL LTD | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2013-10-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3
MIG BUILDING SYSTEMS | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ONTARIO EXTERIORS, INC | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2013-10-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 12-0246 | 2013-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Long time LCS sub
MONTGOMERY TRUSS | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MAX T. DOLAND | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D.W INC. | S | 13-0271 | 2014-02-01 | 5 | 4 | 3 | 4 | 4 | 4 | N/A | Works well with team
AAA QUALITY MAINTAINENCE | S | 13-0271 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLOY WELDING CO. INC. | S | 13-0271 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
ALLOY WELDING CO. INC. | S | 13-0271 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
BGI INTERIORS | S | 13-0271 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 13-0271 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRUCE HOFFMAN AND SONS MASONRY | S | 13-0271 | 2013-12-01 | 4 | 3 | 4 | 2 | N/A | 4 | N/A | 2 man team needs to pick it up
BRUCE HOFFMAN AND SONS MASONRY | S | 13-0271 | 2014-02-01 | 4 | 4 | 4 | 2 | N/A | 4 | N/A | 2 man team needs to pick it up
COFFEY BROTHERS INC | S | 13-0271 | 2013-12-01 | 4 | 2 | 3 | 3 | N/A | 4 | 2 | didn’t return calls
COFFEY BROTHERS INC | S | 13-0271 | 2014-02-01 | 4 | 3 | 2 | 3 | N/A | 4 | 2 | Better with correspondence
DDS CONSTRUCTORS, LLC | S | 13-0272 | 2014-02-01 | 4 | 4 | 4 | 4 | 3 | 4 | 4
FLOWER CITY GLASS | S | 13-0271 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HARRINGTON CONSTRUCTION CO. | S | 13-0271 | 2013-12-01 | 4 | 3 | 4 | 3 | N/A | 3 | N/A | Independent
HARRINGTON CONSTRUCTION CO. | S | 13-0271 | 2014-02-01 | 4 | 4 | 2 | 3 | N/A | 3 | N/A
HENRIETTA BUILDING SUPPLIES, INC. | S | 13-0271 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRIETTA BUILDING SUPPLIES, INC. | S | 13-0271 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HUNTERDON HEATING & A.C. | S | 13-0271 | 2013-12-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4 | no issue
HUNTERDON HEATING & A.C. | S | 13-0271 | 2014-02-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
A.D CALL & SONS EXCAVAT. | S | 13-0262 | 2013-12-01 | 4 | 4 | 4 | 4 | 2 | 2 | 4 | Stepped up at the end of the job.
AGAPE WHOLESALE FURNITURE | S | 13-0262 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
BROCCOLO TREE & LAWN CARE | S | 13-0262 | 2013-12-01 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | They are inexperienced with submittals and paperwork and insurances, however their workmanship is supposed to be very good
CATENARY CONSTRUCTION CORP. | S | 13-0262 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ES SYSTEMS, INC | S | 13-0262 | 2013-12-01 | 4 | 3 | 4 | 3 | 3 | 2 | 3 | Came through at the end of the job
HENRY ISAACS HOME REMODELING | S | 13-0262 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 4 | 3
J&K CONSTRUCTION | S | 13-0262 | 2013-12-01 | 4 | 5 | 4 | 4 | 4 | 4 | 4
J&R SPECIALTIES | S | 13-0262 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
JOSEPHINE'S CLEANING SERVICE, LLC | S | 13-0262 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0262 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
MADGE LAND SURVEYING P.C. | S | 13-0262 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MCGURK ELECTRIC, INC. | S | 13-0262 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
NEW YORK STATE FENCE, INC | S | 13-0262 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRECISION CONCRETE AND MASONRY | S | 13-0262 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 1 | 2 | This company is not suited to perform the type of work we do
ROCHESTER FLOORING RESOURCE | S | 13-0262 | 2013-12-01 | 4 | 1 | 3 | 4 | 2 | 2 | 2 | Quality is ok, need to watch for deceptive and false information
SCHINDLER ELEVATOR | S | 13-0262 | 2013-12-01 | N/A | 2 | N/A | N/A | N/A | 4 | 3 | Did not meet delivery date, but did finish on time
US CEILING CORP. | S | 13-0262 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 4 | 5
VANDYKE PAINTING COMPANY | S | 13-0262 | 2013-12-01 | 4 | 4 | 4 | 4 | N/A | 3 | 3
WINDOW ACCENTS INC. | S | 13-0262 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 13-0262 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
MAX T. DOLAND | S | 13-0262 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
MONTGOMERY TRUSS | S | 13-0262 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
NORANDEX INC. | S | 13-0262 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
SERWAY BROTHERS INC. | S | 13-0262 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
WM B. MORSE LUMBER (LUMBER/HOUSE WRAP) | S | 13-0262 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
WM B MORSE LUMBER (FINISH CARPENTRY) | S | 13-0262 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | supplier
AIIA CONSTRUCTION COMPANY, INC | S | 12-0239 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | N/A | 3
ASSA ABLOY ENTRANCE SYSTEMS | S | 12-0239 | 2013-12-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BLOCH INDUSTRIES LLC | S | 12-0239 | 2013-12-01 | N/A | 4 | 5 | 4 | 3 | N/A | 3
E.S. FIRE SUPPRESSION | S | 12-0239 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Improving
FORMATRON LTD. | S | 12-0239 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 12-0239 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINGER LAKES SERVICE GROUP, INC. | S | 12-0239 | 2013-12-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
HOCKENBERGS EQPT. & SUPPLY | S | 12-0239 | 2013-12-01 | N/A | 4 | N/A | 4 | N/A | 4 | 5
JACHLES IMPERIAL LTD | S | 12-0239 | 2013-12-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
KENNEDY MECHANICAL PLUMBING DIV. | S | 12-0239 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 1 | 4
KENNEDY HVAC | S | 12-0239 | 2013-12-01 | 4 | 3 | 5 | 4 | 4 | 3 | 4 | Rob Frace great Foreman- he did his own punchlist and Sam recommends him as a possible recruit
LAKEVIEW LAWN & LANDSCAPE | S | 12-0239 | 2013-12-01 | 4 | 3 | 4 | 4 | N/A | N/A | 3
MIG BUILDING SYSTEMS | S | 12-0239 | 2013-12-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
MARK & DAN FRAMERS, INC | S | 12-0239 | 2013-12-01 | 4 | 3 | 4 | 3 | 3 | N/A | N/A
MCCLAIN ASSOCIATES INC. | S | 12-0239 | 2013-12-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MCGURK ELECTRIC, INC. | S | 12-0239 | 2013-12-01 | 2 | 1 | 4 | 3 | 3 | N/A | 3 | Missed rough in locations
ONTARIO EXTERIORS, INC | S | 12-0239 | 2013-12-01 | 3 | 3 | 4 | 3 | 4 | 4 | 4
POOLER ENTERPIRSES, INC. | S | 12-0239 | 2013-12-01 | 3 | 1 | 2 | 2 | 1 | N/A | 3 | Difficult to get them here when we need them- late changes
SANITAIRE CLEANING CO., INC. | S | 12-0239 | 2013-12-01 | 3 | 2 | 3 | 4 | N/A | N/A | N/A
SCACCIA TILE & MARBLE INC. | S | 12-0239 | 2013-12-01 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | Difficult to contact, must hold hand, Not equipped to handle CO proposals
STATEWIDE CONSTRUCTION INC | S | 12-0239 | 2013-12-01 | 3 | 4 | 4 | 4 | 5 | 4 | 4
CRICKET ON THE HEARTH | S | 12-0239 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
FLOWER CITY GLASS | S | 12-0239 | 2013-12-01 | N/A | 4 | 3 | 3 | 3 | 3 | 4
MONTGOMERY TRUSS | S | 12-0239 | 2013-12-01 | N/A | 4 | 3 | 4 | 4 | 4 | 4
RAMAR STEEL SALES, INC | S | 12-0239 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCHESTER COLONIAL MFG. | S | 12-0239 | 2013-12-01 | N/A | 1 | 1 | 2 | 2 | 1 | 1 | Inter office communication is poor; have not met schedule, delivery dates not met.
SOUTHSIDE PRECAST | S | 12-0239 | 2013-12-01 | N/A | 4 | 4 | N/A | 3 | 4 | 3 | Difficult to get schedule commitment
UPSTATE GRANITE & MARBLE | S | 12-0239 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM. B. MORSE LUMBER CO. | S | 12-0239 | 2013-12-01 | N/A | 5 | N/A | N/A | N/A | 4 | 4 | Tod Cymmermin Highly Recommended
SERWAY BROTHERS INC. | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MIG BUILDING SYSTEMS | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
BETLEM RESIDENTIAL | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
IMPACT PAINTING LLC | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0270 | 2013-12-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2013-12-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2013-12-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
FISHER ASSOCIATES | S | 13-0270 | 2013-12-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
GARAGE DOORS UNLIMITED | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2013-12-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
IMPACT PAINTING LLC | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
J&K CONSTRUCTION | S | 13-0270 | 2013-12-01 | 4 | 5 | 4 | 5 | N/A | 4 | 5
JACHLES IMPERIAL LTD | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2013-12-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
MIG BUILDING SYSTEMS | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ONTARIO EXTERIORS, INC | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2013-12-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
PRO CARPET INC. | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 13-0272 | 2014-03-01 | 4 | 4 | 4 | 4 | 3 | 4 | 4
RADEC CORPORATION | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 13-0272 | 2014-02-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0272 | 2014-02-01 | 3 | 4 | 4 | 4 | 4 | 4 | 2 | Safety issues
FLOWER CITY GLASS | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | 3 | 3 | 3 | Doesn't do paperwork
IMPACT PAINTING LLC | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL P & H INC. | S | 13-0272 | 2014-02-01 | 4 | 5 | 2 | 4 | N/A | 4 | 4
KJW ASSOCIATES | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
LORI JOHNSON CONTRACTING | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCGURK ELECTRIC, INC. | S | 13-0272 | 2014-02-01 | 4 | 4 | 4 | 4 | N/A | 2 | 4
MCMAHON LARUE ASSOCIATES P.C. | S | 13-0272 | 2014-02-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NEW YORK STATE FENCE, INC | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRIDE FIRE PROTECTION | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
PRO CARPET INC. | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAMAR STEEL SALES, INC | S | 13-0272 | 2014-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHINDLER ELEVATOR | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM B. MORSE LUMBER- STAIR | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JPL PAINTING & WALLCOVERING,INC | S | 13-0271 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JPL PAINTING & WALLCOVERING,INC | S | 13-0271 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNON SURVEY SERVICES | S | 13-0271 | 2013-12-01 | 5 | 4 | 2 | 4 | N/A | N/A | N/A
KENNON SURVEY SERVICES | S | 13-0271 | 2014-02-01 | 5 | 3 | 4 | 4 | N/A | N/A | N/A
METROCORP PLUMBING INC | S | 13-0271 | 2013-12-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4 | ok
METROCORP PLUMBING INC | S | 13-0271 | 2014-02-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
MODERNFOLD/STYLES, INC. | S | 13-0271 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODERNFOLD/STYLES, INC. | S | 13-0271 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POMPTON PAINTING CO. | S | 13-0271 | 2013-12-01 | 4 | 4 | 4 | 4 | N/A | 2 | N/A | Poor Paperwork
POMPTON PAINTING CO. | S | 13-0271 | 2014-02-01 | 4 | 4 | 4 | 4 | N/A | 2 | N/A | Poor Paperwork
SLIWINSKI FLOORING COVERING | S | 13-0271 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SLIWINSKI FLOORING COVERING | S | 13-0271 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TILE DESIGN OF WESTCHESTER INC | S | 13-0271 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TILE DESIGN OF WESTCHESTER INC | S | 13-0271 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WIRES ELECTRICAL SHOP | S | 13-0271 | 2013-12-01 | 4 | 4 | 4 | 4 | N/A | 4 | N/A | ok
WIRES ELECTRICAL SHOP | S | 13-0271 | 2014-02-01 | 4 | 4 | 4 | 4 | N/A | 4 | N/A | Ok- RFIs like crazy
WON-DOOR CORP. | S | 13-0271 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WON-DOOR CORP. | S | 13-0271 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MAX T. DOLAND | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
FIRESIDE HEARTH & HOME | S | 13-0271 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 13-0272 | 2014-03-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0272 | 2014-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 2 | Safety issues
FLOWER CITY GLASS | S | 13-0272 | 2014-03-01 | N/A | 4 | N/A | 4 | N/A | 4 | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | 3 | 3 | 3 | Doesn't do paperwork
IMPACT PAINTING LLC | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL P & H INC. | S | 13-0272 | 2014-03-01 | 4 | 4 | 5 | 4 | N/A | 4 | 4
MCGURK ELECTRIC, INC. | S | 13-0272 | 2014-03-01 | 4 | 4 | 4 | 4 | N/A | 2 | 4
MECH TECH | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
NEW YORK STATE FENCE, INC | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRIDE FIRE PROTECTION | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
PRO CARPET INC. | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAMAR STEEL SALES, INC | S | 13-0272 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHINDLER ELEVATOR | S | 13-0272 | 2014-03-01 | N/A | 3 | N/A | N/A | N/A | 4 | 4
SERWAY BROTHERS INC. | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM B. MORSE LUMBER- STAIR | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER- LUMBER MAT | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 12-0250 | 2013-08-14 | 3 | 4 | 3 | 3 | N/A | 4 | 4
HENRY ISAACS HOME REMODELING | S | 12-0250 | 2013-09-11 | 3 | 4 | 3 | 3 | N/A | 4 | 4
HENRY ISAACS HOME REMODELING | S | 13-0271 | 2014-03-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
HENRY ISAACS HOME REMODELING | S | 13-0271 | 2014-03-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
HENRY ISAACS HOME REMODELING | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
HENRY ISAACS HOME REMODELING | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
IAQ TECHNOLOGIES | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KJW ASSOCIATES | S | 13-0272 | 2014-03-01 | N/A | 4 | N/A | N/A | N/A | 4 | 4
LORI JOHNSON CONTRACTING | S | 13-0272 | 2014-03-01 | 1 | 2 | 3 | 3 | N/A | N/A | N/A
MCMAHON LARUE ASSOCIATES P.C. | S | 13-0272 | 2014-03-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
MECH TECH | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
MONTGOMERY TRUSS & PANEL (PANELS) | S | 12-0250 | 2013-08-14 | 4 | 5 | 5 | 5 | N/A | 4 | 4
MONTGOMERY TRUSS & PANEL (PANELS) | S | 12-0250 | 2013-09-11 | 4 | 5 | 5 | 5 | N/A | 4 | 4
POOLER ENTERPIRSES, INC (CONCRETE) | S | 12-0250 | 2013-08-14 | 4 | 4 | 4 | 4 | N/A | 4 | 4
POOLER ENTERPIRSES, INC (CONCRETE) | S | 12-0250 | 2013-09-11 | 4 | 4 | 4 | 4 | N/A | 4 | 4
POOLER ENTERPIRSES, INC (MASONRY) | S | 12-0250 | 2013-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC (MASONRY) | S | 12-0250 | 2013-09-11 | 3 | 2 | 3 | 3 | N/A | 2 | 2
AIIA CONSTRUCTION COMPANY, INC | S | 13-0271 | 2014-03-01 | 3 | 4 | 4 | 5 | 4 | N/A | 4
ALPHA IRON WORKS, LLC | S | 13-0271 | 2014-03-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0271 | 2014-03-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
POOLER ENTERPIRSES, INC (SITE) | S | 12-0250 | 2013-08-14 | 4 | 3 | 4 | 3 | N/A | 3 | 3
CATENARY CONSTRUCTION CORP. | S | 13-0271 | 2014-03-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
FISHER ASSOCIATES | S | 13-0271 | 2014-03-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
GARAGE DOORS UNLIMITED | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
POOLER ENTERPIRSES, INC (SITE) | S | 12-0250 | 2013-09-11 | 4 | 3 | 4 | 3 | N/A | 3 | 3
IMPACT PAINTING LLC | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
J&K CONSTRUCTION | S | 13-0271 | 2014-03-01 | 3 | 5 | 4 | 5 | N/A | 4 | 5
J&R SPECIALTIES | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
JACHLES IMPERIAL LTD | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
MIG BUILDING SYSTEMS | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ONTARIO EXTERIORS, INC | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | Slow office
POOLER ENTERPIRSES, INC. | S | 13-0271 | 2014-03-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PRO CARPET INC. | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RADEC CORPORATION | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ROCHESTER FLOORING RESOURCE | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
US CEILING CORP. | S | 13-0271 | 2014-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
UNICO FINISHING SYSTEMS | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0271 | 2014-03-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | Great performance
WHIRLPOOL CORPORATION | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
UNICO FINISHING SYSTEMS | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MAX T. DOLAND | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SERWAY BROTHERS INC. | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NORANDEX BUILDING MATERIALS | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
BROCCOLO TREE & LAWN CARE | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 12-0246 | 2013-08-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Long time LCS sub
UNICO FINISHING SYSTEMS | S | 12-0246 | 2013-09-12 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Long time LCS sub
WAYSIDE CONTRACTORS | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM B MORSE LUMBER (INT/EXT WOOD DOORS) | S | 13-0262 | 2013-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2013-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2013-12-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 13-0271 | 2014-03-01 | 3 | 4 | 4 | 5 | 4 | N/A | 4
ALPHA IRON WORKS, LLC | S | 13-0271 | 2014-03-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0271 | 2014-03-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
WM. B. MORSE LUMBER CO. | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 13-0271 | 2014-03-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
FISHER ASSOCIATES | S | 13-0271 | 2014-03-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
GARAGE DOORS UNLIMITED | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
WM. B. MORSE LUMBER CO. | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM. B. MORSE LUMBER - RC MAT. | S | 13-0272 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMPACT PAINTING LLC | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
J&K CONSTRUCTION | S | 13-0271 | 2014-03-01 | 3 | 5 | 4 | 5 | N/A | 4 | 5
J&R SPECIALTIES | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
JACHLES IMPERIAL LTD | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
MIG BUILDING SYSTEMS | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ONTARIO EXTERIORS, INC | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | Slow office
POOLER ENTERPIRSES, INC. | S | 13-0271 | 2014-03-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PRO CARPET INC. | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RADEC CORPORATION | S | 13-0271 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ROCHESTER FLOORING RESOURCE | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
US CEILING CORP. | S | 13-0271 | 2014-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
UNICO FINISHING SYSTEMS | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0271 | 2014-03-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | Great performance
WHIRLPOOL CORPORATION | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM. B. MORSE LUMBER- TRIM | S | 13-0272 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SERWAY BROTHERS INC. | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NORANDEX BUILDING MATERIALS | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
BROCCOLO TREE & LAWN CARE | S | 13-0271 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALUMINA RAILING PRODUCTS, INC. | S | 12-0235 | 2014-01-01 | 3 | 2 | 3 | 3 | 4 | 4 | 4 | Not on site
ASSOCIATED DRYWALL PARTNERS | S | 12-0235 | 2014-01-01 | 4 | 2 | 4 | 2 | 2 | 4 | 4
BGI INTERIORS | S | 12-0235 | 2014-01-01 | N/A | 4 | 5 | N/A | 4 | 5 | 4 | Material only
BECKER LANDSCAPE CONTRACTORS INC. | S | 12-0235 | 2014-01-01 | 5 | 4 | 4 | 3 | 4 | 4 | 4 | Just started
BEST RESTAURANT EQUIPMENT & DESIGN, INC. | S | 12-0235 | 2014-01-01 | 5 | 3 | 4 | 2 | 3 | 4 | 4
BLAKLEY CORPORATION | S | 12-0235 | 2014-01-01 | 4 | 3 | 4 | 3 | 3 | 4 | 4
C.E. REEVE ROOFING LLC | S | 12-0235 | 2014-01-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
CAIN CORPORATION | S | 12-0235 | 2014-01-01 | 4 | 2 | 3 | 1 | 4 | 3 | 2
CARBIDE INDUSTRIES | S | 12-0235 | 2014-01-01 | 4 | 1 | 3 | 4 | 3 | 3 | 1 | Not on site
CIRCLE B CONSTRUCTION SYSTEMS, LLC | S | 12-0235 | 2014-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CLARK SALES & SERVICE INC. | S | 12-0235 | 2014-01-01 | 4 | 2 | 4 | 2 | 3 | 4 | 3 | Not on site
DEALERS WHOLESALE | S | 12-0235 | 2014-01-01 | 4 | 2 | 4 | 2 | 4 | 3 | 2
DEL-MONDE, INC. | S | 12-0235 | 2014-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ELBRECHT INVESTMENTS LLC DBA ELBRECHT CONCRETE | S | 12-0235 | 2014-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINAL CLEAN CORP. | S | 12-0235 | 2014-01-01 | 4 | 3 | 3 | 3 | 3 | N/A | 3
GAYLOR, INC. | S | 12-0235 | 2014-01-01 | 4 | 3 | 4 | 2 | 3 | 4 | 3
GLENMARK CONSTRUCTION | S | 12-0235 | 2014-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HALL ALUMINUM | S | 12-0235 | 2014-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HOOSIER PRESTRESS, INC. | S | 12-0235 | 2014-01-01 | 4 | 3 | 4 | 3 | 3 | 3 | 3
INDIANA STEEL FABRICATING, INC. | S | 12-0235 | 2014-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
K & K FENCE, INC. | S | 12-0235 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
LEE SUPPLY CORPORATION | S | 12-0235 | 2014-01-01 | 5 | 3 | 4 | 2 | 3 | 3 | 3
LIGHT-CRETE PRODUCTS & SERVICES, INC. | S | 12-0235 | 2014-01-01 | 4 | 5 | 4 | 4 | 4 | 4 | 4
MOMPER INSULATION | S | 12-0235 | 2014-01-01 | 5 | 5 | 5 | 4 | 4 | 4 | 4
OTIS ELEVATOR, USA | S | 12-0235 | 2014-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OVERHEAD DOOR COMPANY OF INDIANAPOLIS | S | 12-0235 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
OYLER CONSTRUCTION | S | 12-0235 | 2014-01-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4
PROBUILD CO. LLC | S | 12-0235 | 2014-01-01 | 4 | 3 | 4 | 2 | 3 | 3 | 3
QUALITECK LLC | S | 12-0235 | 2014-01-01 | 4 | 3 | 4 | 2 | 3 | 3 | 3
ROBERT HAINES CO. | S | 12-0235 | 2014-01-01 | 5 | 2 | 4 | 2 | 3 | 3 | 3
ROGER WARD ENGINEERING, INC. | S | 12-0235 | 2014-01-01 | 5 | 2 | 3 | 2 | 3 | 3 | 2
SPD TEXTILE & DRAPERY, INC. | S | 12-0235 | 2014-01-01 | 4 | 2 | 3 | 2 | 3 | 3 | 3 | Not on site
STEELCORE CONSTRUCTION CO. INC. | S | 12-0235 | 2014-01-01 | 3 | 2 | 3 | 2 | 3 | 3 | 2 | No longer on site
TP MECHANICAL CONTRACTORS | S | 12-0235 | 2014-01-01 | 5 | 2 | 4 | 2 | 3 | 4 | 3
US AUTOMATIC FIRE & SECURITY | S | 12-0235 | 2014-01-01 | 4 | 2 | 4 | 2 | 3 | 4 | 4
VALENTI HELD, INC. | S | 12-0235 | 2014-01-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
VISION PAINTING | S | 12-0235 | 2014-01-01 | 5 | 4 | 4 | 3 | 4 | 4 | 4
WAGLER CUSTOM HOMES LLC | S | 12-0235 | 2014-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WILSON-PARTENHEIMER, INC. | S | 12-0235 | 2014-01-01 | 4 | 1 | 4 | 2 | 3 | 4 | 4
MAX T. DOLAND | S | 12-0235 | 2014-01-01 | N/A | 5 | 5 | N/A | 4 | 5 | 4
ALLIANCE DOOR & HARDWARE | S | 12-0235 | 2014-01-01 | N/A | 4 | 5 | N/A | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 12-0235 | 2014-01-01 | N/A | 5 | 5 | N/A | 4 | 4 | 4
NATIONAL CONSTRUCTION RENTALS | S | 12-0235 | 2014-01-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
TRUSSWAY MFG. | S | 12-0235 | 2014-01-01 | N/A | 5 | 5 | N/A | 4 | 4 | 4
LAUNDRY CITY EQUIPMENT | S | 12-0235 | 2014-01-01 | 4 | 2 | 4 | 3 | 3 | 4 | 4 | Not on site
SYR BEAUTY | S | 12-0235 | 2014-01-01 | N/A | 2 | 3 | N/A | 3 | 4 | 4 | Not on site
LOOMIS BROS. EQUIPMENT | S | 12-0235 | 2014-01-01 | N/A | N/A | N/A | N/A | 3 | 3 | 3
MARK & DAN FRAMERS, INC | S | 12-0235 | 2014-01-01 | 5 | 4 | 4 | 4 | 4 | N/A | 4 | Procurement on this project
RUNYON EQUIPMENT | S | 12-0235 | 2014-01-01 | 5 | 5 | 5 | 5 | 4 | N/A | 5
RICHARDS BUILDING SUPPLY | S | 12-0235 | 2014-01-01 | N/A | 1 | 4 | N/A | 3 | 3 | 3
GEMINI ELECTRONIC | S | 12-0235 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
MOBILE AIR | S | 12-0235 | 2014-01-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0270 | 2014-01-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2014-01-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2014-01-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
FISHER ASSOCIATES | S | 13-0270 | 2014-01-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
GARAGE DOORS UNLIMITED | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2014-01-01 | 2 | 4 | 4 | 4 | N/A | 4 | 4
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMPACT PAINTING LLC | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
J&K CONSTRUCTION | S | 13-0270 | 2014-01-01 | 4 | 5 | 4 | 5 | N/A | 4 | 5
JACHLES IMPERIAL LTD | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2014-01-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
MIG BUILDING SYSTEMS | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ONTARIO EXTERIORS, INC | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2014-01-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
PRO CARPET INC. | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MONTGOMERY TRUSS | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MAX T. DOLAND | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2014-01-01 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2014-01-01 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ALPHA IRON WORKS, LLC | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 13-0267 | 2014-01-01 | N/A | 5 | 5 | N/A | N/A | 4 | 4
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2014-01-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BUDGET FENCE INCORPORATED | S | 13-0267 | 2014-01-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CFE, INC. | S | 13-0267 | 2014-01-01 | 3 | 5 | 5 | 5 | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2014-01-01 | 5 | 5 | 5 | 5 | 3 | 3 | 4
FILBIN PAINTING INC. | S | 13-0267 | 2014-01-01 | 4 | 4 | 3 | 4 | 4 | N/A | 2
GORICK CONSTRUCTION | S | 13-0267 | 2014-01-01 | 1 | 3 | 4 | 5 | 3 | 3 | 3 | poor communication
HOMER C GOW & SONS | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2014-01-01 | 3 | 4 | 4 | 4 | N/A | N/A | 4
L.A.PAINTING, INC. | S | 13-0267 | 2014-01-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
MATCO ELECTRIC | S | 13-0267 | 2014-01-01 | 4 | 5 | 5 | 5 | 5 | 3 | 4 | solid
MESKO GLASS CO. | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2014-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 3
NORTHERN SPACES INC. | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 5 | N/A
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2014-01-01 | 4 | 2 | 4 | 4 | 4 | 3 | 3 | Very difficult to work with; would not recommend again
RUG FAIR COMMERCIAL | S | 13-0267 | 2014-01-01 | N/A | 4 | N/A | N/A | 3 | 3 | 2
SCHINDLER ELEVATOR | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3 | Too early
SIMPLEXGRINNELL LP | S | 13-0267 | 2014-01-01 | 5 | 2 | 5 | 5 | N/A | 4 | 4
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2014-01-01 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | good
SURE TEMP COMPANY INC. | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2014-01-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2014-01-01 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company
WILLIAM H. LANE INC. | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2014-01-01 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | office is too busy
ALEXANDER MITCHELL & SON | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ERIE MATERIALS INC. | S | 13-0267 | 2014-01-01 | N/A | 4 | N/A | N/A | 4 | 4 | 4
RED HAWK FIRE & SECURITY | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2014-01-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
ARCI, LTD. | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRMP INC | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EVOLUTION POOLS & CONSTRUCTION SERVICES, INC. | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAVEN CONTRACTING, INC | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JEL SITE DEVELOPMENT INC. | S | 13-0273 | 2014-03-01 | 4 | 3 | 4 | 3 | 4 | 4 | 3 | Small operation, apparently capable of doing this but were perform well so far
THYSSENKRUPP ELEVATOR | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICORN PAINTING INC. | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIVERSAL ENGINEERING SCIENCES | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAYNE AUTOMATIC SPRINKLERS | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DELACRUZ DRYWALL PLASTERING | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRUSSWAY MFG. | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CABLE ELECTRICAL SERVICES | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FOX WINDOWS | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIVERSAL BUILDING SUPPLY | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING - MATERIALS | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G&L EXTERIORS | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLORIDA DOOR SOLUTIONS | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRANT & SON | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICORN PAINTING INC. | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GULF COAST PLUMBING | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VALUE LIGHTING | S | 13-0273 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 13-0270 | 2014-03-01 | 3 | 4 | 4 | 5 | 4 | N/A | 4
ALPHA IRON WORKS, LLC | S | 13-0270 | 2014-03-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2014-03-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BRIDGEWATER INTERNATIONAL | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2014-03-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
FISHER ASSOCIATES | S | 13-0270 | 2014-03-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
GARAGE DOORS UNLIMITED | S | 13-0270 | 2014-03-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2014-03-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
IMPACT PAINTING LLC | S | 13-0270 | 2014-03-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
J&K CONSTRUCTION | S | 13-0270 | 2014-03-01 | 3 | 5 | 4 | 5 | N/A | 4 | 5
J&R SPECIALTIES | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
JACHLES IMPERIAL LTD | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2014-03-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
MIG BUILDING SYSTEMS | S | 13-0270 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ONTARIO EXTERIORS, INC | S | 13-0270 | 2014-03-01 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | Slow office
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2014-03-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0270 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PRO CARPET INC. | S | 13-0270 | 2014-03-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RADEC CORPORATION | S | 13-0270 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
US CEILING CORP. | S | 13-0270 | 2014-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
UNICO FINISHING SYSTEMS | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2014-03-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | Great performance
WHIRLPOOL CORPORATION | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MAX T. DOLAND | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SERWAY BROTHERS INC. | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
BROCCOLO TREE & LAWN CARE | S | 13-0270 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL COUNTY GUTTER CO., INC. | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAY TILE MARBLE & TERRAZZO | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DESIGN POOL & SPA LTD. | S | 14-0281 | 2014-05-01 | 4 | 4 | 4 | 5 | N/A | 3 | 4 | Difficult to work with on pre-con
ES SYSTEMS, INC | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
F.G. RAYBURN MASON CONTRACTORS, INC | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GENERAL GLASS AND MIRROR COMPANY | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMPERIAL DOOR CONTROLS, INC. | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JAG CONSTRUCTION, INC. | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL P & H INC. | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCGURK ELECTRIC, INC. | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 14-0281 | 2014-05-01 | 4 | 5 | 5 | 5 | N/A | N/A | 4
WOODSTONE EARTH CONSTRUCTION, INC | S | 14-0281 | 2014-05-01 | 3 | 4 | 4 | 5 | 4 | 5 | 5
B&L WHOLESALE | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE - TRUSSES | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MORSE SASH & DOOR | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SECURITRONICS | S | 14-0281 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARCI, LTD. | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRMP INC | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EVOLUTION POOLS & CONSTRUCTION SERVICES, INC. | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAVEN CONTRACTING, INC | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JEL SITE DEVELOPMENT INC. | S | 13-0273 | 2014-04-01 | 4 | 3 | 4 | 3 | 4 | 4 | 3 | Small operation, apparently capable of doing this but were perform well so far
THYSSENKRUPP ELEVATOR | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICORN PAINTING INC. | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIVERSAL ENGINEERING SCIENCES | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAYNE AUTOMATIC SPRINKLERS | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DELACRUZ DRYWALL PLASTERING | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRUSSWAY MFG. | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CABLE ELECTRICAL SERVICES | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FOX WINDOWS | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIVERSAL BUILDING SUPPLY | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING - MATERIALS | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G&L EXTERIORS | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLORIDA DOOR SOLUTIONS | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRANT & SON | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GULF COAST PLUMBING | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VALUE LIGHTING | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRECISION GUTTERS | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
REW LANDSCAPE | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE LUCKHARDT GROUP | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WATERWATCH CORPORATION | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MASTER WOOD CRAFT CABINETRY | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUSA CABINETS | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STONE INSTALLATION | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAST COAST POURED FLOORS | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BARFIELD FENCE & WALL | S | 13-0273 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARCI, LTD. | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRMP INC | S | 13-0273 | 2014-05-01 | 4 | 2 | 4 | 3 | N/A | N/A | 2 | this sub has a new scheduler and this will hopefully help with the scheduling issues.
EVOLUTION POOLS & CONSTRUCTION SERVICES, INC. | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAVEN CONTRACTING, INC | S | 13-0273 | 2014-05-01 | 4 | 4 | 4 | 3 | 4 | 3 | 3 | field workers are very good
JEL SITE DEVELOPMENT INC. | S | 13-0273 | 2014-05-01 | 4 | 3 | 4 | 3 | 4 | 4 | 3 | Small operation, apparently capable of doing this but were perform well so far
THYSSENKRUPP ELEVATOR | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICORN PAINTING INC. | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIVERSAL ENGINEERING SCIENCES | S | 13-0273 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
WAYNE AUTOMATIC SPRINKLERS | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DELACRUZ DRYWALL PLASTERING | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRUSSWAY MFG. | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CABLE ELECTRICAL SERVICES | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FOX WINDOWS | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIVERSAL BUILDING SUPPLY | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING - MATERIALS | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G&L EXTERIORS | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLORIDA DOOR SOLUTIONS | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRANT & SON | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICORN PAINTING INC. | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GULF COAST PLUMBING | S | 13-0273 | 2014-05-01 | 4 | 5 | 4 | 4 | 5 | 5 | 4
VALUE LIGHTING | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRECISION GUTTERS | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
REW LANDSCAPE | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE LUCKHARDT GROUP | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WATERWATCH CORPORATION | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MASTER WOOD CRAFT CABINETRY | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUSA CABINETS | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STONE INSTALLATION | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAST COAST POURED FLOORS | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BARFIELD FENCE & WALL | S | 13-0273 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARCI, LTD. | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING | S | 13-0273 | 2014-06-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
BRANT & SON | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CABLE ELECTRICAL SERVICES | S | 13-0273 | 2014-06-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3
DRMP INC | S | 13-0273 | 2014-06-01 | 4 | 2 | 4 | 3 | N/A | N/A | 2 | this sub has a new scheduler and this will hopefully help with the scheduling issues.
DELACRUZ DRYWALL PLASTERING | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EVOLUTION POOLS & CONSTRUCTION SERVICES, INC. | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLORIDA DOOR SOLUTIONS | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FOX WINDOWS | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G&L EXTERIORS | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GULF COAST PLUMBING | S | 13-0273 | 2014-06-01 | 4 | 5 | 4 | 4 | 5 | 5 | 4
HAVEN CONTRACTING, INC | S | 13-0273 | 2014-06-01 | 4 | 4 | 4 | 3 | 4 | 3 | 3 | field workers are very good
JEL SITE DEVELOPMENT INC. | S | 13-0273 | 2014-06-01 | 4 | 3 | 4 | 3 | 4 | 4 | 3 | Small operation, apparently capable of doing this but were perform well so far
JL WILSON CONCRETE, INC. | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRECISION GUTTERS | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
REW LANDSCAPE | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUSA CABINETS | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STONE INSTALLATION | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE LUCKHARDT GROUP | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICORN PAINTING INC. | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIVERSAL BUILDING SUPPLY | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIVERSAL ENGINEERING SCIENCES | S | 13-0273 | 2014-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
WAYNE AUTOMATIC SPRINKLERS | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WATERWATCH CORPORATION | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRUSSWAY MFG. | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING - MATERIALS | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VALUE LIGHTING | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MASTER WOOD CRAFT CABINETRY | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EAST COAST POURED FLOORS | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BARFIELD FENCE & WALL | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MALIBU FLOORS | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHADES TO YOU | S | 13-0273 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 13-0270 | 2014-04-01 | 3 | 4 | 4 | 5 | 4 | N/A | 4
ALL COUNTY GUTTER CO., INC. | S | 13-0270 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 13-0270 | 2014-04-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2014-04-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BRIDGEWATER INTERNATIONAL | S | 13-0270 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BROCCOLO TREE & LAWN CARE | S | 13-0270 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2014-04-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
FISHER ASSOCIATES | S | 13-0270 | 2014-04-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
GARAGE DOORS UNLIMITED | S | 13-0270 | 2014-04-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING (ROOFING) | S | 13-0270 | 2014-04-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
HENRY ISAACS HOME REMODELING (SIDING) | S | 13-0270 | 2014-04-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
IMPACT PAINTING LLC | S | 13-0270 | 2014-04-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
J&K CONSTRUCTION | S | 13-0270 | 2014-04-01 | 3 | 5 | 4 | 5 | N/A | 4 | 5
J&R SPECIALTIES | S | 13-0270 | 2014-04-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
JACHLES IMPERIAL LTD | S | 13-0270 | 2014-04-01 | 4 | 3 | 3 | 3 | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2014-04-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
MIG BUILDING SYSTEMS | S | 13-0270 | 2014-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ONTARIO EXTERIORS, INC | S | 13-0270 | 2014-04-01 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | Slow office
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2014-04-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0270 | 2014-04-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PRO CARPET INC. | S | 13-0270 | 2014-04-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RADEC CORPORATION | S | 13-0270 | 2014-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
SANITAIRE CLEANING CO., INC. | S | 13-0270 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0270 | 2014-04-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
UNICO FINISHING SYSTEMS | S | 13-0270 | 2014-04-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2014-04-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | Great performance
WHIRLPOOL CORPORATION | S | 13-0270 | 2014-04-01 | 4 | 4 | 4 | 3 | N/A | 4 | 3
WINDOW ACCENTS INC. | S | 13-0270 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 13-0270 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MAX T. DOLAND | S | 13-0270 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SERWAY BROTHERS INC. | S | 13-0270 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 13-0270 | 2014-05-01 | 3 | 4 | 4 | 5 | 4 | N/A | 4
ALL COUNTY GUTTER CO., INC. | S | 13-0270 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0270 | 2014-05-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2014-05-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BRIDGEWATER INTERNATIONAL | S | 13-0270 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BROCCOLO TREE & LAWN CARE | S | 13-0270 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2014-05-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
FISHER ASSOCIATES | S | 13-0270 | 2014-05-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
GARAGE DOORS UNLIMITED | S | 13-0270 | 2014-05-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING (ROOFING) | S | 13-0270 | 2014-05-01 | 1 | 4 | 4 | 4 | N/A | 4 | 4 | Had a life threatening violation in the past month
HENRY ISAACS HOME REMODELING (SIDING) | S | 13-0270 | 2014-05-01 | 1 | 4 | 4 | 4 | 4 | N/A | 4 | Had a life threatening violation in the past month
IMPACT PAINTING LLC | S | 13-0270 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
J&K CONSTRUCTION | S | 13-0270 | 2014-05-01 | 3 | 5 | 4 | 5 | N/A | 4 | 5
J&R SPECIALTIES | S | 13-0270 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
JACHLES IMPERIAL LTD | S | 13-0270 | 2014-05-01 | 4 | 3 | 3 | 3 | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2014-05-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
MIG BUILDING SYSTEMS | S | 13-0270 | 2014-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ONTARIO EXTERIORS, INC | S | 13-0270 | 2014-05-01 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | Slow office
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2014-05-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0270 | 2014-05-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PRO CARPET INC. | S | 13-0270 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RADEC CORPORATION | S | 13-0270 | 2014-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2014-05-01 | 4 | 3 | 3 | 4 | N/A | 3 | 3
SANITAIRE CLEANING CO., INC. | S | 13-0270 | 2014-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
US CEILING CORP. | S | 13-0270 | 2014-05-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
UNICO FINISHING SYSTEMS | S | 13-0270 | 2014-05-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2014-05-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | Great performance
WHIRLPOOL CORPORATION | S | 13-0270 | 2014-05-01 | 4 | 4 | 4 | 3 | N/A | 4 | 3
WINDOW ACCENTS INC. | S | 13-0270 | 2014-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MONTGOMERY TRUSS | S | 13-0270 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MAX T. DOLAND | S | 13-0270 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SERWAY BROTHERS INC. | S | 13-0270 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
AGAPE WHOLESALE FURNITURE | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 13-0272 | 2014-04-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 13-0272 | 2014-04-01 | 4 | 4 | 4 | 4 | 3 | 4 | 4
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0272 | 2014-04-01 | 3 | 4 | 4 | 4 | 4 | 4 | 2 | Safety issues
FLOWER CITY GLASS | S | 13-0272 | 2014-04-01 | N/A | 4 | N/A | 4 | N/A | 4 | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | 3 | 3 | 3 | Doesn't do paperwork
IAQ TECHNOLOGIES | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMPACT PAINTING LLC | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KJW ASSOCIATES | S | 13-0272 | 2014-04-01 | N/A | 4 | N/A | N/A | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 13-0272 | 2014-04-01 | 4 | 4 | 5 | 4 | N/A | 4 | 4
LORI JOHNSON CONTRACTING | S | 13-0272 | 2014-04-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Abandoned site
MCGURK ELECTRIC, INC. | S | 13-0272 | 2014-04-01 | 4 | 4 | 4 | 4 | N/A | 2 | 4
MCMAHON LARUE ASSOCIATES P.C. | S | 13-0272 | 2014-04-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
MECH TECH | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
NEW YORK STATE FENCE, INC | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRIDE FIRE PROTECTION | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
PRO CARPET INC. | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAMAR STEEL SALES, INC | S | 13-0272 | 2014-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHINDLER ELEVATOR | S | 13-0272 | 2014-04-01 | N/A | 3 | N/A | N/A | N/A | 4 | 4
US CEILING CORP. | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAYSIDE CONTRACTORS | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER - RC MAT. | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM B. MORSE LUMBER- STAIR | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER- TRIM | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CICERO & CICERO | S | 13-0272 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 13-0272 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | Difficult to get full job done at one time- misses items
DRISCOLL MASONRY RESTORATION | S | 13-0272 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 13-0272 | 2014-05-01 | 4 | 4 | 4 | 4 | 3 | 4 | 4
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0272 | 2014-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 3
FLOWER CITY GLASS | S | 13-0272 | 2014-05-01 | N/A | 4 | N/A | 4 | N/A | 4 | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0272 | 2014-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HENRY ISAACS HOME REMODELING | S | 13-0272 | 2014-05-01 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | Doesn't do paperwork
IAQ TECHNOLOGIES | S | 13-0272 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On site for 1 day to do an inspection
IMPACT PAINTING LLC | S | 13-0272 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 13-0272 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KJW ASSOCIATES | S | 13-0272 | 2014-05-01 | 4 | 3 | 4 | 3 | N/A | 2 | 2 | Signage buyout and submittals are behind
KENNEDY MECHANICAL P & H INC. | S | 13-0272 | 2014-05-01 | 4 | 4 | 3 | 4 | 3 | 4 | 2 | Difficult to deal with
LORI JOHNSON CONTRACTING | S | 13-0272 | 2014-05-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Abandoned site
MCGURK ELECTRIC, INC. | S | 13-0272 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | 2 | 3 | Late on submittals
MCMAHON LARUE ASSOCIATES P.C. | S | 13-0272 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
MECH TECH | S | 13-0272 | 2014-05-01 | 4 | 5 | 5 | 5 | 4 | 3 | 4
NEW YORK STATE FENCE, INC | S | 13-0272 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
PRIDE FIRE PROTECTION | S | 13-0272 | 2014-05-01 | 4 | 3 | 3 | 4 | 3 | 3 | 4
PRO CARPET INC. | S | 13-0272 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
RAMAR STEEL SALES, INC | S | 13-0272 | 2014-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHINDLER ELEVATOR | S | 13-0272 | 2014-05-01 | N/A | 3 | N/A | N/A | N/A | 4 | 4
US CEILING CORP. | S | 13-0272 | 2014-05-01 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | Difficult to get pricing for COs and COs are not accurately priced
WAYSIDE CONTRACTORS | S | 13-0272 | 2014-05-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WINDOW ACCENTS INC. | S | 13-0272 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM. B. MORSE LUMBER - RC MAT. | S | 13-0272 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4
WM B. MORSE LUMBER- STAIR | S | 13-0272 | 2014-05-01 | N/A | 4 | N/A | N/A | N/A | N/A | 4
SERWAY BROTHERS INC. | S | 13-0272 | 2014-05-01 | N/A | 3 | N/A | N/A | N/A | 2 | 3 | Issues with cabinet submittals
WM. B. MORSE LUMBER- TRIM | S | 13-0272 | 2014-05-01 | N/A | 4 | N/A | N/A | N/A | 4 | 4
CICERO & CICERO | S | 13-0272 | 2014-05-01 | 4 | 3 | 4 | 3 | 4 | N/A | 4
A.D.W INC. | S | 13-0271 | 2014-04-01 | 2 | 1 | 2 | 1 | 4 | 4 | 2 | Several men needed to be removed for safety concerns and they have not been able to man the job appropriately and maintain schedule; have not been responsive to LCS requests
ALLOY WELDING CO. INC. | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
BRUCE HOFFMAN AND SONS MASONRY | S | 13-0271 | 2014-04-01 | 4 | 3 | 4 | 2 | N/A | 4 | N/A | 2 man team needs to pick it up
COFFEY BROTHERS INC | S | 13-0271 | 2014-04-01 | 4 | 2 | 3 | 3 | N/A | 4 | 2 | Better with correspondence
HARRINGTON CONSTRUCTION CO. | S | 13-0271 | 2014-04-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
HUNTERDON HEATING & A.C. | S | 13-0271 | 2014-04-01 | 2 | 2 | 4 | 2 | N/A | N/A | N/A | Need to be reminded about safety; have not manned the job or maintained the schedule as needed
JPL PAINTING & WALLCOVERING,INC | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNON SURVEY SERVICES | S | 13-0271 | 2014-04-01 | 5 | 4 | 3 | 4 | N/A | N/A | N/A
METROCORP PLUMBING INC | S | 13-0271 | 2014-04-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
MODERNFOLD/STYLES, INC. | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POMPTON PAINTING CO. | S | 13-0271 | 2014-04-01 | 4 | 4 | 4 | 4 | N/A | 2 | N/A | Poor Paperwork
SLIWINSKI FLOORING COVERING | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TILE DESIGN OF WESTCHESTER INC | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WIRES ELECTRICAL SHOP | S | 13-0271 | 2014-04-01 | 4 | 4 | 4 | 4 | N/A | 4 | N/A | Ok- RFIs like crazy
WON-DOOR CORP. | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAA QUALITY MAINTAINENCE | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRESIDE HEARTH & HOME | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRIETTA BUILDING SUPPLIES, INC. | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KUIKEN BROTHERS CO. | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLD WORLD STONEWORKS | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WARREN COUNTY GLASS & MIRROR | S | 13-0271 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D.W INC. | S | 13-0271 | 2014-05-01 | 2 | 1 | 2 | 1 | 4 | 4 | 2 | Several men needed to be removed for safety concerns and they have not been able to man the job appropriately and maintain schedule; have not been responsive to LCS requests
ALLOY WELDING CO. INC. | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
BRUCE HOFFMAN AND SONS MASONRY | S | 13-0271 | 2014-05-01 | 4 | 3 | 4 | 2 | N/A | 4 | N/A | 2 man team needs to pick it up
COFFEY BROTHERS INC | S | 13-0271 | 2014-05-01 | 4 | 2 | 3 | 3 | N/A | 4 | 2 | Better with correspondence
HARRINGTON CONSTRUCTION CO. | S | 13-0271 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
HUNTERDON HEATING & A.C. | S | 13-0271 | 2014-05-01 | 2 | 2 | 4 | 2 | N/A | N/A | N/A | Need to be reminded about safety; have not manned the job or maintained the schedule as needed
JPL PAINTING & WALLCOVERING,INC | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNON SURVEY SERVICES | S | 13-0271 | 2014-05-01 | 5 | 4 | 3 | 4 | N/A | N/A | N/A
METROCORP PLUMBING INC | S | 13-0271 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
MODERNFOLD/STYLES, INC. | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POMPTON PAINTING CO. | S | 13-0271 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | 2 | N/A | Poor Paperwork
SLIWINSKI FLOORING COVERING | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TILE DESIGN OF WESTCHESTER INC | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WIRES ELECTRICAL SHOP | S | 13-0271 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | 4 | N/A | Ok- RFIs like crazy
WON-DOOR CORP. | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAA QUALITY MAINTAINENCE | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRESIDE HEARTH & HOME | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRIETTA BUILDING SUPPLIES, INC. | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KUIKEN BROTHERS CO. | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLD WORLD STONEWORKS | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WARREN COUNTY GLASS & MIRROR | S | 13-0271 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2014-03-01 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2014-03-01 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ALPHA IRON WORKS, LLC | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 13-0267 | 2014-03-01 | N/A | 5 | 5 | N/A | N/A | 4 | 4
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2014-03-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BUDGET FENCE INCORPORATED | S | 13-0267 | 2014-03-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CFE, INC. | S | 13-0267 | 2014-03-01 | 3 | 5 | 5 | 5 | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2014-03-01 | 5 | 5 | 5 | 5 | 3 | 3 | 4
FILBIN PAINTING INC. | S | 13-0267 | 2014-03-01 | 4 | 4 | 3 | 4 | 4 | N/A | 2
GORICK CONSTRUCTION | S | 13-0267 | 2014-03-01 | 1 | 3 | 4 | 5 | 3 | 3 | 3 | poor communication
HOMER C GOW & SONS | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2014-03-01 | 3 | 4 | 4 | 4 | N/A | N/A | 4
L.A.PAINTING, INC. | S | 13-0267 | 2014-03-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
MATCO ELECTRIC | S | 13-0267 | 2014-03-01 | 4 | 5 | 5 | 5 | 5 | 3 | 4 | solid
MESKO GLASS CO. | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2014-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 3
NORTHERN SPACES INC. | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 5 | N/A
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2014-03-01 | 4 | 2 | 4 | 4 | 4 | 3 | 3 | Very difficult to work with; would not recommend again
RED HAWK FIRE & SECURITY | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2014-03-01 | N/A | 4 | N/A | N/A | 3 | 3 | 2
SCHINDLER ELEVATOR | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3 | Too early
SIMPLEXGRINNELL LP | S | 13-0267 | 2014-03-01 | 5 | 2 | 5 | 5 | N/A | 4 | 4
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2014-03-01 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | good
SURE TEMP COMPANY INC. | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2014-03-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2014-03-01 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company
WILLIAM H. LANE INC. | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2014-03-01 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | office is too busy
ALEXANDER MITCHELL & SON | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ERIE MATERIALS INC. | S | 13-0267 | 2014-03-01 | N/A | 4 | N/A | N/A | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2014-03-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2014-04-01 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2014-04-01 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ALPHA IRON WORKS, LLC | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 13-0267 | 2014-04-01 | N/A | 5 | 5 | N/A | N/A | 4 | 4
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2014-04-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BUDGET FENCE INCORPORATED | S | 13-0267 | 2014-04-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CFE, INC. | S | 13-0267 | 2014-04-01 | 3 | 5 | 5 | 5 | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2014-04-01 | 5 | 5 | 5 | 5 | 3 | 3 | 4
FILBIN PAINTING INC. | S | 13-0267 | 2014-04-01 | 4 | 4 | 3 | 4 | 4 | N/A | 2
GORICK CONSTRUCTION | S | 13-0267 | 2014-04-01 | 1 | 3 | 4 | 5 | 3 | 3 | 3 | poor communication
HOMER C GOW & SONS | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2014-04-01 | 3 | 4 | 4 | 4 | N/A | N/A | 4
L.A.PAINTING, INC. | S | 13-0267 | 2014-04-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
MATCO ELECTRIC | S | 13-0267 | 2014-04-01 | 4 | 5 | 5 | 5 | 5 | 3 | 4 | solid
MESKO GLASS CO. | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2014-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 3
NORTHERN SPACES INC. | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | 5 | N/A
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2014-04-01 | 4 | 2 | 4 | 4 | 4 | 3 | 3 | Very difficult to work with; would not recommend again
RED HAWK FIRE & SECURITY | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2014-04-01 | N/A | 4 | N/A | N/A | 3 | 3 | 2
SCHINDLER ELEVATOR | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3 | Too early
SIMPLEXGRINNELL LP | S | 13-0267 | 2014-04-01 | 5 | 2 | 5 | 5 | N/A | 4 | 4
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2014-04-01 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | good
SURE TEMP COMPANY INC. | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2014-04-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2014-04-01 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company
WILLIAM H. LANE INC. | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2014-04-01 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | office is too busy
ALEXANDER MITCHELL & SON | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ERIE MATERIALS INC. | S | 13-0267 | 2014-04-01 | N/A | 4 | N/A | N/A | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2014-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2014-05-01 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2014-05-01 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ALPHA IRON WORKS, LLC | S | 13-0267 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 13-0267 | 2014-05-01 | N/A | 5 | 5 | N/A | N/A | 4 | 4 | Delivery strung out
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2014-05-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BUDGET FENCE INCORPORATED | S | 13-0267 | 2014-05-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CFE, INC. | S | 13-0267 | 2014-05-01 | 3 | 5 | 5 | 5 | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2014-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2014-05-01 | 5 | 5 | 5 | 5 | 3 | 3 | 4
FILBIN PAINTING INC. | S | 13-0267 | 2014-05-01 | 4 | 4 | 3 | 4 | 4 | N/A | 2
GORICK CONSTRUCTION | S | 13-0267 | 2014-05-01 | 1 | 4 | 4 | 5 | 3 | 3 | 3
HOMER C GOW & SONS | S | 13-0267 | 2014-05-01 | 3 | 5 | 5 | 5 | N/A | N/A | N/A
J&R SPECIALTIES | S | 13-0267 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2014-05-01 | 3 | 5 | 5 | 5 | 3 | N/A | N/A
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2014-05-01 | 3 | 4 | 4 | 4 | N/A | N/A | 4
L.A.PAINTING, INC. | S | 13-0267 | 2014-05-01 | 3 | 2 | 3 | 4 | N/A | 4 | 4 | Not concerend about quality of finished product
MATCO ELECTRIC | S | 13-0267 | 2014-05-01 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | solid
MESKO GLASS CO. | S | 13-0267 | 2014-05-01 | 3 | 1 | 3 | 3 | 4 | 4 | 4 | Difficult to get ahold of and manage
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHERN SPACES INC. | S | 13-0267 | 2014-05-01 | 3 | 3 | 4 | 4 | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 13-0267 | 2014-05-01 | 4 | 4 | 4 | 4 | N/A | 5 | N/A
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2014-05-01 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | Very difficult to work with; Need to descope well
RED HAWK FIRE & SECURITY | S | 13-0267 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2014-05-01 | 3 | 4 | 5 | 4 | 3 | 3 | 2
SCHINDLER ELEVATOR | S | 13-0267 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Too early
SIMPLEXGRINNELL LP | S | 13-0267 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | good
SURE TEMP COMPANY INC. | S | 13-0267 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2014-05-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2014-05-01 | 4 | 4 | 5 | 4 | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2014-05-01 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company, would recommend
WILLIAM H. LANE INC. | S | 13-0267 | 2014-05-01 | 3 | 4 | 3 | 4 | N/A | N/A | N/A | Lane's sub was quick but sloppy, owned their mistakes
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2014-05-01 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | office is too busy
ALEXANDER MITCHELL & SON | S | 13-0267 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2014-05-01 | N/A | 5 | 5 | N/A | 4 | 4 | 4
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | 2 | poor management of material procurement
ERIE MATERIALS INC. | S | 13-0267 | 2014-05-01 | N/A | 4 | N/A | N/A | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2014-05-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
AGAPE WHOLESALE FURNITURE | S | 13-0272 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | Difficult to get full job done at one time- misses items
DRISCOLL MASONRY RESTORATION | S | 13-0272 | 2014-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 13-0272 | 2014-06-01 | 4 | 4 | 4 | 4 | 3 | 4 | 4
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0272 | 2014-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 3
FLOWER CITY GLASS | S | 13-0272 | 2014-06-01 | N/A | 4 | N/A | 4 | N/A | 4 | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0272 | 2014-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HENRY ISAACS HOME REMODELING | S | 13-0272 | 2014-06-01 | 3 | 3 | 4 | 3 | 3 | 3 | 3 | Doesn't do paperwork
IAQ TECHNOLOGIES | S | 13-0272 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On site for 1 day to do an inspection
IMPACT PAINTING LLC | S | 13-0272 | 2014-06-01 | 4 | 4 | 4 | 4 | N/A | 3 | 2 | Non-responsive to e-mails and phone calls
JOSEPHINE'S CLEANING SERVICE, LLC | S | 13-0272 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KJW ASSOCIATES | S | 13-0272 | 2014-06-01 | 4 | 3 | 4 | 3 | N/A | 2 | 2 | Signage buyout and submittals are behind
KENNEDY MECHANICAL P & H INC. | S | 13-0272 | 2014-06-01 | 4 | 2 | 3 | 4 | 3 | 4 | 1 | Difficult to deal with and uncooperative; do not return responses quickly
LORI JOHNSON CONTRACTING | S | 13-0272 | 2014-06-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Abandoned site
MCGURK ELECTRIC, INC. | S | 13-0272 | 2014-06-01 | 4 | 2 | 4 | 4 | N/A | 2 | 3 | Late on submittals; do not follow schedule per request
MCMAHON LARUE ASSOCIATES P.C. | S | 13-0272 | 2014-06-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
MECH TECH | S | 13-0272 | 2014-06-01 | 4 | 5 | 5 | 5 | 4 | 3 | 4
NEW YORK STATE FENCE, INC | S | 13-0272 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
PRIDE FIRE PROTECTION | S | 13-0272 | 2014-06-01 | 4 | 3 | 3 | 4 | 3 | 3 | 4
PRO CARPET INC. | S | 13-0272 | 2014-06-01 | 3 | 3 | 3 | 3 | 4 | 3 | 4
RAMAR STEEL SALES, INC | S | 13-0272 | 2014-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHINDLER ELEVATOR | S | 13-0272 | 2014-06-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
US CEILING CORP. | S | 13-0272 | 2014-06-01 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | Difficult to get pricing for COs and COs are not accurately priced
WAYSIDE CONTRACTORS | S | 13-0272 | 2014-06-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WINDOW ACCENTS INC. | S | 13-0272 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM. B. MORSE LUMBER - RC MAT. | S | 13-0272 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4
WM B. MORSE LUMBER- STAIR | S | 13-0272 | 2014-06-01 | N/A | 4 | N/A | N/A | N/A | N/A | 4
SERWAY BROTHERS INC. | S | 13-0272 | 2014-06-01 | N/A | 3 | N/A | N/A | N/A | 2 | 3 | Issues with cabinet submittals
WM. B. MORSE LUMBER- TRIM | S | 13-0272 | 2014-06-01 | N/A | 4 | N/A | N/A | N/A | 4 | 4
CICERO & CICERO | S | 13-0272 | 2014-06-01 | 4 | 3 | 4 | 3 | 4 | N/A | 4
AIIA CONSTRUCTION COMPANY, INC | S | 13-0270 | 2014-06-01 | 3 | 4 | 4 | 5 | 4 | N/A | 4
ALL COUNTY GUTTER CO., INC. | S | 13-0270 | 2014-06-01 | 3 | 3 | 3 | 3 | N/A | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0270 | 2014-06-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2014-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BRIDGEWATER INTERNATIONAL | S | 13-0270 | 2014-06-01 | 3 | 2 | 2 | 3 | N/A | 4 | 4 | Missed some schedule targets
BROCCOLO TREE & LAWN CARE | S | 13-0270 | 2014-06-01 | 4 | 3 | 3 | 3 | N/A | 3 | 4
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2014-06-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
FISHER ASSOCIATES | S | 13-0270 | 2014-06-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
GARAGE DOORS UNLIMITED | S | 13-0270 | 2014-06-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING (ROOFING) | S | 13-0270 | 2014-06-01 | 1 | 4 | 4 | 4 | N/A | 4 | 4 | Had a life threatening violation in the past month
HENRY ISAACS HOME REMODELING (SIDING) | S | 13-0270 | 2014-06-01 | 1 | 4 | 4 | 4 | 4 | N/A | 4 | Had a life threatening violation in the past month
IMPACT PAINTING LLC | S | 13-0270 | 2014-06-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
J&K CONSTRUCTION | S | 13-0270 | 2014-06-01 | 3 | 5 | 4 | 5 | N/A | 4 | 5
J&R SPECIALTIES | S | 13-0270 | 2014-06-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
JACHLES IMPERIAL LTD | S | 13-0270 | 2014-06-01 | 4 | 3 | 3 | 3 | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2014-06-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
MIG BUILDING SYSTEMS | S | 13-0270 | 2014-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ONTARIO EXTERIORS, INC | S | 13-0270 | 2014-06-01 | 4 | 2 | 4 | 4 | 3 | 3 | 2 | Slow office; pulled manpower when there was work to be done
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2014-06-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0270 | 2014-06-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PRO CARPET INC. | S | 13-0270 | 2014-06-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RADEC CORPORATION | S | 13-0270 | 2014-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2014-06-01 | 4 | 3 | 3 | 4 | N/A | 3 | 3
SANITAIRE CLEANING CO., INC. | S | 13-0270 | 2014-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
US CEILING CORP. | S | 13-0270 | 2014-06-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
UNICO FINISHING SYSTEMS | S | 13-0270 | 2014-06-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2014-06-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | Great performance
WHIRLPOOL CORPORATION | S | 13-0270 | 2014-06-01 | 4 | 4 | 4 | 3 | N/A | 4 | 3
WINDOW ACCENTS INC. | S | 13-0270 | 2014-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MONTGOMERY TRUSS | S | 13-0270 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MAX T. DOLAND | S | 13-0270 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SERWAY BROTHERS INC. | S | 13-0270 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2014-06-01 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2014-06-01 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ALPHA IRON WORKS, LLC | S | 13-0267 | 2014-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BGI INTERIORS | S | 13-0267 | 2014-06-01 | N/A | 5 | 5 | N/A | N/A | 4 | 4 | Delivery strung out
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2014-06-01 | 5 | 5 | 5 | 5 | 2 | N/A | 3
BUDGET FENCE INCORPORATED | S | 13-0267 | 2014-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CFE, INC. | S | 13-0267 | 2014-06-01 | 3 | 5 | 5 | 5 | 2 | 2 | 2
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2014-06-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2014-06-01 | 5 | 5 | 5 | 5 | 4 | 3 | 4
FILBIN PAINTING INC. | S | 13-0267 | 2014-06-01 | 4 | 4 | 5 | 4 | 4 | N/A | 2
GORICK CONSTRUCTION | S | 13-0267 | 2014-06-01 | 1 | 4 | 4 | 5 | 3 | 3 | 3
HOMER C GOW & SONS | S | 13-0267 | 2014-06-01 | 4 | 5 | 5 | 5 | N/A | N/A | N/A
J&R SPECIALTIES | S | 13-0267 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2014-06-01 | 3 | 5 | 5 | 5 | 3 | N/A | N/A
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2014-06-01 | 3 | 4 | 4 | 4 | N/A | N/A | 4
L.A.PAINTING, INC. | S | 13-0267 | 2014-06-01 | 3 | 2 | 3 | 4 | 2 | 4 | 4 | Not concerend about quality of finished product
MATCO ELECTRIC | S | 13-0267 | 2014-06-01 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | solid
MESKO GLASS CO. | S | 13-0267 | 2014-06-01 | 3 | 1 | 3 | 3 | 4 | 4 | 4 | Difficult to get ahold of and manage
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHERN SPACES INC. | S | 13-0267 | 2014-06-01 | 3 | 3 | 4 | 4 | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 13-0267 | 2014-06-01 | 4 | 4 | 4 | 4 | N/A | 5 | N/A
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2014-06-01 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | Very difficult to work with; Need to descope well
RED HAWK FIRE & SECURITY | S | 13-0267 | 2014-06-01 | 4 | 4 | 4 | 4 | 3 | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2014-06-01 | 3 | 4 | 5 | 4 | 3 | 3 | 2 | difficult to schedule during school. Work in summer
SCHINDLER ELEVATOR | S | 13-0267 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Too early
SIMPLEXGRINNELL LP | S | 13-0267 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2014-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | good
SURE TEMP COMPANY INC. | S | 13-0267 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2014-06-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2014-06-01 | 4 | 4 | 5 | 4 | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2014-06-01 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company, would recommend
WILLIAM H. LANE INC. | S | 13-0267 | 2014-06-01 | 3 | 4 | 3 | 4 | N/A | N/A | N/A | Lane's sub was quick but sloppy, owned their mistakes
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2014-06-01 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | office is too busy
ALEXANDER MITCHELL & SON | S | 13-0267 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2014-06-01 | N/A | 5 | 5 | N/A | 4 | 4 | 4
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | 2 | poor management of material procurement
ERIE MATERIALS INC. | S | 13-0267 | 2014-06-01 | N/A | 4 | N/A | N/A | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2014-06-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
SOLUTIONS | S | 13-0276 | 2014-05-01 | 4 | 2 | 3 | 4 | 4 | 4 | N/A
OHL | S | 13-0276 | 2014-05-01 | 5 | 5 | 4 | 5 | 4 | 4 | N/A
MEISNER | S | 13-0276 | 2014-05-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
Y&T | S | 13-0276 | 2014-05-01 | 5 | 4 | 4 | 3 | 4 | 3 | N/A
ACQUATIC LANDSCAPING | S | 13-0276 | 2014-05-01 | 4 | 3 | 3 | 3 | 4 | 3 | N/A
GOMEZ & SONS | S | 13-0276 | 2014-05-01 | 5 | 5 | 4 | 4 | 4 | N/A | N/A
WILDCAT | S | 13-0276 | 2014-05-01 | 3 | 1 | 2 | 2 | N/A | N/A | N/A
SPI | S | 13-0276 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
TROPIC | S | 13-0276 | 2014-05-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
A.D.W INC. | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACE WINDOWS | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUILDERS INSTALLED PRODUCTS | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CGM TILE & STONE, INC | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EARL B. FEINDEN | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD & THOMAS O'CONNOR INC | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GENSON OVERHEAD DOOR, INC | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IRV SCHRODER AND SONS | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KONE, INC | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAWRENCE D. COON | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LD COON | S | 14-0291 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LECESSE PROCUREMENT LLC | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MORSE SASH & DOOR | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OCONNOR | S | 14-0291 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PINNACLE ROOFING INC | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RBM GUARDIAN FIRE PROTECTION INC | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RJ GRAVES CONSTRUCTION INC. | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRIPOINT STONE | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDUSEN & STEVES LAND SURVEYORS | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0291 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONVENANT FIRE PROTECTION | S | 14-0288 | 2014-08-11 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DANIELS ELECTRIC CORPORATION | S | 14-0288 | 2014-08-11 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DENRON PLUMBING AND HVAC, LLC | S | 14-0288 | 2014-08-11 | 5 | 4 | 4 | 4 | 4 | 3 | 4
ENVIROVANTAGE INC. | S | 14-0288 | 2014-08-11 | 4 | 3 | 4 | 4 | 4 | 4 | 4
JAMES VERRA ASSOC. | S | 14-0288 | 2014-08-11 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MALTHOUSE CONSTRUCTION | S | 14-0288 | 2014-08-11 | 4 | 3 | 4 | 4 | 4 | 4 | 4
METRO WALLS | S | 14-0288 | 2014-08-11 | 3 | 4 | 4 | 4 | 4 | 4 | 3
NOVEL IRON WORKS | S | 14-0288 | 2014-08-11 | 4 | 4 | N/A | N/A | 3 | 4 | 3
PISCATAQUA LANDSCAPING | S | 14-0288 | 2014-08-11 | 3 | 4 | 3 | 4 | 4 | 4 | 4
SEVERINO TRUCKING CO, INC. | S | 14-0288 | 2014-08-11 | 4 | 3 | 4 | 3 | 4 | 4 | 4
SOUTHERN NH POURED CONCRETE CONSTRUCTION INC. | S | 14-0288 | 2014-08-11 | 4 | 4 | 4 | 4 | 3 | 4 | 3
AAC CONTRACTING, INC. | S | 14-0281 | 2014-06-01 | 5 | 5 | 5 | 5 | 5 | N/A | 4
ALL COUNTY GUTTER CO., INC. | S | 14-0281 | 2014-06-01 | N/A | N/A | N/A | N/A | 4 | N/A | 3
ALLIANCE DOOR & HARDWARE | S | 14-0281 | 2014-06-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
B&L WHOLESALE | S | 14-0281 | 2014-06-01 | 5 | 4 | 5 | N/A | 4 | 4 | 4
BAY TILE MARBLE & TERRAZZO | S | 14-0281 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
DESIGN POOL & SPA LTD. | S | 14-0281 | 2014-06-01 | 4 | 4 | 4 | 5 | N/A | 3 | 4 | Difficult to work with on pre-con
ES SYSTEMS, INC | S | 14-0281 | 2014-06-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
F.G. RAYBURN MASON CONTRACTORS, INC | S | 14-0281 | 2014-06-01 | 5 | 4 | 5 | 5 | 4 | 3 | 4
GENERAL GLASS AND MIRROR COMPANY | S | 14-0281 | 2014-06-01 | 4 | 4 | N/A | N/A | 5 | 5 | 5
GYPSUM SYSTEMS INTERIORS | S | 14-0281 | 2014-06-01 | 4 | 4 | 4 | 4 | N/A | 3 | N/A
IMPERIAL DOOR CONTROLS, INC. | S | 14-0281 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
J&R SPECIALTIES | S | 14-0281 | 2014-06-01 | N/A | N/A | N/A | N/A | 3 | 4 | 3
JACHLES IMPERIAL LTD | S | 14-0281 | 2014-06-01 | N/A | N/A | N/A | N/A | 3 | 2 | 4 | Does not turn in submittals in a timely manner
JAG CONSTRUCTION, INC. | S | 14-0281 | 2014-06-01 | 5 | 5 | 5 | 5 | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 14-0281 | 2014-06-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
MARK & DAN FRAMERS, INC | S | 14-0281 | 2014-06-01 | 4 | 4 | 4 | 5 | 4 | N/A | 4
MCGURK ELECTRIC, INC. | S | 14-0281 | 2014-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MORSE SASH & DOOR | S | 14-0281 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 14-0281 | 2014-06-01 | 4 | 5 | 5 | 5 | N/A | N/A | 4
SECURITRONICS | S | 14-0281 | 2014-06-01 | N/A | N/A | N/A | N/A | 4 | N/A | 4
UPSTATE ROOFING & PAINTING, INC. | S | 14-0281 | 2014-06-01 | 3 | 4 | 4 | 4 | N/A | 3 | 4
WM. B. MORSE - TRUSSES | S | 14-0281 | 2014-06-01 | 5 | 5 | 5 | 5 | 2 | 3 | 4 | Submittals not complete and change management process is slow and unorganized
WOODSTONE EARTH CONSTRUCTION, INC | S | 14-0281 | 2014-06-01 | 3 | 4 | 4 | 5 | 4 | 5 | 5
AAC CONTRACTING, INC. | S | 14-0281 | 2014-07-01 | 5 | 5 | 5 | 5 | 5 | N/A | 4
ALL COUNTY GUTTER CO., INC. | S | 14-0281 | 2014-07-01 | N/A | N/A | N/A | N/A | 4 | N/A | 3
ALLIANCE DOOR & HARDWARE | S | 14-0281 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
B&L WHOLESALE | S | 14-0281 | 2014-07-01 | 5 | 4 | 5 | N/A | 4 | 4 | 4
BAY TILE MARBLE & TERRAZZO | S | 14-0281 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
DESIGN POOL & SPA LTD. | S | 14-0281 | 2014-07-01 | 4 | 4 | 4 | 5 | N/A | 3 | 4 | Difficult to work with on pre-con
ES SYSTEMS, INC | S | 14-0281 | 2014-07-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
F.G. RAYBURN MASON CONTRACTORS, INC | S | 14-0281 | 2014-07-01 | 5 | 4 | 5 | 5 | 4 | 3 | 4
GENERAL GLASS AND MIRROR COMPANY | S | 14-0281 | 2014-07-01 | 4 | 4 | 5 | 5 | 5 | 5 | 5
GYPSUM SYSTEMS INTERIORS | S | 14-0281 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
IMPERIAL DOOR CONTROLS, INC. | S | 14-0281 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
J&R SPECIALTIES | S | 14-0281 | 2014-07-01 | N/A | N/A | N/A | N/A | 3 | 4 | 3
JACHLES IMPERIAL LTD | S | 14-0281 | 2014-07-01 | N/A | N/A | N/A | N/A | 3 | 2 | 4 | Does not turn in submittals in a timely manner
JAG CONSTRUCTION, INC. | S | 14-0281 | 2014-07-01 | 5 | 5 | 5 | 5 | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 14-0281 | 2014-07-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
MARK & DAN FRAMERS, INC | S | 14-0281 | 2014-07-01 | 4 | 4 | 4 | 5 | 4 | N/A | 4
MCGURK ELECTRIC, INC. | S | 14-0281 | 2014-07-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MORSE SASH & DOOR | S | 14-0281 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 14-0281 | 2014-07-01 | 4 | 5 | 5 | 5 | N/A | N/A | 4
SECURITRONICS | S | 14-0281 | 2014-07-01 | N/A | N/A | N/A | N/A | 4 | N/A | 4
UPSTATE ROOFING & PAINTING, INC. | S | 14-0281 | 2014-07-01 | 3 | 4 | 4 | 4 | N/A | 3 | 4
WM. B. MORSE - TRUSSES | S | 14-0281 | 2014-07-01 | 5 | 5 | 5 | 5 | 2 | 3 | 4 | Submittals not complete and change management process is slow and unorganized
WOODSTONE EARTH CONSTRUCTION, INC | S | 14-0281 | 2014-07-01 | 3 | 4 | 4 | 5 | 4 | 5 | 5
AAC CONTRACTING, INC. | S | 14-0281 | 2014-08-01 | 5 | 5 | 5 | 5 | 5 | N/A | 4
ALL COUNTY GUTTER CO., INC. | S | 14-0281 | 2014-08-01 | 4 | 3 | 4 | 4 | 4 | N/A | 3
ALLIANCE DOOR & HARDWARE | S | 14-0281 | 2014-08-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
B&L WHOLESALE | S | 14-0281 | 2014-08-01 | 5 | 4 | 5 | N/A | 4 | 4 | 4
BAY TILE MARBLE & TERRAZZO | S | 14-0281 | 2014-08-01 | 4 | 3 | 5 | 3 | N/A | 3 | 4
DESIGN POOL & SPA LTD. | S | 14-0281 | 2014-08-01 | 4 | 4 | 4 | 5 | N/A | 3 | 4 | Difficult to work with on pre-con
ES SYSTEMS, INC | S | 14-0281 | 2014-08-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
F.G. RAYBURN MASON CONTRACTORS, INC | S | 14-0281 | 2014-08-01 | 5 | 4 | 5 | 5 | 4 | 3 | 4
GENERAL GLASS AND MIRROR COMPANY | S | 14-0281 | 2014-08-01 | 4 | 4 | 5 | 5 | 5 | 5 | 5
GYPSUM SYSTEMS INTERIORS | S | 14-0281 | 2014-08-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
IMPERIAL DOOR CONTROLS, INC. | S | 14-0281 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
J&R SPECIALTIES | S | 14-0281 | 2014-08-01 | N/A | N/A | N/A | N/A | 3 | 4 | 3
JACHLES IMPERIAL LTD | S | 14-0281 | 2014-08-01 | N/A | N/A | N/A | N/A | 3 | 2 | 4 | Does not turn in submittals in a timely manner
JAG CONSTRUCTION, INC. | S | 14-0281 | 2014-08-01 | 5 | 5 | 5 | 5 | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 14-0281 | 2014-08-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
MARK & DAN FRAMERS, INC | S | 14-0281 | 2014-08-01 | 4 | 4 | 4 | 5 | 4 | N/A | 4
MCGURK ELECTRIC, INC. | S | 14-0281 | 2014-08-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MORSE SASH & DOOR | S | 14-0281 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 14-0281 | 2014-08-01 | 4 | 5 | 5 | 5 | N/A | N/A | 4
SECURITRONICS | S | 14-0281 | 2014-08-01 | N/A | N/A | N/A | N/A | 4 | N/A | 4
UPSTATE ROOFING & PAINTING, INC. | S | 14-0281 | 2014-08-01 | 3 | 4 | 4 | 4 | N/A | 3 | 4
WM. B. MORSE - TRUSSES | S | 14-0281 | 2014-08-01 | 5 | 5 | 5 | 5 | 2 | 3 | 4 | Submittals not complete and change management process is slow and unorganized
WOODSTONE EARTH CONSTRUCTION, INC | S | 14-0281 | 2014-08-01 | 3 | 4 | 4 | 5 | 4 | 5 | 5
ARCI, LTD. | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | 4 | 3 | 4
BARFIELD FENCE & WALL | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
BERGERON FRAMING | S | 13-0273 | 2014-07-01 | 3 | 4 | 4 | 4 | N/A | 3 | 4
BERGERON FRAMING - MATERIALS | S | 13-0273 | 2014-07-01 | N/A | 4 | 3 | N/A | N/A | 3 | 3
BRANT & SON | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
CABLE ELECTRICAL SERVICES | S | 13-0273 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3
DELACRUZ DRYWALL PLASTERING | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 2 | 1 | This contractor has been put on notice several times to submit contract and they have not
DRMP INC | S | 13-0273 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | 2 | this sub has a new scheduler and this will hopefully help with the scheduling issues.
EAST COAST POURED FLOORS | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
EVOLUTION POOLS & CONSTRUCTION SERVICES, INC. | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
FLORIDA DOOR SOLUTIONS | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | 2
FOX WINDOWS | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
G&L EXTERIORS | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
GULF COAST PLUMBING | S | 13-0273 | 2014-07-01 | 4 | 5 | 4 | 4 | 5 | 5 | 4
HAVEN CONTRACTING, INC | S | 13-0273 | 2014-07-01 | 3 | 4 | 4 | 3 | 4 | 3 | 3 | field workers are very good
JEL SITE DEVELOPMENT INC. | S | 13-0273 | 2014-07-01 | 4 | 3 | 4 | 3 | 4 | 4 | 3 | Small operation, apparently capable of doing this but were perform well so far
JL WILSON CONCRETE, INC. | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
MALIBU FLOORS | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
MASTER WOOD CRAFT CABINETRY | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | 4 | 3 | 3
PRECISION GUTTERS | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
REW LANDSCAPE | S | 13-0273 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SHADES TO YOU | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
SOUSA CABINETS | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STONE INSTALLATION | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE LUCKHARDT GROUP | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4
THYSSENKRUPP ELEVATOR | S | 13-0273 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
TRUSSWAY MFG. | S | 13-0273 | 2014-07-01 | 3 | 5 | 4 | N/A | N/A | 4 | 4
UNICORN PAINTING INC. | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
UNIVERSAL BUILDING SUPPLY | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
UNIVERSAL ENGINEERING SCIENCES | S | 13-0273 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
VALUE LIGHTING | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | 4 | 3 | 4
WATERWATCH CORPORATION | S | 13-0273 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WAYNE AUTOMATIC SPRINKLERS | S | 13-0273 | 2014-07-01 | 4 | 5 | 4 | 5 | N/A | 3 | 4
ACQUATIC LANDSCAPING | S | 13-0276 | 2014-06-01 | 4 | 3 | 3 | 3 | 4 | 3 | N/A
GOMEZ & SONS | S | 13-0276 | 2014-06-01 | 5 | 5 | 4 | 4 | 4 | N/A | N/A
MEISNER | S | 13-0276 | 2014-06-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
OHL | S | 13-0276 | 2014-06-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A | Coordination of getting proper man power at the proper time was an issue
SOLUTIONS | S | 13-0276 | 2014-06-01 | 4 | 3 | 3 | 4 | 4 | 4 | N/A | Sub has a hard time following a schedule- there has been an improvement in schedule management
SPI | S | 13-0276 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
STATE LINE PRODUCTS | S | 13-0276 | 2014-06-01 | 5 | 5 | 5 | 5 | N/A | 3 | N/A
TROPIC | S | 13-0276 | 2014-06-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
WILDCAT | S | 13-0276 | 2014-06-01 | 3 | 1 | 2 | 2 | N/A | N/A | N/A | Wildcat waited too long to staff up. Would not use this sub again.
Y&T | S | 13-0276 | 2014-06-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
ACQUATIC LANDSCAPING | S | 13-0276 | 2014-07-01 | 4 | 3 | 3 | 3 | 4 | 3 | N/A
GOMEZ & SONS | S | 13-0276 | 2014-07-01 | 5 | 5 | 4 | 4 | 4 | N/A | N/A
MEISNER | S | 13-0276 | 2014-07-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
OHL | S | 13-0276 | 2014-07-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A | Coordination of getting proper man power at the proper time was an issue
SOLUTIONS | S | 13-0276 | 2014-07-01 | 4 | 3 | 3 | 4 | 4 | 4 | N/A | Sub has a hard time following a schedule- there has been an improvement in schedule management
SPI | S | 13-0276 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
STATE LINE PRODUCTS | S | 13-0276 | 2014-07-01 | 5 | 5 | 5 | 5 | N/A | 3 | N/A
TROPIC | S | 13-0276 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
WILDCAT | S | 13-0276 | 2014-07-01 | 3 | 1 | 2 | 2 | N/A | N/A | N/A | Wildcat waited too long to staff up. Would not use this sub again.
Y&T | S | 13-0276 | 2014-07-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
AGAPE WHOLESALE FURNITURE | S | 13-0272 | 2014-07-01 | 3 | 3 | 3 | 4 | 2 | 2 | 2 | Difficult to get full job done at one time- misses items
ONTARIO EXTERIORS, INC | S | 13-0270 | 2014-07-01 | 4 | 2 | 4 | 2 | 2 | 3 | 2 | Slow office; pulled manpower when there was work to be done; submitting COs for work that is in their contract
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MONTGOMERY TRUSS | S | 13-0270 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MIG BUILDING SYSTEMS | S | 13-0270 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MAX T. DOLAND | S | 13-0270 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2014-07-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
J&R SPECIALTIES | S | 13-0270 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
JACHLES IMPERIAL LTD | S | 13-0270 | 2014-07-01 | 4 | 3 | 3 | 3 | N/A | 4 | 4
IMPACT PAINTING LLC | S | 13-0270 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
J&K CONSTRUCTION | S | 13-0270 | 2014-07-01 | 3 | 5 | 4 | 5 | N/A | 4 | 5
HENRY ISAACS HOME REMODELING (SIDING) | S | 13-0270 | 2014-07-01 | 1 | 4 | 4 | 4 | 4 | N/A | 4 | Had a life threatening violation in the past month
HENRY ISAACS HOME REMODELING (ROOFING) | S | 13-0270 | 2014-07-01 | 1 | 4 | 4 | 4 | N/A | 4 | 4 | Had a life threatening violation in the past month
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FISHER ASSOCIATES | S | 13-0270 | 2014-07-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
GARAGE DOORS UNLIMITED | S | 13-0270 | 2014-07-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2014-07-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
BROCCOLO TREE & LAWN CARE | S | 13-0270 | 2014-07-01 | 4 | 3 | 3 | 3 | N/A | 3 | 4
BRIDGEWATER INTERNATIONAL | S | 13-0270 | 2014-07-01 | 3 | 2 | 2 | 3 | N/A | 4 | 4 | Missed some schedule targets
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2014-07-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BETLEM RESIDENTIAL | S | 13-0270 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 13-0270 | 2014-07-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
ALL COUNTY GUTTER CO., INC. | S | 13-0270 | 2014-07-01 | 3 | 3 | 3 | 3 | N/A | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 13-0270 | 2014-07-01 | 3 | 4 | 4 | 5 | 4 | N/A | 4
AIIA CONSTRUCTION COMPANY, INC | S | 13-0272 | 2014-07-01 | 3 | 4 | 4 | 4 | 3 | N/A | 2 | Good labor, but office is unresponsive
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 13-0272 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
CICERO & CICERO | S | 13-0272 | 2014-07-01 | 4 | 3 | 4 | 3 | 4 | N/A | 4
DDS CONSTRUCTORS, LLC | S | 13-0272 | 2014-07-01 | 4 | 4 | 4 | 4 | 3 | 4 | 4
DRISCOLL MASONRY RESTORATION | S | 13-0272 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0272 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 3
FLOWER CITY GLASS | S | 13-0272 | 2014-07-01 | N/A | 4 | N/A | 4 | N/A | 4 | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0272 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
IAQ TECHNOLOGIES | S | 13-0272 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | On site for 1 day to do an inspection
IMPACT PAINTING LLC | S | 13-0272 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | 3 | 2 | Non-responsive to e-mails and phone calls
JOSEPHINE'S CLEANING SERVICE, LLC | S | 13-0272 | 2014-07-01 | 4 | 4 | 5 | 4 | 4 | N/A | 3
KENNEDY MECHANICAL P & H INC. | S | 13-0272 | 2014-07-01 | 4 | 2 | 3 | 4 | 3 | 4 | 1 | Difficult to deal with and uncooperative; do not return responses quickly
KJW ASSOCIATES | S | 13-0272 | 2014-07-01 | 4 | 2 | 4 | 3 | N/A | 2 | 2 | Signage buyout and submittals are behind; materials not delivered on time
LORI JOHNSON CONTRACTING | S | 13-0272 | 2014-07-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Abandoned site
MCGURK ELECTRIC, INC. | S | 13-0272 | 2014-07-01 | 4 | 2 | 4 | 4 | N/A | 2 | 3 | Late on submittals; do not follow schedule per request
MCMAHON LARUE ASSOCIATES P.C. | S | 13-0272 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
MECH TECH | S | 13-0272 | 2014-07-01 | 4 | 5 | 5 | 5 | 4 | 3 | 4
NEW YORK STATE FENCE, INC | S | 13-0272 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site
PRIDE FIRE PROTECTION | S | 13-0272 | 2014-07-01 | 4 | 3 | 3 | 4 | 3 | 3 | 4
PRO CARPET INC. | S | 13-0272 | 2014-07-01 | 3 | 3 | 3 | 3 | 4 | 3 | 4
RAMAR STEEL SALES, INC | S | 13-0272 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHINDLER ELEVATOR | S | 13-0272 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
SERWAY BROTHERS INC. | S | 13-0272 | 2014-07-01 | N/A | 2 | 2 | N/A | 2 | 2 | 3 | Issues with cabinet submittals and difficult to work with
US CEILING CORP. | S | 13-0272 | 2014-07-01 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | Difficult to get pricing for COs and COs are not accurately priced
WAYSIDE CONTRACTORS | S | 13-0272 | 2014-07-01 | 3 | 3 | 4 | 3 | 4 | 4 | 4
WINDOW ACCENTS INC. | S | 13-0272 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM B. MORSE LUMBER- STAIR | S | 13-0272 | 2014-07-01 | N/A | 4 | N/A | N/A | N/A | N/A | 4
WM. B. MORSE LUMBER - RC MAT. | S | 13-0272 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4
WM. B. MORSE LUMBER- LUMBER MAT | S | 13-0272 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER- TRIM | S | 13-0272 | 2014-07-01 | N/A | 4 | N/A | N/A | N/A | 4 | 4
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2014-02-01 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2014-02-01 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ALEXANDER MITCHELL & SON | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2014-02-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BGI INTERIORS | S | 13-0267 | 2014-02-01 | N/A | 5 | 5 | N/A | N/A | 4 | 4
BUDGET FENCE INCORPORATED | S | 13-0267 | 2014-02-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CFE, INC. | S | 13-0267 | 2014-02-01 | 3 | 5 | 5 | 5 | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2014-02-01 | 5 | 5 | 5 | 5 | 3 | 3 | 4
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ERIE MATERIALS INC. | S | 13-0267 | 2014-02-01 | N/A | 4 | N/A | N/A | 4 | 4 | 4
FILBIN PAINTING INC. | S | 13-0267 | 2014-02-01 | 4 | 4 | 3 | 4 | 4 | N/A | 2
GORICK CONSTRUCTION | S | 13-0267 | 2014-02-01 | 1 | 3 | 4 | 5 | 3 | 3 | 3 | poor communication
HOMER C GOW & SONS | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2014-02-01 | 3 | 4 | 4 | 4 | N/A | N/A | 4
L.A.PAINTING, INC. | S | 13-0267 | 2014-02-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
MATCO ELECTRIC | S | 13-0267 | 2014-02-01 | 4 | 5 | 5 | 5 | 5 | 3 | 4 | solid
MESKO GLASS CO. | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2014-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 3
NORTHERN SPACES INC. | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | 5 | N/A
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2014-02-01 | 4 | 2 | 4 | 4 | 4 | 3 | 3 | Very difficult to work with; would not recommend again
RED HAWK FIRE & SECURITY | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2014-02-01 | N/A | 4 | N/A | N/A | 3 | 3 | 2
SCHINDLER ELEVATOR | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3 | Too early
SIMPLEXGRINNELL LP | S | 13-0267 | 2014-02-01 | 5 | 2 | 5 | 5 | N/A | 4 | 4
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2014-02-01 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | good
SURE TEMP COMPANY INC. | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2014-02-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2014-02-01 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company
WILLIAM H. LANE INC. | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2014-02-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2014-02-01 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | office is too busy
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2014-07-01 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2014-07-01 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ALEXANDER MITCHELL & SON | S | 13-0267 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2014-07-01 | N/A | 5 | 5 | N/A | 4 | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0267 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2014-07-01 | 5 | 5 | 5 | 5 | 2 | N/A | 3
BGI INTERIORS | S | 13-0267 | 2014-07-01 | N/A | 5 | 5 | N/A | 5 | 4 | 4 | Delivery strung out
BUDGET FENCE INCORPORATED | S | 13-0267 | 2014-07-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CFE, INC. | S | 13-0267 | 2014-07-01 | 3 | 5 | 3 | 5 | 2 | 2 | 2 | Quality issues with the roof; submittal process was poor; office is difficult to get ahold of
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 13-0267 | 2014-07-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2014-07-01 | N/A | 1 | 2 | N/A | 2 | N/A | 2 | poor management of material procurement; send the wrong materials; do not meet delivery dates; do not send full shipments; did not adhere to LCS CO policy
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2014-07-01 | 5 | 5 | 5 | 5 | 4 | 3 | 4
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ERIE MATERIALS INC. | S | 13-0267 | 2014-07-01 | N/A | 4 | N/A | N/A | 4 | 4 | 4
FILBIN PAINTING INC. | S | 13-0267 | 2014-07-01 | 4 | 4 | 5 | 2 | 4 | N/A | 2 | Office does not communicatte; understaffed for the amount of work they bid
GORICK CONSTRUCTION | S | 13-0267 | 2014-07-01 | 1 | 4 | 4 | 5 | 3 | 3 | 3
HOMER C GOW & SONS | S | 13-0267 | 2014-07-01 | 4 | 5 | 5 | 5 | 3 | N/A | 3
J&R SPECIALTIES | S | 13-0267 | 2014-07-01 | 4 | 3 | 4 | 3 | 4 | 4 | 3
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2014-07-01 | 3 | 5 | 5 | 5 | 3 | N/A | 3
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2014-07-01 | 3 | 4 | 4 | 4 | N/A | N/A | 4
L.A.PAINTING, INC. | S | 13-0267 | 2014-07-01 | 3 | 2 | 3 | 4 | 2 | 4 | 2 | Not concerend about quality of finished product; Unresponsive
MATCO ELECTRIC | S | 13-0267 | 2014-07-01 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | solid
MESKO GLASS CO. | S | 13-0267 | 2014-07-01 | 3 | 1 | 3 | 3 | 4 | 4 | 4 | Difficult to get ahold of and manage
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHERN SPACES INC. | S | 13-0267 | 2014-07-01 | 3 | 3 | 4 | 4 | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 13-0267 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | 5 | N/A
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2014-07-01 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | Very difficult to work with; Need to descope well
RED HAWK FIRE & SECURITY | S | 13-0267 | 2014-07-01 | 4 | 4 | 4 | 4 | 3 | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2014-07-01 | 3 | 4 | 5 | 4 | 3 | 3 | 2 | difficult to schedule during school. Work in summer
SCHINDLER ELEVATOR | S | 13-0267 | 2014-07-01 | 4 | 4 | 3 | 4 | 4 | 4 | 3 | Having trouble getting them onsite to repair a dented door
SIMPLEXGRINNELL LP | S | 13-0267 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | good
SURE TEMP COMPANY INC. | S | 13-0267 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2014-07-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2014-07-01 | 4 | 4 | 5 | 4 | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2014-07-01 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company, would recommend
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2014-07-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2014-07-01 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | office is too busy
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2014-07-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0270 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PRO CARPET INC. | S | 13-0270 | 2014-07-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RADEC CORPORATION | S | 13-0270 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2014-07-01 | 4 | 3 | 3 | 4 | N/A | 3 | 3
SANITAIRE CLEANING CO., INC. | S | 13-0270 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SERWAY BROTHERS INC. | S | 13-0270 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
UNICO FINISHING SYSTEMS | S | 13-0270 | 2014-07-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2014-07-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | Great performance
US CEILING CORP. | S | 13-0270 | 2014-07-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 13-0270 | 2014-07-01 | 4 | 4 | 4 | 3 | N/A | 4 | 3
WINDOW ACCENTS INC. | S | 13-0270 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
A.W. THERRIEN CO.,INC. | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AP DAILEY CUSTOM LAMINATING CORP. | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BLDRS INSTALLED PROD. | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOSTON SHOWCASE COMPANY | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOUCHER ACOUSTIC CONTRACTOR INC. | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CADIEUX FLOORING | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAPRIOLI PAINTING | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONVENANT FIRE PROTECTION | S | 14-0288 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DANIELS ELECTRIC CORPORATION | S | 14-0288 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DENRON PLUMBING AND HVAC, LLC | S | 14-0288 | 2014-07-01 | 5 | 4 | 4 | 4 | 4 | 3 | 4
DOOR CONTROL INC. | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENVIROVANTAGE INC. | S | 14-0288 | 2014-07-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
GRANITE STATE SPECIALTIES | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JAMES VERRA ASSOC. | S | 14-0288 | 2014-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MALTHOUSE CONSTRUCTION | S | 14-0288 | 2014-07-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
MAX T. DOLAND | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
METRO WALLS | S | 14-0288 | 2014-07-01 | 3 | 4 | 4 | 4 | 4 | 4 | 3
MIDDLETON BLDG SPLY | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MORSE SASH & DOOR | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH PLATE GLASS CORP. | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NOVEL IRON WORKS | S | 14-0288 | 2014-07-01 | 4 | 4 | N/A | N/A | 3 | 4 | 3
PARADIGM WINDOWS | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PISCATAQUA LANDSCAPING | S | 14-0288 | 2014-07-01 | 3 | 4 | 3 | 4 | 4 | 4 | 4
SCOTT LAWSON GROUP | S | 14-0288 | 2014-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SEVERINO TRUCKING CO, INC. | S | 14-0288 | 2014-07-01 | 4 | 3 | 4 | 3 | 4 | 4 | 4
SOUTHERN NH POURED CONCRETE CONSTRUCTION INC. | S | 14-0288 | 2014-07-01 | 4 | 4 | 4 | 4 | 3 | 4 | 3
BARFIELD FENCE & WALL | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | 4 | 3 | 4
ARCI, LTD. | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
BOSTON SHOWCASE COMPANY | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOUCHER ACOUSTIC CONTRACTOR INC. | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CADIEUX FLOORING | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAPRIOLI PAINTING | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONVENANT FIRE PROTECTION | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DANIELS ELECTRIC CORPORATION | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DENRON PLUMBING AND HVAC, LLC | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DOOR CONTROL INC. | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENVIROVANTAGE INC. | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRANITE STATE SPECIALTIES | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JAMES VERRA ASSOC. | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MALTHOUSE CONSTRUCTION | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
METRO WALLS | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIDDLETON BLDG SPLY | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MORSE SASH & DOOR | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH PLATE GLASS CORP. | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NOVEL IRON WORKS | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PARADIGM WINDOWS | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PISCATAQUA LANDSCAPING | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCOTT LAWSON GROUP | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SEVERINO TRUCKING CO, INC. | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUTHERN NH POURED CONCRETE CONSTRUCTION INC. | S | 14-0288 | 2014-08-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING | S | 13-0273 | 2014-08-01 | 3 | 4 | 4 | 4 | N/A | 3 | 4
BERGERON FRAMING - MATERIALS | S | 13-0273 | 2014-08-01 | N/A | 4 | 3 | N/A | N/A | 3 | 3
BRANT & SON | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
CABLE ELECTRICAL SERVICES | S | 13-0273 | 2014-08-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3
DELACRUZ DRYWALL PLASTERING | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 2 | 1 | This contractor has been put on notice several times to submit contract and they have not
DRMP INC | S | 13-0273 | 2014-08-01 | 4 | 4 | 4 | 4 | N/A | N/A | 2 | this sub has a new scheduler and this will hopefully help with the scheduling issues.
EAST COAST POURED FLOORS | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
EVOLUTION POOLS & CONSTRUCTION SERVICES, INC. | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
FLORIDA DOOR SOLUTIONS | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | 2
FOX WINDOWS | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
G&L EXTERIORS | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
GULF COAST PLUMBING | S | 13-0273 | 2014-08-01 | 4 | 5 | 4 | 4 | 5 | 5 | 4
HAVEN CONTRACTING, INC | S | 13-0273 | 2014-08-01 | 3 | 4 | 4 | 3 | 4 | 3 | 3 | field workers are very good
JEL SITE DEVELOPMENT INC. | S | 13-0273 | 2014-08-01 | 4 | 3 | 4 | 3 | 4 | 4 | 3 | Small operation, apparently capable of doing this but were perform well so far
JL WILSON CONCRETE, INC. | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
MALIBU FLOORS | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
MASTER WOOD CRAFT CABINETRY | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | 4 | 3 | 3
PRECISION GUTTERS | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
REW LANDSCAPE | S | 13-0273 | 2014-08-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SHADES TO YOU | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
SOUSA CABINETS | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STONE INSTALLATION | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE LUCKHARDT GROUP | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4
THYSSENKRUPP ELEVATOR | S | 13-0273 | 2014-08-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
TRUSSWAY MFG. | S | 13-0273 | 2014-08-01 | 3 | 5 | 4 | N/A | N/A | 4 | 4
UNICORN PAINTING INC. | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
UNIVERSAL BUILDING SUPPLY | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
UNIVERSAL ENGINEERING SCIENCES | S | 13-0273 | 2014-08-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
VALUE LIGHTING | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | 4 | 3 | 4
WATERWATCH CORPORATION | S | 13-0273 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WAYNE AUTOMATIC SPRINKLERS | S | 13-0273 | 2014-08-01 | 4 | 5 | 4 | 5 | N/A | 3 | 4
ACQUATIC LANDSCAPING | S | 13-0276 | 2014-08-01 | 4 | 3 | 3 | 3 | 4 | 3 | N/A
GOMEZ & SONS | S | 13-0276 | 2014-08-01 | 5 | 5 | 4 | 4 | 4 | N/A | N/A
MEISNER | S | 13-0276 | 2014-08-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
OHL | S | 13-0276 | 2014-08-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A | Coordination of getting proper man power at the proper time was an issue
SOLUTIONS | S | 13-0276 | 2014-08-01 | 4 | 3 | 3 | 4 | 4 | 4 | N/A | Sub has a hard time following a schedule- there has been an improvement in schedule management
SPI | S | 13-0276 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
STATE LINE PRODUCTS | S | 13-0276 | 2014-08-01 | 5 | 5 | 5 | 5 | N/A | 3 | N/A
TROPIC | S | 13-0276 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
WILDCAT | S | 13-0276 | 2014-08-01 | 3 | 1 | 2 | 2 | N/A | N/A | N/A | Wildcat waited too long to staff up. Would not use this sub again.
Y&T | S | 13-0276 | 2014-08-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
A.D.W INC. | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACE WINDOWS | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUILDERS INSTALLED PRODUCTS | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CGM TILE & STONE, INC | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EARL B. FEINDEN | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD & THOMAS O'CONNOR INC | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GENSON OVERHEAD DOOR, INC | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IRV SCHRODER AND SONS | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KONE, INC | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRUEGLER CONTRACTING & REMODELING, LLC | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAWRENCE D. COON | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LD COON | S | 14-0291 | 2014-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LECESSE PROCUREMENT LLC | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MORSE SASH & DOOR | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OCONNOR | S | 14-0291 | 2014-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PINNACLE ROOFING INC | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RBM GUARDIAN FIRE PROTECTION INC | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RJ GRAVES CONSTRUCTION INC. | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRIPOINT STONE | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDUSEN & STEVES LAND SURVEYORS | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0291 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUSA CABINETS | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STONE INSTALLATION | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUNBELT GATED ACCESS SYSTEMS | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE LUCKHARDT GROUP | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0273 | 2014-11-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
SIMPSON ENVIRONMENTAL | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHADES TO YOU | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
JEL SITE DEVELOPMENT INC. | S | 13-0273 | 2014-11-01 | 4 | 3 | 4 | 3 | 2 | 4 | 3 | Small operation, apparently capable of doing this but were perform well so far
REW LANDSCAPE | S | 13-0273 | 2014-11-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
PRECISION GUTTERS | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
MASTER WOOD CRAFT CABINETRY | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | 4 | 3 | 3
MASSEY SERVICES | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MALIBU FLOORS | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
KISSIMMEE CONSTRUCTION | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JL WILSON CONCRETE, INC. | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
VANDYKE PAINTING COMPANY | S | 14-0285 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
SYRACUSE MOSAIC | S | 14-0285 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SERWAY BROTHERS INC. | S | 14-0285 | 2014-10-01 | 3 | 4 | 4 | 4 | 4 | 3 | 3
PRO CARPET INC. | S | 14-0285 | 2014-10-01 | 4 | 3 | 3 | 3 | 4 | 4 | 4
MORSE SASH & DOOR | S | 14-0285 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
CONSTRUCTION SPECIALITIES INC. | S | 14-0285 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
MAX T. DOLAND | S | 14-0285 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MGM INSULATION | S | 14-0285 | 2014-10-01 | 4 | 4 | 5 | 4 | 4 | 4 | 4
BENEDETTI BUILDERS | S | 14-0285 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
CEDAR ENTERPRISES | S | 14-0285 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ASI SIGNAGE | S | 14-0285 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 5 | 4
AJAY GLASS & MIRROR | S | 14-0285 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 2 | 3 | Paperwork side is not good
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0285 | 2014-09-01 | 4 | 4 | 4 | 3 | N/A | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0285 | 2014-10-01 | 3 | 4 | 4 | 4 | 4 | N/A | 4
WHIRLPOOL CORPORATION | S | 14-0285 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 5 | 4
WEYDMAN ELECTRIC | S | 14-0285 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 14-0285 | 2014-09-01 | 4 | 3 | 3 | 3 | 4 | 4 | 4
SERWAY BROTHERS INC. | S | 14-0285 | 2014-09-01 | 3 | 4 | 4 | 4 | 4 | 3 | 3
SYRACUSE MOSAIC | S | 14-0285 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2014-08-01 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2014-08-01 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ALEXANDER MITCHELL & SON | S | 13-0267 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2014-08-01 | N/A | 5 | 5 | N/A | 4 | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0267 | 2014-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2014-08-01 | 5 | 5 | 5 | 5 | 2 | N/A | 3
BGI INTERIORS | S | 13-0267 | 2014-08-01 | N/A | 5 | 5 | N/A | 5 | 4 | 4 | Delivery strung out
BUDGET FENCE INCORPORATED | S | 13-0267 | 2014-08-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CFE, INC. | S | 13-0267 | 2014-08-01 | 3 | 5 | 3 | 5 | 2 | 2 | 2 | Quality issues with the roof; submittal process was poor; office is difficult to get ahold of
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 13-0267 | 2014-08-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2014-08-01 | N/A | 1 | 2 | N/A | 2 | N/A | 2 | poor management of material procurement; send the wrong materials; do not meet delivery dates; do not send full shipments; did not adhere to LCS CO policy
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2014-08-01 | 5 | 5 | 5 | 5 | 4 | 3 | 4
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ERIE MATERIALS INC. | S | 13-0267 | 2014-08-01 | N/A | 4 | N/A | N/A | 4 | 4 | 4
FILBIN PAINTING INC. | S | 13-0267 | 2014-08-01 | 4 | 4 | 5 | 2 | 4 | N/A | 2 | Office does not communicatte; understaffed for the amount of work they bid
GORICK CONSTRUCTION | S | 13-0267 | 2014-08-01 | 1 | 4 | 4 | 5 | 3 | 3 | 3
HOMER C GOW & SONS | S | 13-0267 | 2014-08-01 | 4 | 5 | 5 | 5 | 3 | N/A | 3
J&R SPECIALTIES | S | 13-0267 | 2014-08-01 | 4 | 3 | 4 | 3 | 4 | 4 | 3
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2014-08-01 | 3 | 5 | 5 | 5 | 3 | N/A | 3
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2014-08-01 | 3 | 4 | 4 | 4 | N/A | N/A | 4
L.A.PAINTING, INC. | S | 13-0267 | 2014-08-01 | 3 | 2 | 3 | 4 | 2 | 4 | 2 | Not concerend about quality of finished product; Unresponsive
MATCO ELECTRIC | S | 13-0267 | 2014-08-01 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | solid
MESKO GLASS CO. | S | 13-0267 | 2014-08-01 | 3 | 1 | 3 | 3 | 4 | 4 | 4 | Difficult to get ahold of and manage
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHERN SPACES INC. | S | 13-0267 | 2014-08-01 | 3 | 3 | 4 | 4 | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 13-0267 | 2014-08-01 | 4 | 4 | 4 | 4 | N/A | 5 | N/A
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2014-08-01 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | Very difficult to work with; Need to descope well
RED HAWK FIRE & SECURITY | S | 13-0267 | 2014-08-01 | 4 | 4 | 4 | 4 | 3 | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2014-08-01 | 3 | 3 | 5 | 3 | 3 | 3 | 2 | Difficult to schedule during school- Work in summer. Work is not done when expected.
SCHINDLER ELEVATOR | S | 13-0267 | 2014-08-01 | 4 | 4 | 3 | 4 | 4 | 4 | 3 | Having trouble getting them onsite to repair a dented door
SIMPLEXGRINNELL LP | S | 13-0267 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2014-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | good
SURE TEMP COMPANY INC. | S | 13-0267 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2014-08-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2014-08-01 | 4 | 4 | 5 | 4 | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2014-08-01 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company, would recommend
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2014-08-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2014-08-01 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | office is too busy
AIIA CONSTRUCTION COMPANY, INC | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4
AJAY GLASS & MIRROR | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | Paperwork side is not good
ASI SIGNAGE | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 5 | 4
BENEDETTI BUILDERS | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4
MAX T. DOLAND | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MGM INSULATION | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MORSE SASH & DOOR | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
PRO CARPET INC. | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SERWAY BROTHERS INC. | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
SYRACUSE MOSAIC | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
VANDYKE PAINTING COMPANY | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
WEYDMAN ELECTRIC | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 5 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0285 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
VANDYKE PAINTING COMPANY | S | 14-0285 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
MGM INSULATION | S | 14-0285 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MORSE SASH & DOOR | S | 14-0285 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MAX T. DOLAND | S | 14-0285 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
CONSTRUCTION SPECIALITIES INC. | S | 14-0285 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
CEDAR ENTERPRISES | S | 14-0285 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
BENEDETTI BUILDERS | S | 14-0285 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
ASI SIGNAGE | S | 14-0285 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 5 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0285 | 2014-09-01 | 3 | 4 | 4 | 4 | 4 | N/A | 4
AJAY GLASS & MIRROR | S | 14-0285 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 2 | 3 | Paperwork side is not good
SCHINDLER ELEVATOR | S | 13-0267 | 2014-10-05 | 4 | 4 | 3 | 4 | 4 | 4 | 3 | Having trouble getting them onsite to repair a dented door
SIMPLEXGRINNELL LP | S | 13-0267 | 2014-10-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2014-10-05 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | good
SURE TEMP COMPANY INC. | S | 13-0267 | 2014-10-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2014-10-05 | 4 | 3 | 4 | 4 | 3 | 3 | 3
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2014-10-05 | 4 | 4 | 5 | 4 | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2014-10-05 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company, would recommend
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2014-10-05 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2014-10-05 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | office is too busy
J&R SPECIALTIES | S | 13-0270 | 2014-09-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
J&K CONSTRUCTION | S | 13-0270 | 2014-09-01 | 3 | 5 | 4 | 5 | N/A | 4 | 5
IMPACT PAINTING LLC | S | 13-0270 | 2014-09-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
HENRY ISAACS HOME REMODELING (SIDING) | S | 13-0270 | 2014-09-01 | 1 | 4 | 4 | 4 | 4 | N/A | 4 | Had a life threatening violation in the past month
FLORIDA DOOR SOLUTIONS | S | 13-0273 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
FOX WINDOWS | S | 13-0273 | 2014-11-01 | 4 | 4 | 3 | 4 | N/A | 3 | 3
G&L EXTERIORS | S | 13-0273 | 2014-11-01 | 3 | 4 | 4 | 4 | N/A | 3 | 3
GULF COAST PLUMBING | S | 13-0273 | 2014-11-01 | 4 | 5 | 4 | 4 | 5 | 5 | 4
HAVEN CONTRACTING, INC | S | 13-0273 | 2014-11-01 | 3 | 4 | 4 | 3 | 4 | 3 | 3 | field workers are very good
EVOLUTION POOLS & CONSTRUCTION SERVICES, INC. | S | 13-0273 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
EAST COAST POURED FLOORS | S | 13-0273 | 2014-11-01 | 2 | 4 | 3 | 4 | N/A | 4 | 3
DRMP INC | S | 13-0273 | 2014-11-01 | 4 | 4 | 4 | 4 | N/A | N/A | 2 | this sub has a new scheduler and this will hopefully help with the scheduling issues.
DELACRUZ DRYWALL PLASTERING | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 2 | 1 | This contractor has been put on notice several times to submit contract and they have not
CENTRAL FLORIDA SAFETY | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING | S | 13-0273 | 2014-11-01 | 3 | 4 | 4 | 4 | N/A | 3 | 4
BERGERON FRAMING - MATERIALS | S | 13-0273 | 2014-11-01 | N/A | 4 | 3 | N/A | N/A | 3 | 3
BERMAN PROPERTY MAINTENANCE Y CONSTRUCTION | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRANT & SON | S | 13-0273 | 2014-11-01 | 3 | 3 | 4 | 4 | N/A | 3 | N/A
CABLE ELECTRICAL SERVICES | S | 13-0273 | 2014-11-01 | 3 | 4 | 4 | 4 | 4 | 3 | 3
BARFIELD FENCE Y FABRICATION | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
WHIRLPOOL CORPORATION | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARCI, LTD. | S | 13-0273 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 13-0273 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BARFIELD FENCE & WALL | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAYNE AUTOMATIC SPRINKLERS | S | 13-0273 | 2014-10-01 | 4 | 5 | 4 | 3 | N/A | 3 | 4
WATERWATCH CORPORATION | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WALL AND SIGN CONCEPTS | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VALUE LIGHTING | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | 4 | 3 | 4
UNIVERSAL ENGINEERING SCIENCES | S | 13-0273 | 2014-10-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
UNIVERSAL BUILDING SUPPLY | S | 13-0273 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
TRUSSWAY MFG. | S | 13-0273 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNICORN PAINTING INC. | S | 13-0273 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
THYSSENKRUPP ELEVATOR | S | 13-0273 | 2014-10-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
DRMP INC | S | 13-0273 | 2014-09-01 | 4 | 4 | 4 | 4 | N/A | N/A | 2 | this sub has a new scheduler and this will hopefully help with the scheduling issues.
DELACRUZ DRYWALL PLASTERING | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 2 | 1 | This contractor has been put on notice several times to submit contract and they have not
CABLE ELECTRICAL SERVICES | S | 13-0273 | 2014-09-01 | 3 | 4 | 4 | 4 | 4 | 3 | 3
SPI | S | 13-0276 | 2014-11-01 | 4 | 4 | 3 | 4 | 3 | 3 | N/A
CENTRAL FLORIDA SAFETY | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRANT & SON | S | 13-0273 | 2014-09-01 | 3 | 3 | 4 | 4 | N/A | 3 | N/A
BERMAN PROPERTY MAINTENANCE Y CONSTRUCTION | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING - MATERIALS | S | 13-0273 | 2014-09-01 | N/A | 4 | 3 | N/A | N/A | 3 | 3
BARFIELD FENCE Y FABRICATION | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING | S | 13-0273 | 2014-09-01 | 3 | 4 | 4 | 4 | N/A | 3 | 4
BARFIELD FENCE & WALL | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
Y&T | S | 13-0276 | 2014-11-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
ARCI, LTD. | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | 4 | 3 | 4
STATE LINE PRODUCTS | S | 13-0276 | 2014-11-01 | 5 | 5 | 5 | 5 | N/A | 3 | N/A
TROPIC | S | 13-0276 | 2014-11-01 | 4 | 4 | 4 | 4 | N/A | 3 | N/A
WILDCAT | S | 13-0276 | 2014-11-01 | 3 | 1 | 2 | 2 | N/A | N/A | N/A | Wildcat waited too long to staff up. Would not use this sub again.
HENRY ISAACS HOME REMODELING (ROOFING) | S | 13-0270 | 2014-09-01 | 1 | 4 | 4 | 4 | N/A | 4 | 4 | Had a life threatening violation in the past month
SUNBELT GATED ACCESS SYSTEMS | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE LUCKHARDT GROUP | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STONE INSTALLATION | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUSA CABINETS | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHADES TO YOU | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
SIMPSON ENVIRONMENTAL | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MASTER WOOD CRAFT CABINETRY | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | 4 | 3 | 3
PRECISION GUTTERS | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
REW LANDSCAPE | S | 13-0273 | 2014-10-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
MASSEY SERVICES | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MALIBU FLOORS | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
KISSIMMEE CONSTRUCTION | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
JL WILSON CONCRETE, INC. | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
SOUTHERN COAST ROOFING | S | 13-0276 | 2014-11-01 | 4 | 4 | 4 | 4 | 3 | 3 | N/A
GOMEZ & SONS | S | 13-0276 | 2014-11-01 | 5 | 5 | 4 | 4 | 4 | N/A | N/A
MEISNER | S | 13-0276 | 2014-11-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
OHL | S | 13-0276 | 2014-11-01 | 3 | 2 | 2 | 2 | 3 | 2 | N/A | Has a hard time following a schedule including their own.
PARAMOUNT | S | 13-0276 | 2014-11-01 | 4 | 3 | 4 | 4 | N/A | 3 | N/A
SOLUTIONS | S | 13-0276 | 2014-11-01 | 4 | 3 | 3 | 4 | 4 | 4 | N/A | Sub has a hard time following a schedule- there has been an improvement in schedule management
ACQUATIC LANDSCAPING | S | 13-0276 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | took their scores off until they get back on site
Y&T | S | 13-0276 | 2014-10-01 | 5 | 5 | 4 | 4 | 4 | N/A | N/A
WILDCAT | S | 13-0276 | 2014-10-01 | 3 | 1 | 2 | 2 | N/A | N/A | N/A | Wildcat waited too long to staff up. Would not use this sub again.
SOLUTIONS | S | 13-0276 | 2014-10-01 | 4 | 3 | 3 | 4 | 4 | 4 | N/A | Sub has a hard time following a schedule- there has been an improvement in schedule management
SPI | S | 13-0276 | 2014-10-01 | 4 | 4 | 3 | 3 | 3 | 3 | N/A
STATE LINE PRODUCTS | S | 13-0276 | 2014-10-01 | 5 | 5 | 5 | 5 | N/A | 3 | N/A
TROPIC | S | 13-0276 | 2014-10-01 | 4 | 4 | 4 | 4 | N/A | 3 | N/A
SOUTHERN COAST ROOFING | S | 13-0276 | 2014-10-01 | 4 | 4 | 4 | 4 | 3 | 3 | N/A
OHL | S | 13-0276 | 2014-10-01 | 3 | 2 | 2 | 2 | 3 | 2 | N/A | Coordination of getting proper man power at the proper time is still an issue. Quality is a problem
PARAMOUNT | S | 13-0276 | 2014-10-01 | 4 | 3 | 4 | 3 | N/A | 3 | N/A
MEISNER | S | 13-0276 | 2014-10-01 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
GOMEZ & SONS | S | 13-0276 | 2014-10-01 | 5 | 5 | 4 | 4 | 4 | N/A | N/A
ACQUATIC LANDSCAPING | S | 13-0276 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | took their scores off until they get back on site
RED HAWK FIRE & SECURITY | S | 13-0267 | 2014-10-05 | 4 | 4 | 4 | 4 | 3 | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2014-10-05 | 3 | 3 | 5 | 3 | 3 | 3 | 2 | Difficult to schedule during school- Work in summer. Work is not done when expected.
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2014-10-05 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | Very difficult to work with; Need to descope well
OLDCASTLE PRECAST | S | 13-0267 | 2014-10-05 | 4 | 4 | 4 | 4 | N/A | 5 | N/A
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2014-10-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHERN SPACES INC. | S | 13-0267 | 2014-10-05 | 3 | 3 | 4 | 4 | N/A | N/A | N/A
MATCO ELECTRIC | S | 13-0267 | 2014-10-05 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | solid
MESKO GLASS CO. | S | 13-0267 | 2014-10-05 | 3 | 1 | 3 | 3 | 4 | 4 | 4 | Difficult to get ahold of and manage
L.A.PAINTING, INC. | S | 13-0267 | 2014-10-05 | 3 | 2 | 3 | 4 | 2 | 4 | 2 | Not concerend about quality of finished product; Unresponsive
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2014-10-05 | 3 | 4 | 4 | 4 | N/A | N/A | 4
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2014-10-05 | 3 | 5 | 5 | 5 | 3 | N/A | 3
J&R SPECIALTIES | S | 13-0267 | 2014-10-05 | 4 | 3 | 4 | 3 | 4 | 4 | 3
GORICK CONSTRUCTION | S | 13-0267 | 2014-10-05 | 1 | 4 | 4 | 5 | 3 | 3 | 3
HOMER C GOW & SONS | S | 13-0267 | 2014-10-05 | 4 | 5 | 5 | 5 | 3 | N/A | 3
FILBIN PAINTING INC. | S | 13-0267 | 2014-10-05 | 4 | 4 | 5 | 2 | 4 | N/A | 2 | Office does not communicatte; understaffed for the amount of work they bid
ERIE MATERIALS INC. | S | 13-0267 | 2014-10-05 | N/A | 4 | N/A | N/A | 4 | 4 | 4
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2014-10-05 | 5 | 5 | 5 | 5 | 4 | 3 | 4
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2014-10-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 13-0267 | 2014-10-05 | 3 | 3 | 3 | 3 | 3 | 3 | 3
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2014-10-05 | N/A | 1 | 2 | N/A | 2 | N/A | 2 | poor management of material procurement; send the wrong materials; do not meet delivery dates; do not send full shipments; did not adhere to LCS CO policy
CFE, INC. | S | 13-0267 | 2014-10-05 | 3 | 5 | 3 | 5 | 2 | 2 | 2 | Quality issues with the roof; submittal process was poor; office is difficult to get ahold of
BUDGET FENCE INCORPORATED | S | 13-0267 | 2014-10-05 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2014-10-05 | 5 | 5 | 5 | 5 | 2 | N/A | 3
BGI INTERIORS | S | 13-0267 | 2014-10-05 | N/A | 5 | 5 | N/A | 5 | 4 | 4 | Delivery strung out
JEL SITE DEVELOPMENT INC. | S | 13-0273 | 2014-10-01 | 4 | 3 | 4 | 3 | 2 | 4 | 3 | Small operation, apparently capable of doing this but were perform well so far
HAVEN CONTRACTING, INC | S | 13-0273 | 2014-10-01 | 3 | 4 | 4 | 3 | 4 | 3 | 3 | field workers are very good
GULF COAST PLUMBING | S | 13-0273 | 2014-10-01 | 4 | 5 | 4 | 4 | 5 | 5 | 4
G&L EXTERIORS | S | 13-0273 | 2014-10-01 | 3 | 4 | 4 | 4 | N/A | 3 | 3
FLORIDA DOOR SOLUTIONS | S | 13-0273 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
FOX WINDOWS | S | 13-0273 | 2014-10-01 | 4 | 4 | 3 | 4 | N/A | 3 | 3
EAST COAST POURED FLOORS | S | 13-0273 | 2014-10-01 | 2 | 4 | 3 | 4 | N/A | 4 | 3
EVOLUTION POOLS & CONSTRUCTION SERVICES, INC. | S | 13-0273 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DRMP INC | S | 13-0273 | 2014-10-01 | 4 | 4 | 4 | 4 | N/A | N/A | 2 | this sub has a new scheduler and this will hopefully help with the scheduling issues.
CENTRAL FLORIDA SAFETY | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DELACRUZ DRYWALL PLASTERING | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 2 | 1 | This contractor has been put on notice several times to submit contract and they have not
CABLE ELECTRICAL SERVICES | S | 13-0273 | 2014-10-01 | 3 | 4 | 4 | 4 | 4 | 3 | 3
BRANT & SON | S | 13-0273 | 2014-10-01 | 3 | 3 | 4 | 4 | N/A | 3 | N/A
BERMAN PROPERTY MAINTENANCE Y CONSTRUCTION | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BERGERON FRAMING - MATERIALS | S | 13-0273 | 2014-10-01 | N/A | 4 | 3 | N/A | N/A | 3 | 3
BERGERON FRAMING | S | 13-0273 | 2014-10-01 | 3 | 4 | 4 | 4 | N/A | 3 | 4
BARFIELD FENCE Y FABRICATION | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BARFIELD FENCE & WALL | S | 13-0273 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 13-0273 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ARCI, LTD. | S | 13-0273 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAYNE AUTOMATIC SPRINKLERS | S | 13-0273 | 2014-09-01 | 4 | 5 | 4 | 3 | N/A | 3 | 4
WATERWATCH CORPORATION | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WALL AND SIGN CONCEPTS | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VALUE LIGHTING | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | 4 | 3 | 4
UNIVERSAL ENGINEERING SCIENCES | S | 13-0273 | 2014-09-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
UNIVERSAL BUILDING SUPPLY | S | 13-0273 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNICORN PAINTING INC. | S | 13-0273 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
TRUSSWAY MFG. | S | 13-0273 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL COUNTY GUTTER CO., INC. | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 13-0270 | 2014-02-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
BETLEM RESIDENTIAL | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2014-02-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BRIDGEWATER INTERNATIONAL | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BROCCOLO TREE & LAWN CARE | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2014-02-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
FISHER ASSOCIATES | S | 13-0270 | 2014-02-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
GARAGE DOORS UNLIMITED | S | 13-0270 | 2014-02-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2014-02-01 | 2 | 4 | 4 | 4 | N/A | 4 | 4
HENRY ISAACS HOME REMODELING (ROOFING) | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING (SIDING) | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMPACT PAINTING LLC | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&K CONSTRUCTION | S | 13-0270 | 2014-02-01 | 4 | 5 | 4 | 5 | N/A | 4 | 5
J&R SPECIALTIES | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2014-02-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
MAX T. DOLAND | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0270 | 2014-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MONTGOMERY TRUSS | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ONTARIO EXTERIORS, INC | S | 13-0270 | 2014-02-01 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | Slow office
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2014-02-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0270 | 2014-02-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PRO CARPET INC. | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 13-0270 | 2014-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SANITAIRE CLEANING CO., INC. | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
UNICO FINISHING SYSTEMS | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2014-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
US CEILING CORP. | S | 13-0270 | 2014-02-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2014-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 13-0270 | 2014-08-01 | 3 | 4 | 4 | 5 | 4 | N/A | 4
ALL COUNTY GUTTER CO., INC. | S | 13-0270 | 2014-08-01 | 3 | 3 | 3 | 3 | N/A | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0270 | 2014-08-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
BETLEM RESIDENTIAL | S | 13-0270 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2014-08-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BRIDGEWATER INTERNATIONAL | S | 13-0270 | 2014-08-01 | 3 | 2 | 2 | 3 | N/A | 4 | 4 | Missed some schedule targets
BROCCOLO TREE & LAWN CARE | S | 13-0270 | 2014-08-01 | 4 | 3 | 3 | 3 | N/A | 3 | 4
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2014-08-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
FISHER ASSOCIATES | S | 13-0270 | 2014-08-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
GARAGE DOORS UNLIMITED | S | 13-0270 | 2014-08-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING (ROOFING) | S | 13-0270 | 2014-08-01 | 1 | 4 | 4 | 4 | N/A | 4 | 4 | Had a life threatening violation in the past month
HENRY ISAACS HOME REMODELING (SIDING) | S | 13-0270 | 2014-08-01 | 1 | 4 | 4 | 4 | 4 | N/A | 4 | Had a life threatening violation in the past month
IMPACT PAINTING LLC | S | 13-0270 | 2014-08-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
J&K CONSTRUCTION | S | 13-0270 | 2014-08-01 | 3 | 5 | 4 | 5 | N/A | 4 | 5
J&R SPECIALTIES | S | 13-0270 | 2014-08-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
JACHLES IMPERIAL LTD | S | 13-0270 | 2014-08-01 | 4 | 3 | 3 | 3 | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2014-08-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
MAX T. DOLAND | S | 13-0270 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MIG BUILDING SYSTEMS | S | 13-0270 | 2014-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MONTGOMERY TRUSS | S | 13-0270 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ONTARIO EXTERIORS, INC | S | 13-0270 | 2014-08-01 | 4 | 2 | 4 | 2 | 2 | 3 | 2 | Slow office; pulled manpower when there was work to be done; submitting COs for work that is in their contract
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2014-08-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0270 | 2014-08-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PRO CARPET INC. | S | 13-0270 | 2014-08-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RADEC CORPORATION | S | 13-0270 | 2014-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2014-08-01 | 4 | 3 | 3 | 4 | N/A | 3 | 3
SANITAIRE CLEANING CO., INC. | S | 13-0270 | 2014-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SERWAY BROTHERS INC. | S | 13-0270 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
UNICO FINISHING SYSTEMS | S | 13-0270 | 2014-08-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2014-08-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | Great performance
US CEILING CORP. | S | 13-0270 | 2014-08-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 13-0270 | 2014-08-01 | 4 | 4 | 4 | 3 | N/A | 4 | 3
WINDOW ACCENTS INC. | S | 13-0270 | 2014-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2014-09-03 | 4 | 4 | 5 | 4 | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2014-09-03 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company, would recommend
ALPHA IRON WORKS, LLC | S | 13-0267 | 2014-10-05 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2014-10-05 | N/A | 5 | 5 | N/A | 4 | 4 | 4
ALEXANDER MITCHELL & SON | S | 13-0267 | 2014-10-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2014-09-03 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2014-09-03 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | office is too busy
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2014-10-05 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2014-10-05 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
SURE TEMP COMPANY INC. | S | 13-0267 | 2014-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2014-09-03 | 4 | 3 | 4 | 4 | 3 | 3 | 3
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2014-09-03 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | good
SIMPLEXGRINNELL LP | S | 13-0267 | 2014-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 13-0267 | 2014-09-03 | 4 | 4 | 3 | 4 | 4 | 4 | 3 | Having trouble getting them onsite to repair a dented door
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2014-11-03 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | office is too busy
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2014-11-03 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WILLIAM H. LANE INC. | S | 13-0267 | 2014-11-03 | 3 | 4 | 3 | 4 | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2014-11-03 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company, would recommend
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2014-11-03 | 4 | 4 | 5 | 4 | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2014-11-03 | 4 | 3 | 4 | 4 | 3 | 3 | 3
SURE TEMP COMPANY INC. | S | 13-0267 | 2014-11-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2014-11-03 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | good
SIMPLEXGRINNELL LP | S | 13-0267 | 2014-11-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 13-0267 | 2014-11-03 | 4 | 4 | 3 | 4 | 4 | 4 | 3 | Having trouble getting them onsite to repair a dented door
RED HAWK FIRE & SECURITY | S | 13-0267 | 2014-11-03 | 4 | 4 | 4 | 4 | 3 | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2014-11-03 | 3 | 3 | 5 | 3 | 3 | 3 | 2 | Difficult to schedule during school- Work in summer. Work is not done when expected.
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GARAGE DOORS UNLIMITED | S | 13-0270 | 2014-09-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
FISHER ASSOCIATES | S | 13-0270 | 2014-09-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2014-09-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
BROCCOLO TREE & LAWN CARE | S | 13-0270 | 2014-09-01 | 4 | 2 | 3 | 3 | N/A | 3 | 4
BRIDGEWATER INTERNATIONAL | S | 13-0270 | 2014-09-01 | 3 | 2 | 2 | 3 | N/A | 4 | 4 | Missed some schedule targets
BETLEM RESIDENTIAL | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2014-09-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
ALL COUNTY GUTTER CO., INC. | S | 13-0270 | 2014-09-01 | 3 | 3 | 3 | 3 | N/A | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0270 | 2014-09-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 13-0270 | 2014-09-01 | 3 | 4 | 4 | 5 | 4 | N/A | 4
WHIRLPOOL CORPORATION | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAYNE AUTOMATIC SPRINKLERS | S | 13-0273 | 2014-11-01 | 4 | 5 | 4 | 3 | N/A | 3 | 4
WATERWATCH CORPORATION | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WALL AND SIGN CONCEPTS | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VALUE LIGHTING | S | 13-0273 | 2014-11-01 | N/A | N/A | N/A | N/A | 4 | 3 | 4
UNIVERSAL ENGINEERING SCIENCES | S | 13-0273 | 2014-11-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
UNIVERSAL BUILDING SUPPLY | S | 13-0273 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNICORN PAINTING INC. | S | 13-0273 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
TRUSSWAY MFG. | S | 13-0273 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
THYSSENKRUPP ELEVATOR | S | 13-0273 | 2014-09-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
STONE INSTALLATION | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUNBELT GATED ACCESS SYSTEMS | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE LUCKHARDT GROUP | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | 4 | terminated
SIMPSON ENVIRONMENTAL | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUSA CABINETS | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRECISION GUTTERS | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
REW LANDSCAPE | S | 13-0273 | 2014-09-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SHADES TO YOU | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
MASTER WOOD CRAFT CABINETRY | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | 4 | 3 | 3
MASSEY SERVICES | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MALIBU FLOORS | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
KISSIMMEE CONSTRUCTION | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JL WILSON CONCRETE, INC. | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
AGAPE WHOLESALE FURNITURE | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 13-0272 | 2014-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
CICERO & CICERO | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 13-0272 | 2014-01-01 | 4 | 4 | 4 | 4 | 3 | 4 | 4
DRISCOLL MASONRY RESTORATION | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
F.G. RAYBURN MASON CONTRACTORS, INC | S | 13-0272 | 2014-01-01 | 2 | 4 | 4 | 4 | 4 | 4 | 2 | Safety issues and lack of concern for project
FLOWER CITY GLASS | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IAQ TECHNOLOGIES | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMPACT PAINTING LLC | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL P & H INC. | S | 13-0272 | 2014-01-01 | 4 | 2 | 5 | 4 | N/A | 4 | 4
KJW ASSOCIATES | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
LORI JOHNSON CONTRACTING | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCGURK ELECTRIC, INC. | S | 13-0272 | 2014-01-01 | 4 | 4 | 4 | 4 | N/A | 2 | 4
MCMAHON LARUE ASSOCIATES P.C. | S | 13-0272 | 2014-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | N/A
MECH TECH | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 2 | 4 | Late with submittals
MONTGOMERY TRUSS | S | 13-0272 | 2014-01-01 | 4 | 5 | 4 | 4 | 4 | 4 | 4
NEW YORK STATE FENCE, INC | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRIDE FIRE PROTECTION | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 2 | 4 | Late with submittals
PRO CARPET INC. | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAMAR STEEL SALES, INC | S | 13-0272 | 2014-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHINDLER ELEVATOR | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
SERWAY BROTHERS INC. | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAYSIDE CONTRACTORS | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM B. MORSE LUMBER- STAIR | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER - RC MAT. | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER- LUMBER MAT | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER- TRIM | S | 13-0272 | 2014-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAYUGA LANDSCAPE | S | 14-0289 | 2014-08-01 | 3 | 4 | N/A | 4 | 4 | 3 | 4
GERHARZ EQUIPMENT | S | 14-0289 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRS COMPANIES | S | 14-0289 | 2014-08-01 | 3 | 3 | 4 | 2 | 3 | 2 | 2 | Does not provide sufficient manpower- owner and PM are manning the project; poor submittal process
MCPHERSON BUILDERS | S | 14-0289 | 2014-08-01 | 4 | 4 | N/A | N/A | N/A | 3 | 3
MOD SPACE | S | 14-0289 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLEASANT VALLEY ELEC. | S | 14-0289 | 2014-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PREMIER UTILITY SVC. | S | 14-0289 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TG MILLER | S | 14-0289 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE BRAIN DRAIN | S | 14-0289 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2014-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2014-11-03 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | Very difficult to work with; Need to descope well
OLDCASTLE PRECAST | S | 13-0267 | 2014-11-03 | 4 | 4 | 4 | 4 | N/A | 5 | N/A
NORTHERN SPACES INC. | S | 13-0267 | 2014-11-03 | 3 | 3 | 4 | 4 | N/A | N/A | N/A
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2014-11-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MESKO GLASS CO. | S | 13-0267 | 2014-11-03 | 3 | 1 | 3 | 3 | 4 | 4 | 4 | Difficult to get ahold of and manage
MATCO ELECTRIC | S | 13-0267 | 2014-11-03 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | solid
JEL SITE DEVELOPMENT INC. | S | 13-0273 | 2014-09-01 | 4 | 3 | 4 | 3 | 2 | 4 | 3 | Small operation, apparently capable of doing this but were perform well so far
HAVEN CONTRACTING, INC | S | 13-0273 | 2014-09-01 | 3 | 4 | 4 | 3 | 4 | 3 | 3 | field workers are very good
GULF COAST PLUMBING | S | 13-0273 | 2014-09-01 | 4 | 5 | 4 | 4 | 5 | 5 | 4
EAST COAST POURED FLOORS | S | 13-0273 | 2014-09-01 | 2 | 4 | 3 | 4 | N/A | 4 | 3
EVOLUTION POOLS & CONSTRUCTION SERVICES, INC. | S | 13-0273 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLORIDA DOOR SOLUTIONS | S | 13-0273 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 3 | 2
FOX WINDOWS | S | 13-0273 | 2014-09-01 | 4 | 4 | 3 | 4 | N/A | 3 | 3
G&L EXTERIORS | S | 13-0273 | 2014-09-01 | 3 | 4 | 4 | 4 | N/A | 3 | 3
L.A.PAINTING, INC. | S | 13-0267 | 2014-11-03 | 3 | 2 | 3 | 4 | 2 | 4 | 2 | Not concerend about quality of finished product; Unresponsive
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2014-11-03 | 3 | 4 | 4 | 4 | N/A | N/A | 4
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2014-11-03 | 3 | 5 | 5 | 5 | 3 | N/A | 3
J&R SPECIALTIES | S | 13-0267 | 2014-11-03 | 4 | 3 | 4 | 3 | 4 | 4 | 3
HOMER C GOW & SONS | S | 13-0267 | 2014-11-03 | 4 | 5 | 5 | 5 | 3 | N/A | 3
RED HAWK FIRE & SECURITY | S | 13-0267 | 2014-09-03 | 4 | 4 | 4 | 4 | 3 | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2014-09-03 | 3 | 3 | 5 | 3 | 3 | 3 | 2 | Difficult to schedule during school- Work in summer. Work is not done when expected.
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2014-09-03 | 4 | 3 | 4 | 4 | 4 | 3 | 3
OLDCASTLE PRECAST | S | 13-0267 | 2014-09-03 | 4 | 4 | 4 | 4 | N/A | 5 | N/A | Very difficult to work with; Need to descope well
NORTHERN SPACES INC. | S | 13-0267 | 2014-09-03 | 3 | 3 | 4 | 4 | N/A | N/A | N/A
MESKO GLASS CO. | S | 13-0267 | 2014-09-03 | 3 | 1 | 3 | 3 | 4 | 4 | 4 | Difficult to get ahold of and manage
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2014-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MATCO ELECTRIC | S | 13-0267 | 2014-09-03 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | solid
GORICK CONSTRUCTION | S | 13-0267 | 2014-09-03 | 1 | 4 | 4 | 5 | 3 | 3 | 3
HOMER C GOW & SONS | S | 13-0267 | 2014-09-03 | 4 | 5 | 5 | 5 | 3 | N/A | 3
J&R SPECIALTIES | S | 13-0267 | 2014-09-03 | 4 | 3 | 4 | 3 | 4 | 4 | 3
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2014-09-03 | 3 | 5 | 5 | 5 | 3 | N/A | 3
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2014-09-03 | 3 | 4 | 4 | 4 | N/A | N/A | 4
L.A.PAINTING, INC. | S | 13-0267 | 2014-09-03 | 3 | 2 | 3 | 4 | 2 | 4 | 2 | Not concerend about quality of finished product; Unresponsive
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2014-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ERIE MATERIALS INC. | S | 13-0267 | 2014-09-03 | N/A | 4 | N/A | N/A | 4 | 4 | 4
FILBIN PAINTING INC. | S | 13-0267 | 2014-09-03 | 4 | 4 | 5 | 2 | 4 | N/A | 2 | Office does not communicatte; understaffed for the amount of work they bid
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2014-09-03 | 5 | 5 | 5 | 5 | 4 | 3 | 4
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2014-09-03 | N/A | 1 | 2 | N/A | 2 | N/A | 2 | poor management of material procurement; send the wrong materials; do not meet delivery dates; do not send full shipments; did not adhere to LCS CO policy
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 13-0267 | 2014-09-03 | 3 | 3 | 3 | 3 | 3 | 3 | 3
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2014-09-03 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2014-09-03 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ALEXANDER MITCHELL & SON | S | 13-0267 | 2014-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2014-09-03 | N/A | 5 | 5 | N/A | 4 | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0267 | 2014-09-03 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2014-09-03 | 5 | 5 | 5 | 5 | 3 | N/A | 3
BGI INTERIORS | S | 13-0267 | 2014-09-03 | N/A | 5 | 5 | N/A | 5 | 4 | 4 | Delivery strung out
BUDGET FENCE INCORPORATED | S | 13-0267 | 2014-09-03 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CFE, INC. | S | 13-0267 | 2014-09-03 | 3 | 5 | 3 | 5 | 2 | 2 | 2 | Quality issues with the roof; submittal process was poor; office is difficult to get ahold of
GORICK CONSTRUCTION | S | 13-0267 | 2014-11-03 | 1 | 4 | 4 | 5 | 3 | 3 | 3
ERIE MATERIALS INC. | S | 13-0267 | 2014-11-03 | N/A | 4 | N/A | N/A | 4 | 4 | 4
FILBIN PAINTING INC. | S | 13-0267 | 2014-11-03 | 4 | 4 | 5 | 2 | 4 | N/A | 2 | Office does not communicatte; understaffed for the amount of work they bid
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2014-11-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2014-11-03 | 5 | 5 | 5 | 5 | 4 | 3 | 4
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2014-11-03 | N/A | 1 | 2 | N/A | 2 | N/A | 2 | poor management of material procurement; send the wrong materials; do not meet delivery dates; do not send full shipments; did not adhere to LCS CO policy
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 13-0267 | 2014-11-03 | 3 | 3 | 3 | 3 | 3 | 3 | 3
CFE, INC. | S | 13-0267 | 2014-11-03 | 3 | 5 | 3 | 5 | 2 | 2 | 2 | Quality issues with the roof; submittal process was poor; office is difficult to get ahold of
BUDGET FENCE INCORPORATED | S | 13-0267 | 2014-11-03 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BGI INTERIORS | S | 13-0267 | 2014-11-03 | N/A | 5 | 5 | N/A | 5 | 4 | 4 | Delivery strung out
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2014-11-03 | 5 | 5 | 5 | 5 | 2 | N/A | 3
ALPHA IRON WORKS, LLC | S | 13-0267 | 2014-11-03 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2014-11-03 | N/A | 5 | 5 | N/A | 4 | 4 | 4
ALEXANDER MITCHELL & SON | S | 13-0267 | 2014-11-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2014-11-03 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2014-11-03 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
WOODSTONE EARTH CONSTRUCTION, INC | S | 14-0281 | 2014-09-01 | 3 | 4 | 4 | 5 | 4 | 5 | 5
WM. B. MORSE - TRUSSES | S | 14-0281 | 2014-09-01 | 5 | 5 | 5 | 5 | 2 | 3 | 4 | Submittals not complete and change management process is slow and unorganized
VAN PUTTE | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 14-0281 | 2014-09-01 | 3 | 4 | 4 | 4 | N/A | 3 | 4
STILLWATER ENTERPRISES | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
NEW YORK STATE FENCE, INC | S | 14-0281 | 2014-09-01 | 4 | 5 | 5 | 5 | N/A | N/A | 4
SANITAIRE CLEANING CO., INC. | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
SECURITRONICS | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
MORSE SASH & DOOR | S | 14-0281 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCGURK ELECTRIC, INC. | S | 14-0281 | 2014-09-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MARK & DAN FRAMERS, INC | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 5 | 4 | N/A | 4
JACHLES IMPERIAL LTD | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 4 | 3 | 2 | 4 | Does not turn in submittals in a timely manner
JAG CONSTRUCTION, INC. | S | 14-0281 | 2014-09-01 | 5 | 5 | 5 | 5 | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
KRIS OAKS CONSTRUCTION | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | Would recommend for future work
GYPSUM SYSTEMS INTERIORS | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
IMPERIAL DOOR CONTROLS, INC. | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
J&R SPECIALTIES | S | 14-0281 | 2014-09-01 | 3 | 2 | 4 | 4 | 3 | 4 | 3 | Locker lead time was longer than they said it would be
GENERAL GLASS AND MIRROR COMPANY | S | 14-0281 | 2014-09-01 | 4 | 4 | 5 | 5 | 5 | 5 | 5
F.G. RAYBURN MASON CONTRACTORS, INC | S | 14-0281 | 2014-09-01 | 5 | 4 | 5 | 5 | 5 | 5 | 5
ES SYSTEMS, INC | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
BAY TILE MARBLE & TERRAZZO | S | 14-0281 | 2014-09-01 | 4 | 3 | 5 | 3 | N/A | 3 | 4
DESIGN POOL & SPA LTD. | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 5 | N/A | 3 | 4 | Difficult to work with on pre-con
WEYDMAN ELECTRIC | S | 14-0285 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0285 | 2014-10-01 | N/A | 4 | N/A | N/A | N/A | 5 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0285 | 2014-10-01 | 4 | 4 | 4 | 3 | N/A | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0285 | 2014-11-01 | 3 | 4 | 4 | 4 | 4 | N/A | 4
AJAY GLASS & MIRROR | S | 14-0285 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 2 | 3 | Paperwork side is not good
ASI SIGNAGE | S | 14-0285 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 5 | 4
BENEDETTI BUILDERS | S | 14-0285 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
CEDAR ENTERPRISES | S | 14-0285 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
CONSTRUCTION SPECIALITIES INC. | S | 14-0285 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
MAX T. DOLAND | S | 14-0285 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MGM INSULATION | S | 14-0285 | 2014-11-01 | 4 | 4 | 5 | 4 | 4 | 4 | 4
MORSE SASH & DOOR | S | 14-0285 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
PRO CARPET INC. | S | 14-0285 | 2014-11-01 | 4 | 3 | 3 | 3 | 4 | 4 | 4
SERWAY BROTHERS INC. | S | 14-0285 | 2014-11-01 | 3 | 4 | 4 | 4 | 4 | 3 | 3
SYRACUSE MOSAIC | S | 14-0285 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
VANDYKE PAINTING COMPANY | S | 14-0285 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | Contract terminated however will be back on site Monday.
WEYDMAN ELECTRIC | S | 14-0285 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0285 | 2014-11-01 | N/A | 4 | N/A | N/A | N/A | 5 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0285 | 2014-11-01 | 4 | 4 | 4 | 3 | N/A | 4 | 4
AAC CONTRACTING, INC. | S | 14-0281 | 2014-09-01 | 5 | 5 | 5 | 5 | 5 | N/A | 4
ALL COUNTY GUTTER CO., INC. | S | 14-0281 | 2014-09-01 | 4 | 3 | 4 | 4 | 4 | N/A | 3
ALLIANCE DOOR & HARDWARE | S | 14-0281 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
B&L WHOLESALE | S | 14-0281 | 2014-09-01 | 5 | 4 | 5 | N/A | 4 | 4 | 4
JACHLES IMPERIAL LTD | S | 13-0270 | 2014-09-01 | 4 | 3 | 3 | 3 | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2014-09-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
MAX T. DOLAND | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MIG BUILDING SYSTEMS | S | 13-0270 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MONTGOMERY TRUSS | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ONTARIO EXTERIORS, INC | S | 13-0270 | 2014-09-01 | 4 | 2 | 3 | 2 | 2 | 3 | 2 | Slow office; pulled manpower when there was work to be done; submitting COs for work that is in their contract
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2014-09-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0270 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PRO CARPET INC. | S | 13-0270 | 2014-09-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RADEC CORPORATION | S | 13-0270 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2014-09-01 | 4 | 3 | 3 | 4 | N/A | 3 | 3
SANITAIRE CLEANING CO., INC. | S | 13-0270 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SERWAY BROTHERS INC. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
UNICO FINISHING SYSTEMS | S | 13-0270 | 2014-09-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2014-09-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | Great performance
US CEILING CORP. | S | 13-0270 | 2014-09-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 13-0270 | 2014-09-01 | 4 | 4 | 4 | 3 | N/A | 4 | 3
WINDOW ACCENTS INC. | S | 13-0270 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL COUNTY GUTTER CO., INC. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BETLEM RESIDENTIAL | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRIDGEWATER INTERNATIONAL | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BROCCOLO TREE & LAWN CARE | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FISHER ASSOCIATES | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GARAGE DOORS UNLIMITED | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING (ROOFING) | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING (SIDING) | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMPACT PAINTING LLC | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&K CONSTRUCTION | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ONTARIO EXTERIORS, INC | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRIDE FIRE PROTECTION | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SANITAIRE CLEANING CO., INC. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW ACCENTS INC. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 13-0270 | 2014-10-01 | 3 | 4 | 4 | 5 | 4 | N/A | 4
ALL COUNTY GUTTER CO., INC. | S | 13-0270 | 2014-10-01 | 3 | 3 | 3 | 3 | N/A | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0270 | 2014-10-01 | 5 | 4 | 5 | 5 | N/A | 5 | 4
BETLEM RESIDENTIAL | S | 13-0270 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BETLEM RESIDENTIAL HEATING & AIR CONDITIONING | S | 13-0270 | 2014-10-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | Great performance
BRIDGEWATER INTERNATIONAL | S | 13-0270 | 2014-10-01 | 3 | 2 | 2 | 3 | N/A | 4 | 4 | Missed some schedule targets
BROCCOLO TREE & LAWN CARE | S | 13-0270 | 2014-10-01 | 4 | 2 | 3 | 3 | N/A | 3 | 4 | Did not manage out-sourced work well
CATENARY CONSTRUCTION CORP. | S | 13-0270 | 2014-10-01 | 4 | 5 | 5 | 5 | 4 | 4 | 4
FISHER ASSOCIATES | S | 13-0270 | 2014-10-01 | 4 | 4 | 3 | 4 | N/A | N/A | 3 | They replaced worker that was creating errors
GARAGE DOORS UNLIMITED | S | 13-0270 | 2014-10-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 13-0270 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING (ROOFING) | S | 13-0270 | 2014-10-01 | 1 | 4 | 4 | 4 | N/A | 4 | 4 | Had a life threatening violation in the past month
HENRY ISAACS HOME REMODELING (SIDING) | S | 13-0270 | 2014-10-01 | 1 | 4 | 4 | 4 | 4 | N/A | 4 | Had a life threatening violation in the past month
IMPACT PAINTING LLC | S | 13-0270 | 2014-10-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
J&K CONSTRUCTION | S | 13-0270 | 2014-10-01 | 3 | 5 | 4 | 5 | N/A | 4 | 5
J&R SPECIALTIES | S | 13-0270 | 2014-10-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
JACHLES IMPERIAL LTD | S | 13-0270 | 2014-10-01 | 4 | 3 | 3 | 3 | N/A | 4 | 4
KENNEDY MECHANICAL P & H INC. | S | 13-0270 | 2014-10-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | Slow submittal process
MAX T. DOLAND | S | 13-0270 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MIG BUILDING SYSTEMS | S | 13-0270 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MONTGOMERY TRUSS | S | 13-0270 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NORANDEX BUILDING MATERIALS | S | 13-0270 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
ONTARIO EXTERIORS, INC | S | 13-0270 | 2014-10-01 | 3 | 2 | 3 | 2 | 2 | 3 | 2 | Slow office; pulled manpower when there was work to be done; submitting COs for work that is in their contract
POOLER ENTERPIRSES, INC. | S | 13-0270 | 2014-10-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3
PRIDE FIRE PROTECTION | S | 13-0270 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
PRO CARPET INC. | S | 13-0270 | 2014-10-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
RADEC CORPORATION | S | 13-0270 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ROCHESTER FLOORING RESOURCE | S | 13-0270 | 2014-10-01 | 4 | 3 | 3 | 4 | N/A | 3 | 3
SANITAIRE CLEANING CO., INC. | S | 13-0270 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SERWAY BROTHERS INC. | S | 13-0270 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
UNICO FINISHING SYSTEMS | S | 13-0270 | 2014-10-01 | 3 | 4 | 4 | 4 | N/A | 4 | 4
UPSTATE ROOFING & PAINTING, INC. | S | 13-0270 | 2014-10-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4 | Great performance
US CEILING CORP. | S | 13-0270 | 2014-10-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 13-0270 | 2014-10-01 | 4 | 4 | 4 | 3 | N/A | 4 | 3
WINDOW ACCENTS INC. | S | 13-0270 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 13-0270 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
CAYUGA LANDSCAPE | S | 14-0289 | 2014-09-01 | 3 | 4 | N/A | 4 | 4 | 3 | 4
GERHARZ EQUIPMENT | S | 14-0289 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRS COMPANIES | S | 14-0289 | 2014-09-01 | 3 | 3 | 4 | 2 | 3 | 2 | 2 | Does not provide sufficient manpower- owner and PM are manning the project; poor submittal process
MCPHERSON BUILDERS | S | 14-0289 | 2014-09-01 | 4 | 4 | 3 | 3 | 3 | 3 | 3
MOD SPACE | S | 14-0289 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLEASANT VALLEY ELEC. | S | 14-0289 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PREMIER UTILITY SVC. | S | 14-0289 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TG MILLER | S | 14-0289 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
THE BRAIN DRAIN | S | 14-0289 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2014-09-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
CAYUGA LANDSCAPE | S | 14-0289 | 2014-10-01 | 3 | 4 | N/A | 4 | 4 | 2 | 4 | Submittals were late
GERHARZ EQUIPMENT | S | 14-0289 | 2014-10-01 | N/A | N/A | N/A | N/A | 4 | N/A | N/A
LRS COMPANIES | S | 14-0289 | 2014-10-01 | 3 | 2 | 4 | 2 | 3 | 2 | 2 | Does not provide sufficient manpower- owner and PM are manning the project; poor submittal process
MCPHERSON BUILDERS | S | 14-0289 | 2014-10-01 | 3 | 2 | 3 | 2 | 3 | 3 | 3 | Not meeting schedule targets
MOD SPACE | S | 14-0289 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLEASANT VALLEY ELEC. | S | 14-0289 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PREMIER UTILITY SVC. | S | 14-0289 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TG MILLER | S | 14-0289 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Layout only
THE BRAIN DRAIN | S | 14-0289 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | 2 | Unresponsive office
WHITMORE FENCE | S | 14-0289 | 2014-10-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
A.W. THERRIEN CO.,INC. | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AP DAILEY CUSTOM LAMINATING CORP. | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BLDRS INSTALLED PROD. | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOSTON SHOWCASE COMPANY | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOUCHER ACOUSTIC CONTRACTOR INC. | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUILDERS INSTALLED PRODUCTS | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CADIEUX FLOORING | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAPRIOLI PAINTING | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONVENANT FIRE PROTECTION | S | 14-0288 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DANIELS ELECTRIC CORPORATION | S | 14-0288 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DENRON PLUMBING AND HVAC, LLC | S | 14-0288 | 2014-09-01 | 5 | 4 | 4 | 4 | 4 | 3 | 4
DOOR CONTROL INC. | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENVIROVANTAGE INC. | S | 14-0288 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
GRANITE STATE SPECIALTIES | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JAMES VERRA ASSOC. | S | 14-0288 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MALTHOUSE CONSTRUCTION | S | 14-0288 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MAX T. DOLAND | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
METRO WALLS | S | 14-0288 | 2014-09-01 | 3 | 4 | 4 | 4 | 4 | 4 | 3
MIDDLETON BLDG SPLY | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MORSE SASH & DOOR | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NH PLATE GLASS CORP. | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NOVEL IRON WORKS | S | 14-0288 | 2014-09-01 | 4 | 4 | N/A | N/A | 3 | 4 | 3
PARADIGM WINDOWS | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PELMAC INDUSTRIES | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PISCATAQUA LANDSCAPING | S | 14-0288 | 2014-09-01 | 3 | 4 | 3 | 4 | 4 | 4 | 4
SCOTT LAWSON GROUP | S | 14-0288 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SEVERINO TRUCKING CO, INC. | S | 14-0288 | 2014-09-01 | 4 | 3 | 4 | 3 | 4 | 4 | 4
SOUTHERN NH POURED CONCRETE CONSTRUCTION INC. | S | 14-0288 | 2014-09-01 | 4 | 4 | 4 | 4 | 3 | 4 | 3
A.W. THERRIEN CO.,INC. | S | 14-0288 | 2014-10-01 | 3 | 3 | 4 | 4 | 4 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 14-0288 | 2014-10-01 | N/A | 3 | 4 | 4 | 4 | 4 | 3 | Material Supplier
AP DAILEY CUSTOM LAMINATING CORP. | S | 14-0288 | 2014-10-01 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | Disconnect in their office between fabricator and the field staff- this led to issues with getting material per time frame promised
BLDRS INSTALLED PROD. | S | 14-0288 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOSTON SHOWCASE COMPANY | S | 14-0288 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOUCHER ACOUSTIC CONTRACTOR INC. | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BUILDERS INSTALLED PRODUCTS | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CADIEUX FLOORING | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CAPRIOLI PAINTING | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CONVENANT FIRE PROTECTION | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DANIELS ELECTRIC CORPORATION | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DENRON PLUMBING AND HVAC, LLC | S | 14-0288 | 2014-10-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
DOOR CONTROL INC. | S | 14-0288 | 2014-10-01 | 4 | 3 | 4 | 4 | 4 | 4 | 3
ENVIROVANTAGE INC. | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
GRANITE STATE SPECIALTIES | S | 14-0288 | 2014-10-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
JAMES VERRA ASSOC. | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MALTHOUSE CONSTRUCTION | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MAX T. DOLAND | S | 14-0288 | 2014-10-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
METRO WALLS | S | 14-0288 | 2014-10-01 | 3 | 4 | 4 | 4 | 4 | 4 | 3
MIDDLETON BLDG SPLY | S | 14-0288 | 2014-10-01 | N/A | 4 | 3 | 3 | 3 | 4 | 3 | Material Supplier
MORSE SASH & DOOR | S | 14-0288 | 2014-10-01 | N/A | 3 | 4 | 4 | 3 | 3 | 4 | Material Supplier
NH PLATE GLASS CORP. | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
NOVEL IRON WORKS | S | 14-0288 | 2014-10-01 | 4 | 4 | N/A | N/A | 3 | 4 | 3
PARADIGM WINDOWS | S | 14-0288 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Material Supplier
PELMAC INDUSTRIES | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PISCATAQUA LANDSCAPING | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCOTT LAWSON GROUP | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SEVERINO TRUCKING CO, INC. | S | 14-0288 | 2014-10-01 | 4 | 3 | 4 | 3 | 4 | 4 | 4
SOUTHERN NH POURED CONCRETE CONSTRUCTION INC. | S | 14-0288 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.W. THERRIEN CO.,INC. | S | 14-0288 | 2014-11-01 | 3 | 3 | 4 | 4 | 4 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 14-0288 | 2014-11-01 | N/A | 3 | 4 | 4 | 4 | 4 | 3 | Material Supplier
AP DAILEY CUSTOM LAMINATING CORP. | S | 14-0288 | 2014-11-01 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | Disconnect in their office between fabricator and the field staff- this led to issues with getting material per time frame promised
BLDRS INSTALLED PROD. | S | 14-0288 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOSTON SHOWCASE COMPANY | S | 14-0288 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOUCHER ACOUSTIC CONTRACTOR INC. | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BUILDERS INSTALLED PRODUCTS | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CADIEUX FLOORING | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CAPRIOLI PAINTING | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CONVENANT FIRE PROTECTION | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DANIELS ELECTRIC CORPORATION | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DENRON PLUMBING AND HVAC, LLC | S | 14-0288 | 2014-11-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
DOOR CONTROL INC. | S | 14-0288 | 2014-11-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
ENVIROVANTAGE INC. | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
GRANITE STATE SPECIALTIES | S | 14-0288 | 2014-11-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
JAMES VERRA ASSOC. | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MALTHOUSE CONSTRUCTION | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MAX T. DOLAND | S | 14-0288 | 2014-11-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
METRO WALLS | S | 14-0288 | 2014-11-01 | 3 | 4 | 4 | 4 | 4 | 4 | 3
MIDDLETON BLDG SPLY | S | 14-0288 | 2014-11-01 | N/A | 4 | 3 | 3 | 3 | 4 | 3 | Material Supplier
MORSE SASH & DOOR | S | 14-0288 | 2014-11-01 | N/A | 3 | 4 | 4 | 3 | 3 | 4 | Material Supplier
NH PLATE GLASS CORP. | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
NOVEL IRON WORKS | S | 14-0288 | 2014-11-01 | 4 | 4 | N/A | N/A | 3 | 4 | 3
PARADIGM WINDOWS | S | 14-0288 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Material Supplier
PELMAC INDUSTRIES | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PISCATAQUA LANDSCAPING | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCOTT LAWSON GROUP | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SEVERINO TRUCKING CO, INC. | S | 14-0288 | 2014-11-01 | 4 | 3 | 4 | 3 | 4 | 4 | 4
SOUTHERN NH POURED CONCRETE CONSTRUCTION INC. | S | 14-0288 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.D.W INC. | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACE WINDOWS | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUILDERS INSTALLED PRODUCTS | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CARE CLEAN INC | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CGM TILE & STONE, INC | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EARL B. FEINDEN | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD & THOMAS O'CONNOR INC | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GENSON OVERHEAD DOOR, INC | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IRV SCHRODER AND SONS | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KONE, INC | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRUEGLER CONTRACTING & REMODELING, LLC | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAWRENCE D. COON | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LD COON | S | 14-0291 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LECESSE PROCUREMENT LLC | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MORSE SASH & DOOR | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OCONNOR | S | 14-0291 | 2014-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PETERSON BUILDERS | S | 14-0291 | 2014-09-01 | 4 | 3 | 4 | 2 | 4 | N/A | 4
PINNACLE ROOFING INC | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RBM GUARDIAN FIRE PROTECTION INC | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RJ GRAVES CONSTRUCTION INC. | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRIPOINT STONE | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDUSEN & STEVES LAND SURVEYORS | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WESWOOD SPECIALTIES | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0291 | 2014-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D.W INC. | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACE WINDOWS | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUILDERS INSTALLED PRODUCTS | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CARE CLEAN INC | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CGM TILE & STONE, INC | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EARL B. FEINDEN | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD & THOMAS O'CONNOR INC | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GENSON OVERHEAD DOOR, INC | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IRV SCHRODER AND SONS | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KONE, INC | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRUEGLER CONTRACTING & REMODELING, LLC | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAWRENCE D. COON | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LD COON | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LECESSE PROCUREMENT LLC | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MORSE SASH & DOOR | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OCONNOR | S | 14-0291 | 2014-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PETERSON BUILDERS | S | 14-0291 | 2014-10-01 | 4 | 3 | 4 | 2 | 4 | N/A | 4
PINNACLE ROOFING INC | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RBM GUARDIAN FIRE PROTECTION INC | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RJ GRAVES CONSTRUCTION INC. | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRIPOINT STONE | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDUSEN & STEVES LAND SURVEYORS | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WESWOOD SPECIALTIES | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0291 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D.W INC. | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACE WINDOWS | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUILDERS INSTALLED PRODUCTS | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CARE CLEAN INC | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CGM TILE & STONE, INC | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EARL B. FEINDEN | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD & THOMAS O'CONNOR INC | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GENSON OVERHEAD DOOR, INC | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IRV SCHRODER AND SONS | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KONE, INC | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRUEGLER CONTRACTING & REMODELING, LLC | S | 14-0291 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LAWRENCE D. COON | S | 14-0291 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LD COON | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LECESSE PROCUREMENT LLC | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MORSE SASH & DOOR | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OCONNOR | S | 14-0291 | 2014-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PETERSON BUILDERS | S | 14-0291 | 2014-11-01 | 4 | 3 | 4 | 2 | 4 | N/A | 4
PINNACLE ROOFING INC | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RBM GUARDIAN FIRE PROTECTION INC | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RJ GRAVES CONSTRUCTION INC. | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRIPOINT STONE | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDUSEN & STEVES LAND SURVEYORS | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WESWOOD SPECIALTIES | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0291 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 14-0296 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SEASONS GENERAL | S | 14-0296 | 2014-12-31 | 3 | 2 | 1 | 3 | 2 | 1 | 2 | Would not recommend hiring this sub again
ARCHER EXTERIORS | S | 14-0296 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BLUE RIDGE LUMBER COMPANY | S | 14-0296 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BYRNES ELECTRIC | S | 14-0296 | 2014-12-31 | 4 | 4 | 4 | 4 | 5 | 5 | 5
CUSTOM STEEL CONTRACTORS | S | 14-0296 | 2014-12-31 | 4 | 3 | 3 | 4 | N/A | 3 | 4
DUKES LANDSCAPE MANAGEMENT | S | 14-0296 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0296 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 14-0296 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNON SURVEY SERVICES | S | 14-0296 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LOWTHERS CONTRACTING | S | 14-0296 | 2014-12-31 | 2 | 1 | 3 | 2 | N/A | 4 | 4 | Completely underachieved on this project
PENTEL DRYWALL | S | 14-0296 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RED LION INSULATION | S | 14-0296 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RJK FLOOR COVERING | S | 14-0296 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S Y R MECHANICAL | S | 14-0296 | 2014-12-31 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | Only faxes, does not use e-mail
SPEICHER EXCAVATING | S | 14-0296 | 2014-12-31 | 4 | 3 | 4 | 4 | 4 | 3 | 4
UNICO FINISHING SYSTEMS | S | 14-0296 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WIRES ELECTRICAL SHOP | S | 14-0296 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ORVILLES APPLIANCE, INC. | S | 14-0292 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 4
MCGURK ELECTRIC, INC. | S | 14-0292 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 4
KENNEDY MECHANICAL | S | 14-0292 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 4
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0292 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 4
JACHLES IMPERIAL LTD | S | 14-0292 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 4
FINGER LAKES PTG. | S | 14-0292 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 4
AAC CONTRACTING, INC. | S | 14-0292 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 4
STILLWATER ENTERPRISES | S | 14-0292 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 4
VP SUPPLY | S | 14-0292 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 4
WHIRLPOOL CORPORATION | S | 14-0292 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0285 | 2014-12-31 | 3 | 4 | 4 | 4 | 4 | N/A | 4
AJAY GLASS & MIRROR | S | 14-0285 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 2 | 3 | Paperwork side is not good
ASI SIGNAGE | S | 14-0285 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 5 | 4
BENEDETTI BUILDERS | S | 14-0285 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | N/A | 4
CEDAR ENTERPRISES | S | 14-0285 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 4 | 4
CONSTRUCTION SPECIALITIES INC. | S | 14-0285 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
MAX T. DOLAND | S | 14-0285 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MGM INSULATION | S | 14-0285 | 2014-12-31 | 4 | 4 | 5 | 4 | 4 | 4 | 4
MORSE SASH & DOOR | S | 14-0285 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 4 | 4
PRO CARPET INC. | S | 14-0285 | 2014-12-31 | 4 | 3 | 3 | 3 | 4 | 4 | 4
SERWAY BROTHERS INC. | S | 14-0285 | 2014-12-31 | 3 | 4 | 4 | 4 | 4 | 3 | 3
SYRACUSE MOSAIC | S | 14-0285 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 4 | 4
VANDYKE PAINTING COMPANY | S | 14-0285 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | Contract terminated however will be back on site Monday.
WEYDMAN ELECTRIC | S | 14-0285 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0285 | 2014-12-31 | N/A | 4 | N/A | N/A | N/A | 5 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0285 | 2014-12-31 | 4 | 4 | 4 | 3 | N/A | 4 | 4
ACQUATIC LANDSCAPING | S | 13-0276 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | took their scores off until they get back on site
FIRE PAK | S | 13-0276 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
GOMEZ & SONS | S | 13-0276 | 2014-12-31 | 5 | 5 | 4 | 4 | 4 | N/A | N/A | No longer on site
MEISNER | S | 13-0276 | 2014-12-31 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
OHL | S | 13-0276 | 2014-12-31 | 3 | 1 | 2 | 1 | 2 | 2 | N/A | Has a hard time following a schedule including their own.
PARAMOUNT | S | 13-0276 | 2014-12-31 | 4 | 4 | N/A | 3 | 4 | 4 | N/A
SOLUTIONS | S | 13-0276 | 2014-12-31 | 4 | 3 | 3 | 4 | 4 | 4 | N/A | Sub has a hard time following a schedule- there has been an improvement in schedule management
SOUTHERN COAST ROOFING | S | 13-0276 | 2014-12-31 | 4 | 4 | 4 | 4 | 3 | 3 | N/A
SPI | S | 13-0276 | 2014-12-31 | 4 | 4 | 3 | 4 | 3 | 3 | N/A
STATE LINE PRODUCTS | S | 13-0276 | 2014-12-31 | 5 | 5 | 5 | 5 | N/A | 3 | N/A
STEEL FAB | S | 13-0276 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
TROPIC | S | 13-0276 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | 3 | N/A
WILDCAT | S | 13-0276 | 2014-12-31 | 3 | 1 | 2 | 2 | N/A | N/A | N/A | Wildcat waited too long to staff up. Would not use this sub again.
Y&T | S | 13-0276 | 2014-12-31 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
ARCI, LTD. | S | 13-0273 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 13-0273 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BARFIELD FENCE & WALL | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BARFIELD FENCE Y FABRICATION | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 3 | 3
BERGERON FRAMING | S | 13-0273 | 2014-12-31 | 3 | 4 | 4 | 4 | N/A | 3 | 4
BERGERON FRAMING - MATERIALS | S | 13-0273 | 2014-12-31 | N/A | 4 | 3 | N/A | N/A | 3 | 3
BERMAN PROPERTY MAINTENANCE Y CONSTRUCTION | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRANT & SON | S | 13-0273 | 2014-12-31 | 3 | 3 | 4 | 4 | N/A | 3 | N/A
CABLE ELECTRICAL SERVICES | S | 13-0273 | 2014-12-31 | 3 | 4 | 4 | 4 | 4 | 3 | 3
CENTRAL FLORIDA SAFETY | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DELACRUZ DRYWALL PLASTERING | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 2 | 1 | This contractor has been put on notice several times to submit contract and they have not
DRMP INC | S | 13-0273 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 2 | this sub has a new scheduler and this will hopefully help with the scheduling issues.
EAST COAST POURED FLOORS | S | 13-0273 | 2014-12-31 | 2 | 4 | 3 | 4 | N/A | 4 | 3
EVOLUTION POOLS & CONSTRUCTION SERVICES, INC. | S | 13-0273 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLORIDA DOOR SOLUTIONS | S | 13-0273 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 3 | 4
FOX WINDOWS | S | 13-0273 | 2014-12-31 | 4 | 4 | 3 | 4 | N/A | 3 | 3
G&L EXTERIORS | S | 13-0273 | 2014-12-31 | 3 | 4 | 4 | 4 | N/A | 3 | 3
GULF COAST PLUMBING | S | 13-0273 | 2014-12-31 | 4 | 5 | 4 | 4 | 5 | 5 | 4
HAVEN CONTRACTING, INC | S | 13-0273 | 2014-12-31 | 3 | 4 | 4 | 3 | 4 | 3 | 3 | field workers are very good
JEL SITE DEVELOPMENT INC. | S | 13-0273 | 2014-12-31 | 4 | 3 | 4 | 3 | 2 | 4 | 3 | Small operation, apparently capable of doing this but were perform well so far
JL WILSON CONCRETE, INC. | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 3 | 4
KISSIMMEE CONSTRUCTION | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MALIBU FLOORS | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 3 | 3
MASSEY SERVICES | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MASTER WOOD CRAFT CABINETRY | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | 4 | 3 | 3
PRECISION GUTTERS | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 3 | 3
REW LANDSCAPE | S | 13-0273 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SHADES TO YOU | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 4 | 3
SIMPSON ENVIRONMENTAL | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUSA CABINETS | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STONE INSTALLATION | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUNBELT GATED ACCESS SYSTEMS | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE LUCKHARDT GROUP | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0273 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | 3 | 4
TRUSSWAY MFG. | S | 13-0273 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNICORN PAINTING INC. | S | 13-0273 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNIVERSAL BUILDING SUPPLY | S | 13-0273 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNIVERSAL ENGINEERING SCIENCES | S | 13-0273 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | N/A | 4
VALUE LIGHTING | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | 4 | 3 | 4
WALL AND SIGN CONCEPTS | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WATERWATCH CORPORATION | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WAYNE AUTOMATIC SPRINKLERS | S | 13-0273 | 2014-12-31 | 4 | 5 | 4 | 3 | N/A | 3 | 4
WHIRLPOOL CORPORATION | S | 13-0273 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAYUGA LANDSCAPE | S | 14-0289 | 2014-12-31 | 3 | 4 | N/A | 4 | 4 | 2 | 4 | Submittals were late
GERHARZ EQUIPMENT | S | 14-0289 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRS COMPANIES | S | 14-0289 | 2014-12-31 | 3 | 2 | 4 | 2 | 3 | 2 | 2 | Does not provide sufficient manpower- owner and PM are manning the project; poor submittal process
MCPHERSON BUILDERS | S | 14-0289 | 2014-12-31 | 3 | 2 | 3 | 2 | 3 | 3 | 3 | Not meeting schedule targets
MOD SPACE | S | 14-0289 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLEASANT VALLEY ELEC. | S | 14-0289 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PREMIER UTILITY SVC. | S | 14-0289 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TG MILLER | S | 14-0289 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Layout only
THE BRAIN DRAIN | S | 14-0289 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | 2 | Unresponsive office
WHITMORE FENCE | S | 14-0289 | 2014-12-31 | 4 | 3 | 4 | 4 | 4 | 4 | 4
A.W. THERRIEN CO.,INC. | S | 14-0288 | 2014-12-31 | 3 | 3 | 4 | 4 | 4 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 14-0288 | 2014-12-31 | N/A | 3 | 4 | 4 | 4 | 4 | 3 | Material Supplier
AP DAILEY CUSTOM LAMINATING CORP. | S | 14-0288 | 2014-12-31 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | Disconnect in their office between fabricator and the field staff- this led to issues with getting material per time frame promised
BLDRS INSTALLED PROD. | S | 14-0288 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOSTON SHOWCASE COMPANY | S | 14-0288 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOUCHER ACOUSTIC CONTRACTOR INC. | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BUILDERS INSTALLED PRODUCTS | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CADIEUX FLOORING | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CAPRIOLI PAINTING | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CONVENANT FIRE PROTECTION | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DANIELS ELECTRIC CORPORATION | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DENRON PLUMBING AND HVAC, LLC | S | 14-0288 | 2014-12-31 | 5 | 4 | 4 | 4 | 4 | 4 | 4
DOOR CONTROL INC. | S | 14-0288 | 2014-12-31 | 4 | 3 | 4 | 4 | 4 | 4 | 3
ENVIROVANTAGE INC. | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
GRANITE STATE SPECIALTIES | S | 14-0288 | 2014-12-31 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
JAMES VERRA ASSOC. | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MALTHOUSE CONSTRUCTION | S | 14-0288 | 2014-12-31 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MAX T. DOLAND | S | 14-0288 | 2014-12-31 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
METRO WALLS | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MIDDLETON BLDG SPLY | S | 14-0288 | 2014-12-31 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
MORSE SASH & DOOR | S | 14-0288 | 2014-12-31 | N/A | 3 | 4 | 4 | 3 | 3 | 4 | Material Supplier
NH PLATE GLASS CORP. | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
NOVEL IRON WORKS | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PARADIGM WINDOWS | S | 14-0288 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Material Supplier
PELMAC INDUSTRIES | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PISCATAQUA LANDSCAPING | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCOTT LAWSON GROUP | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SEVERINO TRUCKING CO, INC. | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 3 | 4 | 4 | 4
SOUTHERN NH POURED CONCRETE CONSTRUCTION INC. | S | 14-0288 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.D.W INC. | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACE WINDOWS | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUILDERS INSTALLED PRODUCTS | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CARE CLEAN INC | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CGM TILE & STONE, INC | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES DRISCOLL | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EARL B. FEINDEN | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD & THOMAS O'CONNOR INC | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GENSON OVERHEAD DOOR, INC | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IRV SCHRODER AND SONS | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KONE, INC | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRUEGLER CONTRACTING & REMODELING, LLC | S | 14-0291 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LAWRENCE D. COON | S | 14-0291 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LD COON | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LECESSE PROCUREMENT LLC | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MORSE SASH & DOOR | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OCONNOR | S | 14-0291 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PETERSON BUILDERS | S | 14-0291 | 2014-12-31 | 4 | 3 | 4 | 2 | 4 | N/A | 4
PINNACLE ROOFING INC | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RBM GUARDIAN FIRE PROTECTION INC | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RJ GRAVES CONSTRUCTION INC. | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRIPOINT STONE | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VANDUSEN & STEVES LAND SURVEYORS | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WESWOOD SPECIALTIES | S | 14-0291 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0291 | 2014-12-31 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2014-12-31 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2014-12-31 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ALEXANDER MITCHELL & SON | S | 13-0267 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2014-12-31 | N/A | 5 | 5 | N/A | 4 | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0267 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2014-12-31 | 5 | 5 | 5 | 5 | 2 | N/A | 3
BGI INTERIORS | S | 13-0267 | 2014-12-31 | N/A | 5 | 5 | N/A | 5 | 4 | 4 | Delivery strung out
BUDGET FENCE INCORPORATED | S | 13-0267 | 2014-12-31 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CFE, INC. | S | 13-0267 | 2014-12-31 | 3 | 5 | 3 | 5 | 2 | 2 | 2 | Quality issues with the roof; submittal process was poor; office is difficult to get ahold of
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 13-0267 | 2014-12-31 | 3 | 3 | 3 | 3 | 3 | 3 | 3
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2014-12-31 | N/A | 1 | 2 | N/A | 2 | N/A | 2 | poor management of material procurement; send the wrong materials; do not meet delivery dates; do not send full shipments; did not adhere to LCS CO policy
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2014-12-31 | 5 | 5 | 5 | 5 | 4 | 3 | 4
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ERIE MATERIALS INC. | S | 13-0267 | 2014-12-31 | N/A | 4 | N/A | N/A | 4 | 4 | 4
FILBIN PAINTING INC. | S | 13-0267 | 2014-12-31 | 4 | 4 | 5 | 2 | 4 | N/A | 2 | Office does not communicatte; understaffed for the amount of work they bid
GORICK CONSTRUCTION | S | 13-0267 | 2014-12-31 | 1 | 4 | 4 | 5 | 3 | 3 | 3
HOMER C GOW & SONS | S | 13-0267 | 2014-12-31 | 4 | 5 | 5 | 5 | 3 | N/A | 3
J&R SPECIALTIES | S | 13-0267 | 2014-12-31 | 4 | 3 | 4 | 3 | 4 | 4 | 3
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2014-12-31 | 3 | 5 | 5 | 5 | 3 | N/A | 3
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2014-12-31 | 3 | 4 | 4 | 4 | N/A | N/A | 4
L.A.PAINTING, INC. | S | 13-0267 | 2014-12-31 | 3 | 2 | 3 | 4 | 2 | 4 | 2 | Not concerend about quality of finished product; Unresponsive
MATCO ELECTRIC | S | 13-0267 | 2014-12-31 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | solid
MESKO GLASS CO. | S | 13-0267 | 2014-12-31 | 3 | 1 | 3 | 3 | 4 | 4 | 4 | Difficult to get ahold of and manage
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHERN SPACES INC. | S | 13-0267 | 2014-12-31 | 3 | 3 | 4 | 4 | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 13-0267 | 2014-12-31 | 4 | 4 | 4 | 4 | N/A | 5 | N/A
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2014-12-31 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | Very difficult to work with; Need to descope well
RED HAWK FIRE & SECURITY | S | 13-0267 | 2014-12-31 | 4 | 4 | 4 | 4 | 3 | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2014-12-31 | 3 | 3 | 5 | 3 | 3 | 3 | 2 | Difficult to schedule during school- Work in summer. Work is not done when expected.
SCHINDLER ELEVATOR | S | 13-0267 | 2014-12-31 | 4 | 4 | 3 | 4 | 4 | 4 | 3 | Having trouble getting them onsite to repair a dented door
SIMPLEXGRINNELL LP | S | 13-0267 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2014-12-31 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | good
SURE TEMP COMPANY INC. | S | 13-0267 | 2014-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2014-12-31 | 4 | 3 | 4 | 4 | 3 | 3 | 3
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2014-12-31 | 4 | 4 | 5 | 4 | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2014-12-31 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company, would recommend
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2014-12-31 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2014-12-31 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | office is too busy
AIIA CONSTRUCTION COMPANY, INC | S | 14-0285 | 2015-01-20 | 3 | 4 | 4 | 4 | 4 | N/A | 4
AJAY GLASS & MIRROR | S | 14-0285 | 2015-01-20 | 4 | 4 | 4 | 4 | N/A | 2 | 3 | Paperwork side is not good
ASI SIGNAGE | S | 14-0285 | 2015-01-20 | N/A | N/A | N/A | N/A | N/A | 5 | 4
BENEDETTI BUILDERS | S | 14-0285 | 2015-01-20 | 4 | 4 | 4 | 4 | 4 | N/A | 4
CEDAR ENTERPRISES | S | 14-0285 | 2015-01-20 | N/A | N/A | N/A | N/A | N/A | 4 | 4
COMMERCIAL Y RESIDENTIAL PAINTING | S | 14-0285 | 2015-01-20 | 4 | 4 | 4 | 3 | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 14-0285 | 2015-01-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
MAX T. DOLAND | S | 14-0285 | 2015-01-20 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MGM INSULATION | S | 14-0285 | 2015-01-20 | 4 | 4 | 5 | 4 | 4 | 4 | 4
MORSE SASH & DOOR | S | 14-0285 | 2015-01-20 | N/A | N/A | N/A | N/A | N/A | 4 | 4
PRO CARPET INC. | S | 14-0285 | 2015-01-20 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SANITAIRE CLEANING CO., INC. | S | 14-0285 | 2015-01-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0285 | 2015-01-20 | 3 | 4 | 4 | 4 | 4 | 3 | 3
SYRACUSE MOSAIC | S | 14-0285 | 2015-01-20 | N/A | N/A | N/A | N/A | N/A | 4 | 4
VANDYKE PAINTING COMPANY | S | 14-0285 | 2015-01-20 | 4 | 2 | 4 | 2 | 4 | 3 | 4 | Contract terminated however will be back on site Monday.
WEYDMAN ELECTRIC | S | 14-0285 | 2015-01-20 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0285 | 2015-01-20 | N/A | 4 | N/A | N/A | N/A | 5 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0285 | 2015-01-20 | 4 | 4 | 4 | 4 | N/A | 4 | 4
A.D.W INC. | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAA QUALITY MAINTAINENCE | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SEASONS GENERAL | S | 14-0296 | 2015-01-01 | 3 | 2 | 1 | 3 | 2 | 1 | 2 | Would not recommend hiring this sub again
ARCHER EXTERIORS | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BLUE RIDGE LUMBER COMPANY | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BYRNES ELECTRIC | S | 14-0296 | 2015-01-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
CUSTOM STEEL CONTRACTORS | S | 14-0296 | 2015-01-01 | 4 | 3 | 3 | 4 | N/A | 4 | 4
DUKES LANDSCAPE MANAGEMENT | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GE APPLIANCES | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNON SURVEY SERVICES | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHL BUILDING PRODUCTS | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LODI WELDING COMPANY | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LOWTHERS CONTRACTING | S | 14-0296 | 2015-01-01 | 2 | 1 | 3 | 2 | N/A | 4 | 4 | Completely underachieved on this project
PENTEL DRYWALL | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER GRANITE AND MARBLE | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RED LION INSULATION | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RJK FLOOR COVERING | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S Y R MECHANICAL | S | 14-0296 | 2015-01-01 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | Only faxes, does not use e-mail
SLIWINSKI FLOORING COVERING | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPEICHER EXCAVATING | S | 14-0296 | 2015-01-01 | 4 | 3 | 4 | 4 | 4 | 3 | 4
UNICO FINISHING SYSTEMS | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WIRES ELECTRICAL SHOP | S | 14-0296 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 14-0296 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 14-0292 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
FINGER LAKES PTG. | S | 14-0292 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
JACHLES IMPERIAL LTD | S | 14-0292 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0292 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
KENNEDY MECHANICAL | S | 14-0292 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
MCGURK ELECTRIC, INC. | S | 14-0292 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
ORVILLES APPLIANCE, INC. | S | 14-0292 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
STILLWATER ENTERPRISES | S | 14-0292 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
VP SUPPLY | S | 14-0292 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
WHIRLPOOL CORPORATION | S | 14-0292 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0285 | 2015-02-18 | 3 | 4 | 4 | 4 | 4 | N/A | 4
AJAY GLASS & MIRROR | S | 14-0285 | 2015-02-18 | 4 | 4 | 4 | 4 | 4 | 2 | 3 | Paperwork side is not good
ASI SIGNAGE | S | 14-0285 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | 5 | 4
BENEDETTI BUILDERS | S | 14-0285 | 2015-02-18 | 4 | 4 | 4 | 4 | 4 | N/A | 4
CEDAR ENTERPRISES | S | 14-0285 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | 4 | 4
COMMERCIAL Y RESIDENTIAL PAINTING | S | 14-0285 | 2015-02-18 | 4 | 4 | 4 | 3 | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 14-0285 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
MAX T. DOLAND | S | 14-0285 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MGM INSULATION | S | 14-0285 | 2015-02-18 | 4 | 4 | 5 | 4 | 4 | 4 | 4
MORSE SASH & DOOR | S | 14-0285 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | 4 | 4
PRO CARPET INC. | S | 14-0285 | 2015-02-18 | 4 | 4 | 4 | 3 | 4 | 4 | 4
SANITAIRE CLEANING CO., INC. | S | 14-0285 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0285 | 2015-02-18 | 3 | 4 | 4 | 4 | 3 | 3 | 3
SYRACUSE MOSAIC | S | 14-0285 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
VANDYKE PAINTING COMPANY | S | 14-0285 | 2015-02-18 | 3 | 2 | 4 | 2 | 3 | 3 | 4 | Contract terminated however will be back on site Monday.
WEYDMAN ELECTRIC | S | 14-0285 | 2015-02-18 | 3 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0285 | 2015-02-18 | N/A | 4 | N/A | N/A | N/A | 5 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0285 | 2015-02-18 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.M. STERN, INC. | S | 14-0284 | 2015-02-18 | 4 | 5 | 4 | 4 | 4 | 4 | 4
ABJ FIRE PROTECTION CO. | S | 14-0284 | 2015-02-18 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIRSIDE TECHNOLOGY CORP. | S | 14-0284 | 2015-02-18 | 4 | 5 | 4 | 4 | 3 | 4 | 3
ALEXANDER MITCHELL & SON | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0284 | 2015-02-18 | 4 | 4 | 4 | 4 | 2 | 2 | 3 | Not proactive
DESIGN SPECIALISTS INC. | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 14-0284 | 2015-02-18 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | Do not arrive on site per promised dates
E J CONSTRUCTION | S | 14-0284 | 2015-02-18 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | 4 | 4
GRANDPAS NURSERY Y GARDENS | S | 14-0284 | 2015-02-18 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | 4 | 4
JHP INDUSTRIAL SUPPLY | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | N/A | 2 | Totally unresponsive. Complete Negligance.
KAPPER LANDSCAPING INC. | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | completely unresponsive. Supposed to provide WBE and this is in their contract and they have yet to deliver on this.
LEMOYNE INTERIORS, INC. | S | 14-0284 | 2015-02-18 | 5 | 5 | 5 | 5 | 4 | 4 | 4
MAC CONSTRUCTION CORP. | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NEW YORK STATE FENCE, INC | S | 14-0284 | 2015-02-18 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PARKITECTS | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | 5 | 5 | 5
PRO CARPET INC. | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | 4 | 4 | 4
RAULLI Y SONS, INC. | S | 14-0284 | 2015-02-18 | 3 | 4 | 4 | 4 | 4 | 4 | 3
SCHINDLER ELEVATOR | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | 4 | 4 | 2
US CEILING CORP. | S | 14-0284 | 2015-02-18 | 4 | 4 | 4 | 4 | N/A | 4 | 4
WOOD ETC., INC. | S | 14-0284 | 2015-02-18 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0284 | 2015-02-18 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAYUGA LANDSCAPE | S | 14-0289 | 2015-01-01 | 3 | 4 | N/A | 4 | 4 | 2 | 4 | Submittals were late
COMFORT SYSTEMS (SYRACUSE) | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GERHARZ EQUIPMENT | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOHN C. LOWERY | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLY BROS. | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRS COMPANIES | S | 14-0289 | 2015-01-01 | 3 | 2 | 4 | 2 | 3 | 2 | 2 | Does not provide sufficient manpower- owner and PM are manning the project; poor submittal process
MCPHERSON BUILDERS | S | 14-0289 | 2015-01-01 | 3 | 2 | 3 | 2 | 3 | 3 | 3 | Not meeting schedule targets
MOD SPACE | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL LUMBER | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLEASANT VALLEY ELEC. | S | 14-0289 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PREMIER UTILITY SVC. | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TG MILLER | S | 14-0289 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Layout only
THE BRAIN DRAIN | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | 2 | Unresponsive office
UPSTATE ROOFING & PAINTING, INC. | S | 14-0289 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2015-01-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
A.W. THERRIEN CO.,INC. | S | 14-0288 | 2015-01-01 | 3 | 3 | 4 | 4 | 4 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 14-0288 | 2015-01-01 | N/A | 3 | 4 | 4 | 4 | 4 | 3 | Material Supplier
AP DAILEY CUSTOM LAMINATING CORP. | S | 14-0288 | 2015-01-01 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | Disconnect in their office between fabricator and the field staff- this led to issues with getting material per time frame promised
BLDRS INSTALLED PROD. | S | 14-0288 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOSTON SHOWCASE COMPANY | S | 14-0288 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOUCHER ACOUSTIC CONTRACTOR INC. | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BUILDERS INSTALLED PRODUCTS | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CADIEUX FLOORING | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CAPRIOLI PAINTING | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CONVENANT FIRE PROTECTION | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DANIELS ELECTRIC CORPORATION | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DENRON PLUMBING AND HVAC, LLC | S | 14-0288 | 2015-01-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
DOOR CONTROL INC. | S | 14-0288 | 2015-01-01 | 4 | 3 | 4 | 4 | 4 | 4 | 3
ENVIROVANTAGE INC. | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
GRANITE STATE SPECIALTIES | S | 14-0288 | 2015-01-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
JAMES VERRA ASSOC. | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MALTHOUSE CONSTRUCTION | S | 14-0288 | 2015-01-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MAX T. DOLAND | S | 14-0288 | 2015-01-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
METRO WALLS | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MIDDLETON BLDG SPLY | S | 14-0288 | 2015-01-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
MORSE SASH & DOOR | S | 14-0288 | 2015-01-01 | N/A | 4 | 4 | 4 | 3 | 3 | 4 | Material Supplier
NH PLATE GLASS CORP. | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
NOVEL IRON WORKS | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PARADIGM WINDOWS | S | 14-0288 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Material Supplier
PELMAC INDUSTRIES | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PISCATAQUA LANDSCAPING | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCOTT LAWSON GROUP | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SEVERINO TRUCKING CO, INC. | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SOUTHERN NH POURED CONCRETE CONSTRUCTION INC. | S | 14-0288 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.D.W INC. | S | 14-0296 | 2015-02-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
AAA QUALITY MAINTAINENCE | S | 14-0296 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0296 | 2015-02-01 | 3 | 4 | 3 | 4 | 3 | N/A | 3
ALL SEASONS GENERAL | S | 14-0296 | 2015-02-01 | 3 | 2 | 1 | 3 | 2 | 1 | 2 | Would not recommend hiring this sub again
ARCHER EXTERIORS | S | 14-0296 | 2015-02-01 | 1 | 3 | 2 | 3 | 4 | 3 | 3
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0296 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
BLUE RIDGE LUMBER COMPANY | S | 14-0296 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier only
BYRNES ELECTRIC | S | 14-0296 | 2015-02-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
CUSTOM STEEL CONTRACTORS | S | 14-0296 | 2015-02-01 | 4 | 3 | 3 | 4 | N/A | 4 | 4
DUKES LANDSCAPE MANAGEMENT | S | 14-0296 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
FLOWER CITY GLASS | S | 14-0296 | 2015-02-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
GE APPLIANCES | S | 14-0296 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
HOWARD BURD & SONS | S | 14-0296 | 2015-02-01 | 2 | 2 | 5 | 3 | 3 | N/A | 2 | currently developing relationship
J&R SPECIALTIES | S | 14-0296 | 2015-02-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
KENNON SURVEY SERVICES | S | 14-0296 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHL BUILDING PRODUCTS | S | 14-0296 | 2015-02-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
LODI WELDING COMPANY | S | 14-0296 | 2015-02-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
LOWTHERS CONTRACTING | S | 14-0296 | 2015-02-01 | 2 | 1 | 3 | 2 | N/A | 4 | 4 | Completely underachieved on this project
MAX T. DOLAND | S | 14-0296 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PENTEL DRYWALL | S | 14-0296 | 2015-02-01 | 2 | 1 | 2 | 1 | 3 | 3 | 3 | manpower issues,
PENYAK ROOFING | S | 14-0296 | 2015-02-01 | 2 | 4 | 4 | 4 | 2 | 2 | 2 | office is lacking
PREMIER GRANITE AND MARBLE | S | 14-0296 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
RED LION INSULATION | S | 14-0296 | 2015-02-01 | 3 | 4 | 3 | 4 | 3 | 3 | 3
RJK FLOOR COVERING | S | 14-0296 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | no longer a sub, been replaced
S Y R MECHANICAL | S | 14-0296 | 2015-02-01 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | Only faxes, does not use e-mail
SLIWINSKI FLOORING COVERING | S | 14-0296 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
SPEICHER EXCAVATING | S | 14-0296 | 2015-02-01 | 4 | 3 | 4 | 4 | 4 | 3 | 4
UNICO FINISHING SYSTEMS | S | 14-0296 | 2015-02-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
WIRES ELECTRICAL SHOP | S | 14-0296 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 14-0296 | 2015-02-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
B&L WHOLESALE | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSR | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | 5
CATENARY CONSTRUCTION CORP. | S | 14-0289 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CAYUGA LANDSCAPE | S | 14-0289 | 2015-02-01 | 3 | 4 | N/A | 4 | 4 | 2 | 4
COMFORT SYSTEMS (SYRACUSE) | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D & R JONES CONSTRUCTION | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EZ WAY | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GERHARZ EQUIPMENT | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
INNOVATIVE WINDOWEAR | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOHN C. LOWERY | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLY BROS. | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRS COMPANIES | S | 14-0289 | 2015-02-01 | 2 | 2 | N/A | 4 | 2 | 4 | 2 | Safety isnt a priority for them.
MCPHERSON BUILDERS | S | 14-0289 | 2015-02-01 | 3 | 2 | 3 | 2 | 3 | 3 | 3 | Not meeting schedule targets
MOD SPACE | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | 1 | 1 | Unresponsive office
NATIONAL LUMBER | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLEASANT VALLEY ELEC. | S | 14-0289 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PREMIER UTILITY SVC. | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TG MILLER | S | 14-0289 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Layout only
THE BRAIN DRAIN | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | 2 | Unresponsive office
UPSTATE ROOFING & PAINTING, INC. | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2015-02-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
A.W. THERRIEN CO.,INC. | S | 14-0288 | 2015-02-01 | 3 | 3 | 4 | 4 | 4 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 14-0288 | 2015-02-01 | N/A | 3 | 4 | 4 | 4 | 4 | 3 | Material Supplier
AP DAILEY CUSTOM LAMINATING CORP. | S | 14-0288 | 2015-02-01 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | Disconnect in their office between fabricator and the field staff- this led to issues with getting material per time frame promised
BLDRS INSTALLED PROD. | S | 14-0288 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOSTON SHOWCASE COMPANY | S | 14-0288 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOUCHER ACOUSTIC CONTRACTOR INC. | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BUILDERS INSTALLED PRODUCTS | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CADIEUX FLOORING | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CAPRIOLI PAINTING | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CONVENANT FIRE PROTECTION | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DANIELS ELECTRIC CORPORATION | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DENRON PLUMBING AND HVAC, LLC | S | 14-0288 | 2015-02-01 | 5 | 4 | 4 | 4 | 4 | 4 | 4
DOOR CONTROL INC. | S | 14-0288 | 2015-02-01 | 4 | 3 | 4 | 4 | 4 | 4 | 3
ENVIROVANTAGE INC. | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
GRANITE STATE SPECIALTIES | S | 14-0288 | 2015-02-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
JAMES VERRA ASSOC. | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MALTHOUSE CONSTRUCTION | S | 14-0288 | 2015-02-01 | 5 | 5 | 5 | 5 | 5 | N/A | 5
MAX T. DOLAND | S | 14-0288 | 2015-02-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
METRO WALLS | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MIDDLETON BLDG SPLY | S | 14-0288 | 2015-02-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | Material Supplier
MORSE SASH & DOOR | S | 14-0288 | 2015-02-01 | N/A | 4 | 4 | 4 | 3 | 3 | 4 | Material Supplier
NH PLATE GLASS CORP. | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
NOVEL IRON WORKS | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PARADIGM WINDOWS | S | 14-0288 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Material Supplier
PELMAC INDUSTRIES | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PISCATAQUA LANDSCAPING | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCOTT LAWSON GROUP | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SEVERINO TRUCKING CO, INC. | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SOUTHERN NH POURED CONCRETE CONSTRUCTION INC. | S | 14-0288 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WILSON 5 SERVICE | S | 14-0288 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D.W INC. | S | 14-0291 | 2015-02-01 | 2 | 2 | 3 | 2 | 4 | 4 | 3 | not enough manpower; safety glasses issue
ACE WINDOWS | S | 14-0291 | 2015-02-01 | 3 | 4 | 3 | 4 | 4 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 14-0291 | 2015-02-01 | N/A | N/A | N/A | N/A | 1 | 2 | 2 | supplier; office is unresponsive - they "have no clue"
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0291 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
B&L WHOLESALE | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BAST HATFIELD CONSTRUCTION, LLC (CMU) | S | 14-0291 | 2015-02-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
BGI INTERIORS | S | 14-0291 | 2015-02-01 | N/A | 5 | 5 | N/A | 5 | 5 | 5 | supplier
BUILDERS INSTALLED PRODUCTS | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CARE CLEAN INC | S | 14-0291 | 2015-02-01 | 3 | 4 | 4 | 4 | N/A | N/A | 4
CGM TILE & STONE, INC | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CHARLES DRISCOLL | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DEMCO NEW YORK CORP. | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 3 | 4 | 4 | 4
EARL B. FEINDEN | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
EDWARD & THOMAS O'CONNOR INC | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 14-0291 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not onsite yet
GENSON OVERHEAD DOOR, INC | S | 14-0291 | 2015-02-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENDERSON-JOHNSON CO.INC. | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
IRV SCHRODER AND SONS | S | 14-0291 | 2015-02-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
KONE, INC | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
KRUEGLER CONTRACTING & REMODELING, LLC | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LAWRENCE D. COON | S | 14-0291 | 2015-02-01 | 4 | 4 | 3 | 4 | 4 | 4 | 4
LD COON | S | 14-0291 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LECESSE PROCUREMENT LLC | S | 14-0291 | 2015-02-01 | 5 | 5 | 4 | 5 | 5 | 5 | 5
MAX T. DOLAND | S | 14-0291 | 2015-02-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MORSE SASH & DOOR | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OCONNOR | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PETERSON BUILDERS | S | 14-0291 | 2015-02-01 | 4 | 3 | 4 | 2 | 4 | N/A | 4 | inconsistent crews; not enough manpower
PINNACLE ROOFING INC | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 14-0291 | 2015-02-01 | 4 | 4 | 3 | 4 | 4 | 4 | 4
RBM GUARDIAN FIRE PROTECTION INC | S | 14-0291 | 2015-02-01 | 4 | 3 | 3 | 3 | 2 | 4 | 2
RJ GRAVES CONSTRUCTION INC. | S | 14-0291 | 2015-02-01 | 5 | 5 | 4 | 5 | 5 | 5 | 5
SERWAY BROTHERS INC. | S | 14-0291 | 2015-02-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
TRIPOINT STONE | S | 14-0291 | 2015-02-01 | 3 | 4 | 3 | 4 | 4 | 4 | 4
UNICO FINISHING SYSTEMS | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
VANDUSEN & STEVES LAND SURVEYORS | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WESWOOD SPECIALTIES | S | 14-0291 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not onsite yet
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0291 | 2015-02-01 | 4 | 4 | 4 | 3 | 4 | 4 | 4
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2015-02-01 | 5 | 5 | 5 | 5 | N/A | N/A | 5 | Great
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2015-02-01 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | Office Lacks Communication
ALEXANDER MITCHELL & SON | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2015-02-01 | N/A | 5 | 5 | N/A | 4 | 4 | 4
ALPHA IRON WORKS, LLC | S | 13-0267 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2015-02-01 | 5 | 5 | 5 | 5 | 2 | N/A | 3
BGI INTERIORS | S | 13-0267 | 2015-02-01 | N/A | 5 | 5 | N/A | 5 | 4 | 4 | Delivery strung out
BUDGET FENCE INCORPORATED | S | 13-0267 | 2015-02-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
CFE, INC. | S | 13-0267 | 2015-02-01 | 3 | 5 | 3 | 5 | 2 | 2 | 2 | Quality issues with the roof; submittal process was poor; office is difficult to get ahold of
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 13-0267 | 2015-02-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2015-02-01 | N/A | 1 | 2 | N/A | 2 | N/A | 2 | poor management of material procurement; send the wrong materials; do not meet delivery dates; do not send full shipments; did not adhere to LCS CO policy
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2015-02-01 | 5 | 5 | 5 | 5 | 4 | 3 | 4
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ERIE MATERIALS INC. | S | 13-0267 | 2015-02-01 | N/A | 4 | N/A | N/A | 4 | 4 | 4
FILBIN PAINTING INC. | S | 13-0267 | 2015-02-01 | 4 | 4 | 5 | 2 | 4 | N/A | 2 | Office does not communicatte; understaffed for the amount of work they bid
GORICK CONSTRUCTION | S | 13-0267 | 2015-02-01 | 1 | 4 | 4 | 5 | 3 | 3 | 3
HOMER C GOW & SONS | S | 13-0267 | 2015-02-01 | 4 | 5 | 5 | 5 | 3 | N/A | 3
J&R SPECIALTIES | S | 13-0267 | 2015-02-01 | 4 | 3 | 4 | 3 | 4 | 4 | 3
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2015-02-01 | 3 | 5 | 5 | 5 | 3 | N/A | 3
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2015-02-01 | 3 | 4 | 4 | 4 | N/A | N/A | 4
L.A.PAINTING, INC. | S | 13-0267 | 2015-02-01 | 3 | 2 | 3 | 4 | 2 | 4 | 2 | Not concerend about quality of finished product; Unresponsive
MATCO ELECTRIC | S | 13-0267 | 2015-02-01 | 5 | 5 | 5 | 5 | 5 | 3 | 4 | solid
MESKO GLASS CO. | S | 13-0267 | 2015-02-01 | 3 | 1 | 3 | 3 | 4 | 4 | 4 | Difficult to get ahold of and manage
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHERN SPACES INC. | S | 13-0267 | 2015-02-01 | 3 | 3 | 4 | 4 | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 13-0267 | 2015-02-01 | 4 | 4 | 4 | 4 | N/A | 5 | N/A
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2015-02-01 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | Very difficult to work with; Need to descope well
RED HAWK FIRE & SECURITY | S | 13-0267 | 2015-02-01 | 4 | 4 | 4 | 4 | 3 | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2015-02-01 | 3 | 3 | 5 | 3 | 3 | 3 | 2 | Difficult to schedule during school- Work in summer. Work is not done when expected.
SCHINDLER ELEVATOR | S | 13-0267 | 2015-02-01 | 4 | 4 | 3 | 4 | 4 | 4 | 3 | Having trouble getting them onsite to repair a dented door
SCHULER-HAAS | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SIMPLEXGRINNELL LP | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | good
SURE TEMP COMPANY INC. | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2015-02-01 | 4 | 3 | 4 | 4 | 3 | 3 | 3
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2015-02-01 | 4 | 4 | 5 | 4 | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2015-02-01 | 4 | 3 | 5 | 3 | 4 | 4 | 4 | good company, would recommend
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
ABSCOPE ENVIRONMENTAL INC. | S | 13-0267 | 2015-02-01 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | Great
AIR TEMP HEATING AND A.C. | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | Office Lacks Communication
ALEXANDER MITCHELL & SON | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
BEACH LAKE SPRINKLER CORP. | S | 13-0267 | 2015-02-01 | 5 | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Delivery strung out
BUDGET FENCE INCORPORATED | S | 13-0267 | 2015-02-01 | 5 | N/A | N/A | N/A | N/A | N/A | N/A
CFE, INC. | S | 13-0267 | 2015-02-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | Quality issues with the roof; submittal process was poor; office is difficult to get ahold of
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 13-0267 | 2015-02-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | poor management of material procurement; send the wrong materials; do not meet delivery dates; do not send full shipments; did not adhere to LCS CO policy
CUTMORE CONSTRUCTION INC. | S | 13-0267 | 2015-02-01 | 5 | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ERIE MATERIALS INC. | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FILBIN PAINTING INC. | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | Office does not communicatte; understaffed for the amount of work they bid
GORICK CONSTRUCTION | S | 13-0267 | 2015-02-01 | 1 | N/A | N/A | N/A | N/A | N/A | N/A
HOMER C GOW & SONS | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
KNOWLTON & SONS CONSTRUCTION | S | 13-0267 | 2015-02-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
KOSLOWSKY CONSTRUCTION | S | 13-0267 | 2015-02-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 13-0267 | 2015-02-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | Not concerend about quality of finished product; Unresponsive
MATCO ELECTRIC | S | 13-0267 | 2015-02-01 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | solid
MESKO GLASS CO. | S | 13-0267 | 2015-02-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | Difficult to get ahold of and manage
NELSON'S LAMP LIGHTERS, INC. | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHERN SPACES INC. | S | 13-0267 | 2015-02-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
PETCOSKY & SONS PLUMBING | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | Very difficult to work with; Need to descope well
RED HAWK FIRE & SECURITY | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
RUG FAIR COMMERCIAL | S | 13-0267 | 2015-02-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | Difficult to schedule during school- Work in summer. Work is not done when expected.
SCHINDLER ELEVATOR | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | Having trouble getting them onsite to repair a dented door
SCHULER-HAAS | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SIMPLEXGRINNELL LP | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | good
SURE TEMP COMPANY INC. | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
TIM DUFFEK CONTRACTING, INC. | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
TRI CITIES TEMPERATURE CONTROL | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | good company, would recommend
WILLIAM H. LANE INC. | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 13-0267 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 13-0267 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LEMOYNE INTERIORS, INC. | S | 14-0289 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.M. STERN, INC. | S | 14-0284 | 2014-10-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
ABJ FIRE PROTECTION CO. | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIRSIDE TECHNOLOGY CORP. | S | 14-0284 | 2014-10-01 | 4 | 5 | N/A | 4 | N/A | 4 | 4
ALEXANDER MITCHELL & SON | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0284 | 2014-10-01 | 4 | 4 | N/A | 4 | N/A | 4 | 4
DESIGN SPECIALISTS INC. | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 14-0284 | 2014-10-01 | N/A | 2 | N/A | N/A | N/A | N/A | 2 | Do not arrive on site per promised dates
E J CONSTRUCTION | S | 14-0284 | 2014-10-01 | 4 | 4 | N/A | 4 | N/A | 4 | 4
FLOWER CITY GLASS | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRANDPAS NURSERY Y GARDENS | S | 14-0284 | 2014-10-01 | 5 | 5 | 5 | 5 | N/A | 5 | 5
HENRY ISAACS HOME REMODELING | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JHP INDUSTRIAL SUPPLY | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KAPPER LANDSCAPING INC. | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LEMOYNE INTERIORS, INC. | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAC CONSTRUCTION CORP. | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PARKITECTS | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 14-0284 | 2014-10-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
WOOD ETC., INC. | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0284 | 2014-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.M. STERN, INC. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABJ FIRE PROTECTION CO. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIRSIDE TECHNOLOGY CORP. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DESIGN SPECIALISTS INC. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E J CONSTRUCTION | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRANDPAS NURSERY Y GARDENS | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JHP INDUSTRIAL SUPPLY | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KAPPER LANDSCAPING INC. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LEMOYNE INTERIORS, INC. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAC CONSTRUCTION CORP. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PARKITECTS | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOOD ETC., INC. | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0284 | 2014-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.M. STERN, INC. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABJ FIRE PROTECTION CO. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIRSIDE TECHNOLOGY CORP. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALEXANDER MITCHELL & SON | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DESIGN SPECIALISTS INC. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E J CONSTRUCTION | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRANDPAS NURSERY Y GARDENS | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JHP INDUSTRIAL SUPPLY | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KAPPER LANDSCAPING INC. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LEMOYNE INTERIORS, INC. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAC CONSTRUCTION CORP. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PARKITECTS | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOOD ETC., INC. | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0284 | 2014-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.M. STERN, INC. | S | 14-0284 | 2015-01-01 | 4 | 5 | 4 | 4 | 4 | 4 | 4
ABJ FIRE PROTECTION CO. | S | 14-0284 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIRSIDE TECHNOLOGY CORP. | S | 14-0284 | 2015-01-01 | 4 | 5 | 4 | 4 | 3 | 4 | 3
ALEXANDER MITCHELL & SON | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0284 | 2015-01-01 | 4 | 4 | 4 | 4 | 2 | 2 | 3 | Not proactive
DESIGN SPECIALISTS INC. | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 14-0284 | 2015-01-01 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | Do not arrive on site per promised dates
E J CONSTRUCTION | S | 14-0284 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRANDPAS NURSERY Y GARDENS | S | 14-0284 | 2015-01-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
JHP INDUSTRIAL SUPPLY | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | 2 | Totally unresponsive. Complete Negligance.
KAPPER LANDSCAPING INC. | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | completely unresponsive. Supposed to provide WBE and this is in their contract and they have yet to deliver on this.
LEMOYNE INTERIORS, INC. | S | 14-0284 | 2015-01-01 | 5 | 5 | 5 | 5 | 4 | 4 | 4
MAC CONSTRUCTION CORP. | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 14-0284 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PARKITECTS | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5
PRO CARPET INC. | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 14-0284 | 2015-01-01 | 3 | 4 | 4 | 4 | 4 | 4 | 3
SCHINDLER ELEVATOR | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | 4 | 4 | 2
US CEILING CORP. | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WOOD ETC., INC. | S | 14-0284 | 2015-01-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0284 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.M. STERN, INC. | S | 14-0284 | 2015-02-01 | 4 | 5 | 4 | 4 | 4 | 4 | 4
ABJ FIRE PROTECTION CO. | S | 14-0284 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIRSIDE TECHNOLOGY CORP. | S | 14-0284 | 2015-02-01 | 4 | 5 | 4 | 4 | 3 | 4 | 3
ALEXANDER MITCHELL & SON | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
DDS CONSTRUCTORS, LLC | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0284 | 2015-02-01 | 4 | 4 | 4 | 4 | 2 | 2 | 3 | Not proactive
DESIGN SPECIALISTS INC. | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 14-0284 | 2015-02-01 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | Do not arrive on site per promised dates
E J CONSTRUCTION | S | 14-0284 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
GRANDPAS NURSERY Y GARDENS | S | 14-0284 | 2015-02-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
JHP INDUSTRIAL SUPPLY | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | 2 | Totally unresponsive. Complete Negligance.
KAPPER LANDSCAPING INC. | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | completely unresponsive. Supposed to provide WBE and this is in their contract and they have yet to deliver on this.
LEMOYNE INTERIORS, INC. | S | 14-0284 | 2015-02-01 | 5 | 5 | 5 | 5 | 4 | 4 | 4
MAC CONSTRUCTION CORP. | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NEW YORK STATE FENCE, INC | S | 14-0284 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PARKITECTS | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5
PRO CARPET INC. | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
RAULLI Y SONS, INC. | S | 14-0284 | 2015-02-01 | 3 | 4 | 4 | 4 | 4 | 4 | 3
SCHINDLER ELEVATOR | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | 4 | 4 | 2
US CEILING CORP. | S | 14-0284 | 2015-02-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
WOOD ETC., INC. | S | 14-0284 | 2015-02-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0284 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
84 LUMBER COMPANY | S | 14-0295 | 2015-02-01 | N/A | 4 | 4 | 4 | 3 | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0295 | 2015-02-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 14-0295 | 2015-02-01 | 4 | 4 | 4 | 3 | N/A | 4 | 4
AMERICAN PLUMBING, INC | S | 14-0295 | 2015-02-01 | 4 | 3 | 4 | 2 | 4 | 2 | 3 | Manpower issues
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0295 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0295 | 2015-02-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
DDS CONSTRUCTORS, LLC | S | 14-0295 | 2015-02-01 | 4 | 4 | 5 | 3 | 2 | 4 | 3 | Not pricing, just changed PM on project
FLOWER CITY GLASS | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 14-0295 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KAPPER LANDSCAPING INC. | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KSP PAINTING OF SYRACUSE | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARACLE BUILDERS | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0295 | 2015-02-01 | 5 | N/A | N/A | N/A | N/A | N/A | N/A
MEIER SUPPLY CO | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 14-0295 | 2015-02-01 | N/A | 4 | N/A | N/A | N/A | 4 | 4
POSTLER & JAECKLE CORP. | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 14-0295 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 2 | 3 | Have not yet submitted submittals
RUSS & KATHY RAWLEIGH | S | 14-0295 | 2015-02-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
SCHINDLER ELEVATOR | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRUAX & HOVEY | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 14-0295 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 14-0295 | 2015-03-01 | N/A | 4 | 4 | 4 | 3 | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 14-0295 | 2015-03-01 | 4 | 4 | 4 | 3 | N/A | 4 | 4
AMERICAN PLUMBING, INC | S | 14-0295 | 2015-03-01 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | Manpower issues, office is not responsive, schedule and quality concerns with meeting first milestone
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0295 | 2015-03-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
DDS CONSTRUCTORS, LLC | S | 14-0295 | 2015-03-01 | 4 | 4 | 5 | 3 | 2 | 4 | 3 | Not pricing, just changed PM on project
FLOWER CITY GLASS | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KAPPER LANDSCAPING INC. | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KSP PAINTING OF SYRACUSE | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARACLE BUILDERS | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEIER SUPPLY CO | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 14-0295 | 2015-03-01 | N/A | 4 | N/A | N/A | N/A | 4 | 4
POSTLER & JAECKLE CORP. | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 14-0295 | 2015-03-01 | 4 | 4 | 4 | 4 | 4 | 2 | 3 | Have not yet submitted submittals
RUSS & KATHY RAWLEIGH | S | 14-0295 | 2015-03-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
SCHINDLER ELEVATOR | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRUAX & HOVEY | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 14-0295 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACQUATIC LANDSCAPING | S | 13-0276 | 2015-03-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | took their scores off until they get back on site
FIRE PAK | S | 13-0276 | 2015-03-18 | 4 | 3 | 4 | 3 | 4 | 4 | N/A
GOMEZ & SONS | S | 13-0276 | 2015-03-18 | 5 | 5 | 4 | 4 | 4 | N/A | N/A | No longer on site
MEISNER | S | 13-0276 | 2015-03-18 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
OHL | S | 13-0276 | 2015-03-18 | 3 | 1 | 2 | 1 | 2 | 2 | N/A | Has a hard time following a schedule including their own.
PARAMOUNT | S | 13-0276 | 2015-03-18 | 4 | 4 | N/A | 3 | 4 | 4 | N/A
SOLUTIONS | S | 13-0276 | 2015-03-18 | 4 | 3 | 3 | 4 | 4 | 4 | N/A | Sub has a hard time following a schedule- there has been an improvement in schedule management
SOUTHERN COAST ROOFING | S | 13-0276 | 2015-03-18 | 4 | 4 | 4 | 4 | 3 | 3 | N/A
SPI | S | 13-0276 | 2015-03-18 | N/A | N/A | N/A | 4 | 3 | 3 | N/A | Off site
STATE LINE PRODUCTS | S | 13-0276 | 2015-03-18 | 5 | 5 | 5 | 5 | N/A | 3 | N/A
STEEL FAB | S | 13-0276 | 2015-03-18 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
TROPIC | S | 13-0276 | 2015-03-18 | 4 | 3 | 4 | 3 | N/A | 3 | N/A
WILDCAT | S | 13-0276 | 2015-03-18 | 3 | 1 | 2 | 2 | N/A | N/A | N/A
Y&T | S | 13-0276 | 2015-03-18 | 5 | 5 | 4 | 4 | 4 | 4 | N/A
AGAPE WHOLESALE FURNITURE | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0298 | 2015-02-02 | 4 | 4 | 5 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0298 | 2015-02-02 | 4 | 4 | 5 | 4 | 4 | 3 | 4
DEMCO NEW YORK CORP. | S | 14-0298 | 2015-02-02 | 4 | 3 | 3 | 3 | 4 | 4 | 4
ERIE MATERIALS INC. | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HIGHLAND QUALITY CONSTRUCTION | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 14-0298 | 2015-02-02 | 4 | 3 | 4 | 3 | 4 | 4 | 4
KJW ASSOCIATES | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 14-0298 | 2015-02-02 | N/A | 3 | N/A | N/A | 4 | 4 | 4
MAX T. DOLAND | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 14-0298 | 2015-02-02 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PARKITECTS | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHACHTLER CONTRACTING | S | 14-0298 | 2015-02-02 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHINDLER ELEVATOR | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SESSLER EXCAVATING | S | 14-0298 | 2015-02-02 | 5 | 5 | 5 | 5 | 5 | 5 | 5
TG MILLER | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TOWER ROOFING | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRUAX & HOVEY | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0298 | 2015-02-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0298 | 2015-02-02 | 4 | 4 | N/A | N/A | N/A | N/A | 4
A.M. STERN, INC. | S | 14-0284 | 2015-03-01 | 4 | 5 | 4 | 4 | 4 | 4 | 4
ABJ FIRE PROTECTION CO. | S | 14-0284 | 2015-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIRSIDE TECHNOLOGY CORP. | S | 14-0284 | 2015-03-01 | 4 | 5 | 4 | 4 | 3 | 4 | 3
ALEXANDER MITCHELL & SON | S | 14-0284 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0284 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0284 | 2015-03-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0284 | 2015-03-01 | 3 | 4 | 4 | 4 | 1 | 2 | 3 | The PM seems to be the primary source of issues.Not proactive
DESIGN SPECIALISTS INC. | S | 14-0284 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 14-0284 | 2015-03-01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Do not arrive on site per promised dates
E J CONSTRUCTION | S | 14-0284 | 2015-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 14-0284 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRANDPAS NURSERY Y GARDENS | S | 14-0284 | 2015-03-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 14-0284 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
JHP INDUSTRIAL SUPPLY | S | 14-0284 | 2015-03-01 | N/A | 1 | N/A | N/A | 1 | 1 | 1 | Totally unresponsive. Complete Negligance.
KAPPER LANDSCAPING INC. | S | 14-0284 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0284 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | completely unresponsive. Supposed to provide WBE and this is in their contract and they have yet to deliver on this.
LEMOYNE INTERIORS, INC. | S | 14-0284 | 2015-03-01 | 5 | 5 | 5 | 5 | 4 | 4 | 4
MAC CONSTRUCTION CORP. | S | 14-0284 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 14-0284 | 2015-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PARKITECTS | S | 14-0284 | 2015-03-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5
PRO CARPET INC. | S | 14-0284 | 2015-03-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
RAULLI Y SONS, INC. | S | 14-0284 | 2015-03-01 | 3 | 2 | 4 | 4 | 4 | 4 | 3 | Rauli shows up on site when they want to and refuses to work with the teams schedule
SCHINDLER ELEVATOR | S | 14-0284 | 2015-03-01 | N/A | N/A | N/A | N/A | 4 | 4 | 2
US CEILING CORP. | S | 14-0284 | 2015-03-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
WOOD ETC., INC. | S | 14-0284 | 2015-03-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0284 | 2015-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACQUATIC LANDSCAPING | S | 13-0276 | 2015-04-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Carpet Tech | S | 13-0276 | 2015-04-22 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Designer Tops | S | 13-0276 | 2015-04-22 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Finy Sales | S | 13-0276 | 2015-04-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRE PAK | S | 13-0276 | 2015-04-22 | 4 | 3 | 4 | 3 | 4 | 4 | 4
GOMEZ & SONS | S | 13-0276 | 2015-04-22 | 5 | 5 | 4 | 4 | 4 | N/A | 4
Lace | S | 13-0276 | 2015-04-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEISNER | S | 13-0276 | 2015-04-22 | 5 | 5 | 4 | 4 | 4 | 4 | 4
OHL | S | 13-0276 | 2015-04-22 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | Has a hard time following a schedule including their own.
PARAMOUNT | S | 13-0276 | 2015-04-22 | 4 | 5 | 4 | 4 | N/A | 3 | 3
Pena-Alum | S | 13-0276 | 2015-04-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOLUTIONS | S | 13-0276 | 2015-04-22 | 4 | 3 | 3 | 4 | 4 | 4 | 3 | Sub has a hard time following a schedule- there has been an improvement in schedule management
SOUTHERN COAST ROOFING | S | 13-0276 | 2015-04-22 | 4 | 4 | 4 | 4 | 3 | 3 | 4
SPI | S | 13-0276 | 2015-04-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STATE LINE PRODUCTS | S | 13-0276 | 2015-04-22 | 5 | 5 | 5 | 5 | N/A | 3 | 4
STEEL FAB | S | 13-0276 | 2015-04-22 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Tempo | S | 13-0276 | 2015-04-22 | 5 | 5 | 4 | 4 | 4 | 5 | 5
TROPIC | S | 13-0276 | 2015-04-22 | 4 | 3 | 4 | 3 | N/A | 3 | 4
Unicorn | S | 13-0276 | 2015-04-22 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Vassell | S | 13-0276 | 2015-04-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Viviano | S | 13-0276 | 2015-04-22 | 5 | 5 | 5 | 5 | 5 | 5 | 5
WILDCAT | S | 13-0276 | 2015-04-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Y&T | S | 13-0276 | 2015-04-22 | 5 | 3 | 3 | 2 | 3 | 3 | 4
AGAPE WHOLESALE FURNITURE | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0298 | 2015-03-27 | 4 | 4 | 5 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0298 | 2015-03-27 | 4 | 4 | 5 | 4 | 4 | 3 | 4
DEMCO NEW YORK CORP. | S | 14-0298 | 2015-03-27 | 4 | 3 | 3 | 3 | 4 | 4 | 4
ERIE MATERIALS INC. | S | 14-0298 | 2015-03-27 | N/A | 4 | N/A | N/A | N/A | N/A | N/A | Supplier
FLOWER CITY GLASS | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HIGHLAND QUALITY CONSTRUCTION | S | 14-0298 | 2015-03-27 | 4 | 4 | 3 | 4 | 4 | N/A | 4
J&R SPECIALTIES | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 14-0298 | 2015-03-27 | 4 | 3 | 4 | 3 | 4 | 4 | 4
KJW ASSOCIATES | S | 14-0298 | 2015-03-27 | 4 | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 14-0298 | 2015-03-27 | N/A | 3 | N/A | N/A | 4 | 4 | 4
MAX T. DOLAND | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PARKITECTS | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHACHTLER CONTRACTING | S | 14-0298 | 2015-03-27 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHINDLER ELEVATOR | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SESSLER EXCAVATING | S | 14-0298 | 2015-03-27 | 5 | 5 | 5 | 5 | 5 | 5 | 5
TG MILLER | S | 14-0298 | 2015-03-27 | 4 | 4 | 4 | 4 | 4 | 4 | N/A
TOWER ROOFING | S | 14-0298 | 2015-03-27 | 4 | 2 | 4 | 3 | N/A | 3 | 3 | Didn?t start ontime
TRUAX & HOVEY | S | 14-0298 | 2015-03-27 | 4 | 3 | 4 | 4 | N/A | 4 | 4
WHITMORE FENCE | S | 14-0298 | 2015-03-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0298 | 2015-03-27 | 4 | 4 | N/A | N/A | N/A | N/A | 4
AGAPE WHOLESALE FURNITURE | S | 14-0298 | 2015-05-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 14-0298 | 2015-05-27 | 4 | 3 | 4 | 3 | 3 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 14-0298 | 2015-05-27 | N/A | 4 | N/A | 4 | N/A | 4 | 4 | Supplier
ALPHA IRON WORKS, LLC | S | 14-0298 | 2015-05-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0298 | 2015-05-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0298 | 2015-05-27 | 4 | 4 | 5 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 14-0298 | 2015-05-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0298 | 2015-05-27 | 4 | 4 | 5 | 4 | 4 | 3 | 4
DEMCO NEW YORK CORP. | S | 14-0298 | 2015-05-27 | 4 | 3 | 3 | 3 | 4 | 4 | 4
ERIE MATERIALS INC. | S | 14-0298 | 2015-05-27 | N/A | 4 | N/A | N/A | N/A | N/A | N/A | Supplier
FLOWER CITY GLASS | S | 14-0298 | 2015-05-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0298 | 2015-05-27 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HIGHLAND QUALITY CONSTRUCTION | S | 14-0298 | 2015-05-27 | 4 | 4 | 3 | 4 | 4 | N/A | 4
J&R SPECIALTIES | S | 14-0298 | 2015-05-27 | 4 | 4 | 4 | 4 | 4 | 4 | 4
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0298 | 2015-05-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 14-0298 | 2015-05-27 | 4 | 3 | 4 | 3 | 4 | 4 | 4
KJW ASSOCIATES | S | 14-0298 | 2015-05-27 | 4 | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 14-0298 | 2015-05-27 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LAKEVIEW LAWN & LANDSCAPE | S | 14-0298 | 2015-05-27 | 4 | 3 | 4 | 3 | 4 | 4 | 4
MAX T. DOLAND | S | 14-0298 | 2015-05-27 | N/A | 4 | N/A | 4 | N/A | 4 | 4 | Supplier
MONTGOMERY TRUSS | S | 14-0298 | 2015-05-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PARKITECTS | S | 14-0298 | 2015-05-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0298 | 2015-05-27 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHACHTLER CONTRACTING | S | 14-0298 | 2015-05-27 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHINDLER ELEVATOR | S | 14-0298 | 2015-05-27 | 4 | 3 | 4 | 4 | 4 | 4 | 3
SERWAY BROTHERS INC. | S | 14-0298 | 2015-05-27 | N/A | 3 | 3 | 4 | 4 | 4 | 4
SESSLER EXCAVATING | S | 14-0298 | 2015-05-27 | 5 | 5 | 5 | 5 | 5 | 5 | 5
TG MILLER | S | 14-0298 | 2015-05-27 | 4 | 4 | 4 | 4 | 4 | 4 | 4
TOWER ROOFING | S | 14-0298 | 2015-05-27 | 4 | 2 | 4 | 3 | N/A | 3 | 3 | Didn?t start ontime
TRUAX & HOVEY | S | 14-0298 | 2015-05-27 | 4 | 3 | 4 | 4 | N/A | 4 | 4
WHITMORE FENCE | S | 14-0298 | 2015-05-27 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 14-0298 | 2015-05-27 | 4 | 4 | N/A | N/A | N/A | N/A | 4 | Supplier
AGAPE WHOLESALE FURNITURE | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0298 | 2015-04-01 | 4 | 4 | 5 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0298 | 2015-04-01 | 4 | 4 | 5 | 4 | 4 | 3 | 4
DEMCO NEW YORK CORP. | S | 14-0298 | 2015-04-01 | 4 | 3 | 3 | 3 | 4 | 4 | 4
ERIE MATERIALS INC. | S | 14-0298 | 2015-04-01 | N/A | 4 | N/A | N/A | N/A | N/A | N/A | Supplier
FLOWER CITY GLASS | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HIGHLAND QUALITY CONSTRUCTION | S | 14-0298 | 2015-04-01 | 4 | 4 | 3 | 4 | 4 | N/A | 4
J&R SPECIALTIES | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KJW ASSOCIATES | S | 14-0298 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 14-0298 | 2015-04-01 | N/A | 3 | N/A | N/A | 4 | 4 | 4
MAX T. DOLAND | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PARKITECTS | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHACHTLER CONTRACTING | S | 14-0298 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHINDLER ELEVATOR | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SESSLER EXCAVATING | S | 14-0298 | 2015-04-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
TG MILLER | S | 14-0298 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
TOWER ROOFING | S | 14-0298 | 2015-04-01 | 4 | 2 | 4 | 3 | N/A | 3 | 3 | Didn?t start ontime
TRUAX & HOVEY | S | 14-0298 | 2015-04-01 | 4 | 3 | 4 | 4 | N/A | 4 | 4
WHITMORE FENCE | S | 14-0298 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0298 | 2015-04-01 | 4 | 4 | N/A | N/A | N/A | N/A | 4
84 LUMBER COMPANY | S | 14-0295 | 2015-06-03 | N/A | 4 | 4 | 4 | 3 | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 14-0295 | 2015-06-03 | 4 | 4 | 4 | 3 | N/A | 4 | 4
AMERICAN PLUMBING, INC | S | 14-0295 | 2015-06-03 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | Manpower issues, office is not responsive, schedule and quality concerns with meeting first milestone
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0295 | 2015-06-03 | N/A | 5 | N/A | N/A | N/A | 4 | 4 | Vendor
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0295 | 2015-06-03 | 5 | 5 | 5 | 5 | 5 | 5 | 5
DDS CONSTRUCTORS, LLC | S | 14-0295 | 2015-06-03 | 4 | 4 | 5 | 3 | 2 | 4 | 3 | Not pricing, just changed PM on project
FLOWER CITY GLASS | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 14-0295 | 2015-06-03 | 3 | 2 | 3 | 1 | 3 | 2 | 2 | Staffing issues which are causing schedule issues
J&R SPECIALTIES | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KAPPER LANDSCAPING INC. | S | 14-0295 | 2015-06-03 | 4 | 4 | 4 | 4 | N/A | 4 | 4
KSP PAINTING OF SYRACUSE | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARACLE BUILDERS | S | 14-0295 | 2015-06-03 | 3 | 4 | 4 | 5 | 2 | N/A | 3 | Impressed and would use them again
MAX T. DOLAND | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEIER SUPPLY CO | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 14-0295 | 2015-06-03 | N/A | 4 | N/A | N/A | N/A | 4 | 4
POSTLER & JAECKLE CORP. | S | 14-0295 | 2015-06-03 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 14-0295 | 2015-06-03 | 4 | 4 | 4 | 4 | 4 | 2 | 3 | Have not yet submitted submittals
RUSS & KATHY RAWLEIGH | S | 14-0295 | 2015-06-03 | 4 | 4 | 4 | 4 | N/A | 4 | 4
SCHINDLER ELEVATOR | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | Difficult to work with
SPECIAL CARE SYSTEMS, LLC | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRUAX & HOVEY | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 14-0295 | 2015-06-03 | 4 | 4 | 4 | 4 | 3 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0295 | 2015-06-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.D.W INC. | S | 14-0296 | 2015-03-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
AAA QUALITY MAINTAINENCE | S | 14-0296 | 2015-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0296 | 2015-03-01 | 3 | 4 | 3 | 4 | 3 | N/A | 3
ALL SEASONS GENERAL | S | 14-0296 | 2015-03-01 | 3 | 2 | 1 | 3 | 2 | 1 | 2 | Would not recommend hiring this sub again
ARCHER EXTERIORS | S | 14-0296 | 2015-03-01 | 1 | 3 | 2 | 3 | 4 | 3 | 3
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0296 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
BLUE RIDGE LUMBER COMPANY | S | 14-0296 | 2015-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier only
BYRNES ELECTRIC | S | 14-0296 | 2015-03-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
CUSTOM STEEL CONTRACTORS | S | 14-0296 | 2015-03-01 | 4 | 3 | 3 | 4 | N/A | 4 | 4
DUKES LANDSCAPE MANAGEMENT | S | 14-0296 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
FLOWER CITY GLASS | S | 14-0296 | 2015-03-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
GE APPLIANCES | S | 14-0296 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
HOWARD BURD & SONS | S | 14-0296 | 2015-03-01 | 2 | 5 | 2 | 3 | 3 | N/A | 2 | currently developing relationship
J&R SPECIALTIES | S | 14-0296 | 2015-03-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
KENNON SURVEY SERVICES | S | 14-0296 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHL BUILDING PRODUCTS | S | 14-0296 | 2015-03-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
LODI WELDING COMPANY | S | 14-0296 | 2015-03-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
LOWTHERS CONTRACTING | S | 14-0296 | 2015-03-01 | 2 | 3 | 1 | 2 | N/A | 4 | 4 | Completely underachieved on this project
MAX T. DOLAND | S | 14-0296 | 2015-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PENTEL DRYWALL | S | 14-0296 | 2015-03-01 | 2 | 2 | 1 | 1 | 3 | 3 | 3 | manpower issues,
PENYAK ROOFING | S | 14-0296 | 2015-03-01 | 2 | 4 | 4 | 4 | 2 | 2 | 2 | office is lacking
PREMIER GRANITE AND MARBLE | S | 14-0296 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
RED LION INSULATION | S | 14-0296 | 2015-03-01 | 3 | 3 | 4 | 4 | 3 | 3 | 3
RJK FLOOR COVERING | S | 14-0296 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | no longer a sub, been replaced
S Y R MECHANICAL | S | 14-0296 | 2015-03-01 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | Only faxes, does not use e-mail
SLIWINSKI FLOORING COVERING | S | 14-0296 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
SPEICHER EXCAVATING | S | 14-0296 | 2015-03-01 | 4 | 4 | 3 | 4 | 4 | 3 | 4
UNICO FINISHING SYSTEMS | S | 14-0296 | 2015-03-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
WIRES ELECTRICAL SHOP | S | 14-0296 | 2015-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 14-0296 | 2015-03-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
A.D.W INC. | S | 14-0296 | 2015-04-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
AAA QUALITY MAINTAINENCE | S | 14-0296 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0296 | 2015-04-01 | 3 | 3 | 4 | 4 | 3 | N/A | 3
ALL SEASONS GENERAL | S | 14-0296 | 2015-04-01 | 3 | 2 | 1 | 3 | 2 | 1 | 2 | Would not recommend hiring this sub again
ARCHER EXTERIORS | S | 14-0296 | 2015-04-01 | 1 | 2 | 3 | 3 | 4 | 3 | 3
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0296 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
BLUE RIDGE LUMBER COMPANY | S | 14-0296 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier only
BYRNES ELECTRIC | S | 14-0296 | 2015-04-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
CUSTOM STEEL CONTRACTORS | S | 14-0296 | 2015-04-01 | 4 | 3 | 3 | 4 | N/A | 4 | 4
DUKES LANDSCAPE MANAGEMENT | S | 14-0296 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
FLOWER CITY GLASS | S | 14-0296 | 2015-04-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
GE APPLIANCES | S | 14-0296 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
HOWARD BURD & SONS | S | 14-0296 | 2015-04-01 | 2 | 5 | 2 | 3 | 3 | N/A | 2 | currently developing relationship
J&R SPECIALTIES | S | 14-0296 | 2015-04-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
KENNON SURVEY SERVICES | S | 14-0296 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHL BUILDING PRODUCTS | S | 14-0296 | 2015-04-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
LODI WELDING COMPANY | S | 14-0296 | 2015-04-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
LOWTHERS CONTRACTING | S | 14-0296 | 2015-04-01 | 2 | 3 | 1 | 2 | N/A | 4 | 4 | Completely underachieved on this project
MAX T. DOLAND | S | 14-0296 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PENTEL DRYWALL | S | 14-0296 | 2015-04-01 | 2 | 2 | 1 | 1 | 3 | 3 | 3 | manpower issues,
PENYAK ROOFING | S | 14-0296 | 2015-04-01 | 2 | 4 | 4 | 4 | 2 | 2 | 2 | office is lacking
PREMIER GRANITE AND MARBLE | S | 14-0296 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
RED LION INSULATION | S | 14-0296 | 2015-04-01 | 3 | 3 | 4 | 4 | 3 | 3 | 3
RJK FLOOR COVERING | S | 14-0296 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | no longer a sub, been replaced
S Y R MECHANICAL | S | 14-0296 | 2015-04-01 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | Only faxes, does not use e-mail
SLIWINSKI FLOORING COVERING | S | 14-0296 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
SPEICHER EXCAVATING | S | 14-0296 | 2015-04-01 | 4 | 4 | 3 | 4 | 4 | 3 | 4
UNICO FINISHING SYSTEMS | S | 14-0296 | 2015-04-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
WIRES ELECTRICAL SHOP | S | 14-0296 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 14-0296 | 2015-04-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
A.D.W INC. | S | 14-0296 | 2015-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
AAA QUALITY MAINTAINENCE | S | 14-0296 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0296 | 2015-05-01 | 3 | 3 | 4 | 4 | 3 | N/A | 3
ALL SEASONS GENERAL | S | 14-0296 | 2015-05-01 | 3 | 1 | 2 | 3 | 2 | 1 | 2 | Would not recommend hiring this sub again
ARCHER EXTERIORS | S | 14-0296 | 2015-05-01 | 1 | 2 | 3 | 3 | 4 | 3 | 3
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0296 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
BLUE RIDGE LUMBER COMPANY | S | 14-0296 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier only
BYRNES ELECTRIC | S | 14-0296 | 2015-05-01 | 4 | 4 | 4 | 4 | 5 | 5 | 5
CUSTOM STEEL CONTRACTORS | S | 14-0296 | 2015-05-01 | 4 | 3 | 3 | 4 | N/A | 4 | 4
DUKES LANDSCAPE MANAGEMENT | S | 14-0296 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
FLOWER CITY GLASS | S | 14-0296 | 2015-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
GE APPLIANCES | S | 14-0296 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
HOWARD BURD & SONS | S | 14-0296 | 2015-05-01 | 2 | 5 | 2 | 3 | 3 | N/A | 2 | currently developing relationship
J&R SPECIALTIES | S | 14-0296 | 2015-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
KENNON SURVEY SERVICES | S | 14-0296 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOHL BUILDING PRODUCTS | S | 14-0296 | 2015-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
LODI WELDING COMPANY | S | 14-0296 | 2015-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
LOWTHERS CONTRACTING | S | 14-0296 | 2015-05-01 | 2 | 3 | 1 | 2 | N/A | 4 | 4 | Completely underachieved on this project
MAX T. DOLAND | S | 14-0296 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PENTEL DRYWALL | S | 14-0296 | 2015-05-01 | 2 | 2 | 1 | 1 | 3 | 3 | 3 | manpower issues,
PENYAK ROOFING | S | 14-0296 | 2015-05-01 | 2 | 4 | 4 | 4 | 2 | 2 | 2 | office is lacking
PREMIER GRANITE AND MARBLE | S | 14-0296 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
RED LION INSULATION | S | 14-0296 | 2015-05-01 | 3 | 3 | 4 | 4 | 3 | 3 | 3
RJK FLOOR COVERING | S | 14-0296 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | no longer a sub, been replaced
S Y R MECHANICAL | S | 14-0296 | 2015-05-01 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | Only faxes, does not use e-mail
SLIWINSKI FLOORING COVERING | S | 14-0296 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | not yet onsite
SPEICHER EXCAVATING | S | 14-0296 | 2015-05-01 | 4 | 4 | 3 | 4 | 4 | 3 | 4
UNICO FINISHING SYSTEMS | S | 14-0296 | 2015-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
WIRES ELECTRICAL SHOP | S | 14-0296 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 14-0296 | 2015-05-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
AIIA CONSTRUCTION COMPANY, INC | S | 14-0285 | 2015-03-01 | 3 | 4 | 4 | 4 | 4 | N/A | 4
AJAY GLASS & MIRROR | S | 14-0285 | 2015-03-01 | 4 | 4 | 4 | 4 | 4 | 2 | 3 | Paperwork side is not good
ASI SIGNAGE | S | 14-0285 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | 5 | 4
BENEDETTI BUILDERS | S | 14-0285 | 2015-03-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
CEDAR ENTERPRISES | S | 14-0285 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
COMMERCIAL Y RESIDENTIAL PAINTING | S | 14-0285 | 2015-03-01 | 4 | 4 | 4 | 3 | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 14-0285 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
MAX T. DOLAND | S | 14-0285 | 2015-03-01 | 4 | N/A | N/A | N/A | N/A | 4 | 4
MGM INSULATION | S | 14-0285 | 2015-03-01 | 4 | 4 | 5 | 4 | 4 | 4 | 4
MORSE SASH & DOOR | S | 14-0285 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
PRO CARPET INC. | S | 14-0285 | 2015-03-01 | 4 | 4 | 4 | 3 | 4 | 4 | 4
SANITAIRE CLEANING CO., INC. | S | 14-0285 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0285 | 2015-03-01 | 3 | 4 | 4 | 4 | 3 | 3 | 3
SYRACUSE MOSAIC | S | 14-0285 | 2015-03-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
VANDYKE PAINTING COMPANY | S | 14-0285 | 2015-03-01 | 3 | 2 | 4 | 2 | 3 | 3 | 4 | Contract terminated however will be back on site Monday.
WEYDMAN ELECTRIC | S | 14-0285 | 2015-03-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0285 | 2015-03-01 | N/A | 4 | N/A | N/A | N/A | 5 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0285 | 2015-03-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0285 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AJAY GLASS & MIRROR | S | 14-0285 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 2 | 3 | Paperwork side is not good
ASI SIGNAGE | S | 14-0285 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | 5 | 4
BENEDETTI BUILDERS | S | 14-0285 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CEDAR ENTERPRISES | S | 14-0285 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
COMMERCIAL Y RESIDENTIAL PAINTING | S | 14-0285 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 14-0285 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
MAX T. DOLAND | S | 14-0285 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | Supplier
MGM INSULATION | S | 14-0285 | 2015-04-01 | 4 | 4 | 5 | 4 | 4 | 4 | 4
MORSE SASH & DOOR | S | 14-0285 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
PRO CARPET INC. | S | 14-0285 | 2015-04-01 | 4 | 4 | 4 | 3 | 4 | 4 | 4
SANITAIRE CLEANING CO., INC. | S | 14-0285 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
SERWAY BROTHERS INC. | S | 14-0285 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYRACUSE MOSAIC | S | 14-0285 | 2015-04-01 | 4 | 5 | 4 | 5 | 4 | 4 | 4
VANDYKE PAINTING COMPANY | S | 14-0285 | 2015-04-01 | 3 | 2 | 4 | 2 | 3 | 3 | 4
WEYDMAN ELECTRIC | S | 14-0285 | 2015-04-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0285 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0285 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 14-0285 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AJAY GLASS & MIRROR | S | 14-0285 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | 2 | 3 | Paperwork side is not good
ASI SIGNAGE | S | 14-0285 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BENEDETTI BUILDERS | S | 14-0285 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CEDAR ENTERPRISES | S | 14-0285 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
COMMERCIAL Y RESIDENTIAL PAINTING | S | 14-0285 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 14-0285 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
MAX T. DOLAND | S | 14-0285 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | Supplier
MGM INSULATION | S | 14-0285 | 2015-05-01 | 4 | 4 | 5 | 4 | 4 | 4 | 4
MORSE SASH & DOOR | S | 14-0285 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
PRO CARPET INC. | S | 14-0285 | 2015-05-01 | 4 | 4 | 4 | 3 | 4 | 4 | 4
SANITAIRE CLEANING CO., INC. | S | 14-0285 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
SERWAY BROTHERS INC. | S | 14-0285 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYRACUSE MOSAIC | S | 14-0285 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
VANDYKE PAINTING COMPANY | S | 14-0285 | 2015-05-01 | 3 | 2 | 4 | 3 | 3 | 3 | 4
WEYDMAN ELECTRIC | S | 14-0285 | 2015-05-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0285 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0285 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 14-0285 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AJAY GLASS & MIRROR | S | 14-0285 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 2 | 4
ASI SIGNAGE | S | 14-0285 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BENEDETTI BUILDERS | S | 14-0285 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CEDAR ENTERPRISES | S | 14-0285 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
COMMERCIAL Y RESIDENTIAL PAINTING | S | 14-0285 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONSTRUCTION SPECIALITIES INC. | S | 14-0285 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Supplier
MAX T. DOLAND | S | 14-0285 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4 | Supplier
MGM INSULATION | S | 14-0285 | 2015-06-01 | 4 | 4 | 5 | 4 | 4 | 4 | 4
MORSE SASH & DOOR | S | 14-0285 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
PRO CARPET INC. | S | 14-0285 | 2015-06-01 | 4 | 4 | 4 | 3 | 4 | 4 | 4
SANITAIRE CLEANING CO., INC. | S | 14-0285 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | N/A | 4
SERWAY BROTHERS INC. | S | 14-0285 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYRACUSE MOSAIC | S | 14-0285 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
VANDYKE PAINTING COMPANY | S | 14-0285 | 2015-06-01 | 3 | 2 | 4 | 3 | 3 | 3 | 4
WEYDMAN ELECTRIC | S | 14-0285 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0285 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0285 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIED MECHANICAL | S | 15-0305 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.J. QUIGLIANO | S | 15-0305 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 15-0305 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PASSERO ASSOCIATES | S | 15-0305 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S.A.B. SPECIALTIES | S | 15-0305 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIED MECHANICAL | S | 15-0305 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.J. QUIGLIANO | S | 15-0305 | 2015-06-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
MAX T. DOLAND | S | 15-0305 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PASSERO ASSOCIATES | S | 15-0305 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S.A.B. SPECIALTIES | S | 15-0305 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACPRODUCTS, INC | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIED MECHANICAL | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BALTZ CONCRETE CONST., INC | S | 15-0305 | 2015-07-01 | 5 | 5 | 5 | 5 | 5 | N/A | 5 | Excellent Safety. Great all around.
BUFFALO CONCRETE ACCESSORIES | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAPITIAL FENCE CO., INC | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATALANO CONTRACTING, INC | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENERGY INSULATION SYSTEMS, INC | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FISHER CONCRETE, INC | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J Y R SPECIALITIES, INC | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | 2 | 4 | 3 | Great in-house CAD dept.
KLEIN REINFORCING SERVICES | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.J. QUIGLIANO | S | 15-0305 | 2015-07-01 | 4 | 4 | N/A | 4 | 4 | 3 | 4
MAX T. DOLAND | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS & PANEL (PANELS) | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ONTARIO EXTERIORS, INC | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PASSERO ASSOCIATES | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S.A.B. SPECIALTIES | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNITED MATERIALS, LLC | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 15-0305 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACPRODUCTS, INC | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIED MECHANICAL | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BALTZ CONCRETE CONST., INC | S | 15-0305 | 2015-08-01 | 5 | 5 | 5 | 5 | 5 | N/A | 5 | Excellent Safety. Great all around.
BUFFALO CONCRETE ACCESSORIES | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAPITIAL FENCE CO., INC | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATALANO CONTRACTING, INC | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENERGY INSULATION SYSTEMS, INC | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FISHER CONCRETE, INC | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J Y R SPECIALITIES, INC | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | 2 | 4 | 3 | Great in-house CAD dept.
KLEIN REINFORCING SERVICES | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.J. QUIGLIANO | S | 15-0305 | 2015-08-01 | 4 | 4 | N/A | 4 | 4 | 3 | 4
MAX T. DOLAND | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS & PANEL (PANELS) | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ONTARIO EXTERIORS, INC | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PASSERO ASSOCIATES | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S.A.B. SPECIALTIES | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNITED MATERIALS, LLC | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 15-0305 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A.M. STERN, INC. | S | 14-0284 | 2015-04-01 | 4 | 5 | 4 | 4 | 4 | 4 | 4
ABJ FIRE PROTECTION CO. | S | 14-0284 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIRSIDE TECHNOLOGY CORP. | S | 14-0284 | 2015-04-01 | 4 | 5 | 4 | 4 | 3 | 4 | 3
ALEXANDER MITCHELL & SON | S | 14-0284 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0284 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0284 | 2015-04-01 | N/A | N/A | N/A | N/A | 3 | 3 | 3 | not yet onsite
DEMCO NEW YORK CORP. | S | 14-0284 | 2015-04-01 | 3 | 4 | 4 | 4 | 1 | 2 | 3 | The PM seems to be the primary source of issues.Not proactive
DESIGN SPECIALISTS INC. | S | 14-0284 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 14-0284 | 2015-04-01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Do not arrive on site per promised dates
E J CONSTRUCTION | S | 14-0284 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 14-0284 | 2015-04-01 | 3 | N/A | N/A | N/A | N/A | 4 | 4
GRANDPAS NURSERY Y GARDENS | S | 14-0284 | 2015-04-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 14-0284 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
JHP INDUSTRIAL SUPPLY | S | 14-0284 | 2015-04-01 | N/A | 1 | N/A | N/A | 1 | 1 | 1 | Totally unresponsive. Complete Negligance.
KAPPER LANDSCAPING INC. | S | 14-0284 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0284 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LEMOYNE INTERIORS, INC. | S | 14-0284 | 2015-04-01 | 5 | 5 | 5 | 5 | 4 | 4 | 4
MAC CONSTRUCTION CORP. | S | 14-0284 | 2015-04-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
NEW YORK STATE FENCE, INC | S | 14-0284 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PARKITECTS | S | 14-0284 | 2015-04-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5
PRO CARPET INC. | S | 14-0284 | 2015-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
RAULLI Y SONS, INC. | S | 14-0284 | 2015-04-01 | 3 | 2 | 4 | 4 | 4 | 4 | 3 | Rauli shows up on site when they want to and refuses to work with the teams schedule
SCHINDLER ELEVATOR | S | 14-0284 | 2015-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 2
US CEILING CORP. | S | 14-0284 | 2015-04-01 | 4 | 4 | 4 | 2 | 2 | 4 | 4
WOOD ETC., INC. | S | 14-0284 | 2015-04-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0284 | 2015-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.M. STERN, INC. | S | 14-0284 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | no longer onsite
ABJ FIRE PROTECTION CO. | S | 14-0284 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIRSIDE TECHNOLOGY CORP. | S | 14-0284 | 2015-05-01 | 4 | 5 | 4 | 4 | 3 | 4 | 3
ALEXANDER MITCHELL & SON | S | 14-0284 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0284 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0284 | 2015-05-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | not yet onsite
DEMCO NEW YORK CORP. | S | 14-0284 | 2015-05-01 | 3 | 4 | 4 | 4 | 1 | 2 | 3 | The PM seems to be the primary source of issues.Not proactive
DESIGN SPECIALISTS INC. | S | 14-0284 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRISCOLL MASONRY RESTORATION | S | 14-0284 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | no longer onsite
E J CONSTRUCTION | S | 14-0284 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 14-0284 | 2015-05-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
GRANDPAS NURSERY Y GARDENS | S | 14-0284 | 2015-05-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 14-0284 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
JHP INDUSTRIAL SUPPLY | S | 14-0284 | 2015-05-01 | N/A | 2 | 3 | N/A | 3 | 1 | 2 | Unresponsive. Complete Negligance.
KAPPER LANDSCAPING INC. | S | 14-0284 | 2015-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0284 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LEMOYNE INTERIORS, INC. | S | 14-0284 | 2015-05-01 | 5 | 5 | 5 | 5 | 4 | 4 | 4
MAC CONSTRUCTION CORP. | S | 14-0284 | 2015-05-01 | 5 | 4 | 5 | 3 | 3 | 3 | 3
NEW YORK STATE FENCE, INC | S | 14-0284 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PARKITECTS | S | 14-0284 | 2015-05-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5
PRO CARPET INC. | S | 14-0284 | 2015-05-01 | N/A | N/A | N/A | N/A | 4 | 4 | 4
RAULLI Y SONS, INC. | S | 14-0284 | 2015-05-01 | 3 | 2 | 4 | 4 | 4 | 4 | 3 | Rauli shows up on site when they want to and refuses to work with the teams schedule
SCHINDLER ELEVATOR | S | 14-0284 | 2015-05-01 | 5 | 5 | 5 | 5 | 4 | 4 | 3
US CEILING CORP. | S | 14-0284 | 2015-05-01 | 4 | 4 | 4 | 2 | 2 | 4 | 4
WOOD ETC., INC. | S | 14-0284 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0284 | 2015-05-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.M. STERN, INC. | S | 14-0284 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | no longer onsite
ABJ FIRE PROTECTION CO. | S | 14-0284 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIRSIDE TECHNOLOGY CORP. | S | 14-0284 | 2015-06-01 | 4 | 5 | 4 | 4 | 3 | 4 | 3
ALEXANDER MITCHELL & SON | S | 14-0284 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0284 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0284 | 2015-06-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3
DEMCO NEW YORK CORP. | S | 14-0284 | 2015-06-01 | 4 | 3 | 4 | 2 | 1 | 2 | 3 | never had enough manpower
DESIGN SPECIALISTS INC. | S | 14-0284 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DRISCOLL MASONRY RESTORATION | S | 14-0284 | 2015-06-01 | 4 | 2 | 2 | 3 | 2 | 3 | 3 | could have been more proactive with color matching
E J CONSTRUCTION | S | 14-0284 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 14-0284 | 2015-06-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
GRANDPAS NURSERY Y GARDENS | S | 14-0284 | 2015-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 14-0284 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
JHP INDUSTRIAL SUPPLY | S | 14-0284 | 2015-06-01 | N/A | 2 | 3 | N/A | 3 | 1 | 2 | Unresponsive. Complete Negligance.
KAPPER LANDSCAPING INC. | S | 14-0284 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0284 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LEMOYNE INTERIORS, INC. | S | 14-0284 | 2015-06-01 | 5 | 5 | 5 | 5 | 4 | 4 | 4
MAC CONSTRUCTION CORP. | S | 14-0284 | 2015-06-01 | 5 | 4 | 5 | 3 | 3 | 3 | 3
NEW YORK STATE FENCE, INC | S | 14-0284 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PARKITECTS | S | 14-0284 | 2015-06-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5
PRO CARPET INC. | S | 14-0284 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RAULLI Y SONS, INC. | S | 14-0284 | 2015-06-01 | 3 | 2 | 4 | 4 | 4 | 4 | 3 | Rauli shows up on site when they want to and refuses to work with the teams schedule
SCHINDLER ELEVATOR | S | 14-0284 | 2015-06-01 | 5 | 5 | 5 | 5 | 4 | 4 | 3
WOOD ETC., INC. | S | 14-0284 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0284 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
A.M. STERN, INC. | S | 14-0284 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | no longer onsite
ABJ FIRE PROTECTION CO. | S | 14-0284 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AIRSIDE TECHNOLOGY CORP. | S | 14-0284 | 2015-07-01 | 4 | 5 | 4 | 4 | 3 | 4 | 3
ALEXANDER MITCHELL & SON | S | 14-0284 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0284 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0284 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DEMCO NEW YORK CORP. | S | 14-0284 | 2015-07-01 | 4 | 3 | 4 | 2 | 1 | 2 | 3 | never had enough manpower- do not want to use again
DESIGN SPECIALISTS INC. | S | 14-0284 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
DRISCOLL MASONRY RESTORATION | S | 14-0284 | 2015-07-01 | 4 | 2 | 2 | 3 | 2 | 3 | 3 | could have been more proactive with color matching
E J CONSTRUCTION | S | 14-0284 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 14-0284 | 2015-07-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
GRANDPAS NURSERY Y GARDENS | S | 14-0284 | 2015-07-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY ISAACS HOME REMODELING | S | 14-0284 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
JHP INDUSTRIAL SUPPLY | S | 14-0284 | 2015-07-01 | N/A | 2 | 3 | N/A | 3 | 1 | 2 | unresponsive. Complete Negligance.
KAPPER LANDSCAPING INC. | S | 14-0284 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 14-0284 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LEMOYNE INTERIORS, INC. | S | 14-0284 | 2015-07-01 | 5 | 5 | 5 | 5 | 4 | 4 | 4
MAC CONSTRUCTION CORP. | S | 14-0284 | 2015-07-01 | 5 | 4 | 5 | 3 | 3 | 3 | 3 | high quality work
NEW YORK STATE FENCE, INC | S | 14-0284 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PARKITECTS | S | 14-0284 | 2015-07-01 | N/A | N/A | N/A | N/A | 5 | 5 | 5
PRO CARPET INC. | S | 14-0284 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RAULLI Y SONS, INC. | S | 14-0284 | 2015-07-01 | 3 | 2 | 4 | 4 | 4 | 4 | 3 | Rauli shows up on site when they want to and refuses to work with the teams schedule
SCHINDLER ELEVATOR | S | 14-0284 | 2015-07-01 | 5 | 5 | 5 | 5 | 4 | 4 | 3
WOOD ETC., INC. | S | 14-0284 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 14-0284 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACQUATIC LANDSCAPING | S | 13-0276 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | took their scores off until they get back on site
Carpet Tech | S | 13-0276 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Designer Tops | S | 13-0276 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Finy Sales | S | 13-0276 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRE PAK | S | 13-0276 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
GOMEZ & SONS | S | 13-0276 | 2015-01-01 | 5 | 5 | 4 | 4 | 4 | N/A | 4 | No longer on site
Lace | S | 13-0276 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEISNER | S | 13-0276 | 2015-01-01 | 5 | 5 | 4 | 4 | 4 | 4 | 4
OHL | S | 13-0276 | 2015-01-01 | 3 | 1 | 2 | 1 | 2 | 2 | 2 | Has a hard time following a schedule including their own.
PARAMOUNT | S | 13-0276 | 2015-01-01 | 4 | 3 | 4 | 4 | N/A | 3 | 3
Pena-Alum | S | 13-0276 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOLUTIONS | S | 13-0276 | 2015-01-01 | 4 | 3 | 3 | 4 | 4 | 4 | 3 | Sub has a hard time following a schedule- there has been an improvement in schedule management
SOUTHERN COAST ROOFING | S | 13-0276 | 2015-01-01 | 4 | 4 | 4 | 4 | 3 | 3 | 4
SPI | S | 13-0276 | 2015-01-01 | 4 | 4 | 3 | 4 | 3 | 3 | 4
STATE LINE PRODUCTS | S | 13-0276 | 2015-01-01 | 5 | 5 | 5 | 5 | N/A | 3 | 4
STEEL FAB | S | 13-0276 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Tempo | S | 13-0276 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TROPIC | S | 13-0276 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
Unicorn | S | 13-0276 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Vassell | S | 13-0276 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Viviano | S | 13-0276 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILDCAT | S | 13-0276 | 2015-01-01 | 3 | 1 | 2 | 2 | N/A | N/A | 1 | Wildcat waited too long to staff up. Would not use this sub again.
Y&T | S | 13-0276 | 2015-01-01 | 5 | 5 | 4 | 4 | 4 | 4 | 4
ACQUATIC LANDSCAPING | S | 13-0276 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | took their scores off until they get back on site
Carpet Tech | S | 13-0276 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Designer Tops | S | 13-0276 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Finy Sales | S | 13-0276 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRE PAK | S | 13-0276 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
GOMEZ & SONS | S | 13-0276 | 2015-02-01 | 5 | 5 | 4 | 4 | 4 | N/A | 4 | No longer on site
Lace | S | 13-0276 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEISNER | S | 13-0276 | 2015-02-01 | 5 | 5 | 4 | 4 | 4 | 4 | 4
OHL | S | 13-0276 | 2015-02-01 | 3 | 1 | 2 | 1 | 2 | 2 | 2 | Has a hard time following a schedule including their own.
PARAMOUNT | S | 13-0276 | 2015-02-01 | 4 | 3 | 4 | 4 | N/A | 3 | 3
Pena-Alum | S | 13-0276 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOLUTIONS | S | 13-0276 | 2015-02-01 | 4 | 3 | 3 | 4 | 4 | 4 | 3 | Sub has a hard time following a schedule- there has been an improvement in schedule management
SOUTHERN COAST ROOFING | S | 13-0276 | 2015-02-01 | 4 | 4 | 4 | 4 | 3 | 3 | 4
SPI | S | 13-0276 | 2015-02-01 | 4 | 4 | 3 | 4 | 3 | 3 | 4
STATE LINE PRODUCTS | S | 13-0276 | 2015-02-01 | 5 | 5 | 5 | 5 | N/A | 3 | 4
STEEL FAB | S | 13-0276 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Tempo | S | 13-0276 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TROPIC | S | 13-0276 | 2015-02-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
Unicorn | S | 13-0276 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Vassell | S | 13-0276 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Viviano | S | 13-0276 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILDCAT | S | 13-0276 | 2015-02-01 | 3 | 1 | 2 | 2 | N/A | N/A | 1 | Wildcat waited too long to staff up. Would not use this sub again.
Y&T | S | 13-0276 | 2015-02-01 | 5 | 5 | 4 | 4 | 4 | 4 | 4
ACQUATIC LANDSCAPING | S | 13-0276 | 2015-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | took their scores off until they get back on site
Carpet Tech | S | 13-0276 | 2015-08-28 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Designer Tops | S | 13-0276 | 2015-08-28 | 5 | 5 | 5 | 4 | 4 | 5 | 5
Finy Sales | S | 13-0276 | 2015-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRE PAK | S | 13-0276 | 2015-08-28 | 4 | 3 | 4 | 3 | 4 | 4 | 4
GOMEZ & SONS | S | 13-0276 | 2015-08-28 | 5 | 5 | 4 | 4 | 4 | N/A | 4 | No longer on site
Lace | S | 13-0276 | 2015-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEISNER | S | 13-0276 | 2015-08-28 | 5 | 5 | 4 | 4 | 4 | 4 | 4
OHL | S | 13-0276 | 2015-08-28 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | Has a hard time following a schedule including their own.
PARAMOUNT | S | 13-0276 | 2015-08-28 | 4 | 5 | 4 | 4 | N/A | 3 | 3
Pena-Alum | S | 13-0276 | 2015-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOLUTIONS | S | 13-0276 | 2015-08-28 | 4 | 3 | 3 | 4 | 4 | 4 | 3 | Sub has a hard time following a schedule- there has been an improvement in schedule management
SOUTHERN COAST ROOFING | S | 13-0276 | 2015-08-28 | 4 | 4 | 4 | 4 | 3 | 3 | 4
SPI | S | 13-0276 | 2015-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STATE LINE PRODUCTS | S | 13-0276 | 2015-08-28 | 5 | 5 | 5 | 5 | N/A | 3 | 4
STEEL FAB | S | 13-0276 | 2015-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Tempo | S | 13-0276 | 2015-08-28 | 5 | 5 | 4 | 4 | 4 | 5 | 5
TROPIC | S | 13-0276 | 2015-08-28 | 4 | 3 | 4 | N/A | N/A | 3 | 4
Unicorn | S | 13-0276 | 2015-08-28 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Vassell | S | 13-0276 | 2015-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Viviano | S | 13-0276 | 2015-08-28 | 5 | 5 | 5 | 5 | 5 | 5 | 5
WILDCAT | S | 13-0276 | 2015-08-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Y&T | S | 13-0276 | 2015-08-28 | 5 | 3 | 3 | 2 | 3 | 3 | 4
ACQUATIC LANDSCAPING | S | 13-0276 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | took their scores off until they get back on site
Carpet Tech | S | 13-0276 | 2015-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Designer Tops | S | 13-0276 | 2015-06-01 | 5 | 5 | 5 | 4 | 4 | 5 | 5
Finy Sales | S | 13-0276 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIRE PAK | S | 13-0276 | 2015-06-01 | 4 | 3 | 4 | 3 | 4 | 4 | 4
GOMEZ & SONS | S | 13-0276 | 2015-06-01 | 5 | 5 | 4 | 4 | 4 | N/A | 4 | No longer on site
Lace | S | 13-0276 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEISNER | S | 13-0276 | 2015-06-01 | 5 | 5 | 4 | 4 | 4 | 4 | 4
OHL | S | 13-0276 | 2015-06-01 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | Has a hard time following a schedule including their own.
PARAMOUNT | S | 13-0276 | 2015-06-01 | 4 | 5 | 4 | 4 | N/A | 3 | 3
Pena-Alum | S | 13-0276 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOLUTIONS | S | 13-0276 | 2015-06-01 | 4 | 3 | 3 | 4 | 4 | 4 | 3 | Sub has a hard time following a schedule- there has been an improvement in schedule management
SOUTHERN COAST ROOFING | S | 13-0276 | 2015-06-01 | 4 | 4 | 4 | 4 | 3 | 3 | 4
SPI | S | 13-0276 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Off site
STATE LINE PRODUCTS | S | 13-0276 | 2015-06-01 | 5 | 5 | 5 | 5 | N/A | 3 | 4
STEEL FAB | S | 13-0276 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Tempo | S | 13-0276 | 2015-06-01 | 5 | 5 | 4 | 4 | 4 | 5 | 5
TROPIC | S | 13-0276 | 2015-06-01 | 4 | 3 | 4 | 3 | N/A | 3 | 4
Unicorn | S | 13-0276 | 2015-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Vassell | S | 13-0276 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Viviano | S | 13-0276 | 2015-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
WILDCAT | S | 13-0276 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Y&T | S | 13-0276 | 2015-06-01 | 5 | 3 | 3 | 2 | 3 | 3 | 4
ARCI, LTD. | S | 13-0273 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 13-0273 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BARFIELD FENCE & WALL | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BARFIELD FENCE Y FABRICATION | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
BERGERON FRAMING | S | 13-0273 | 2015-01-01 | 3 | 4 | 4 | 4 | N/A | 3 | 4
BERGERON FRAMING - MATERIALS | S | 13-0273 | 2015-01-01 | N/A | 3 | 4 | N/A | N/A | 3 | 3
BERMAN PROPERTY MAINTENANCE Y CONSTRUCTION | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRANT & SON | S | 13-0273 | 2015-01-01 | 3 | 4 | 3 | 4 | N/A | 3 | N/A
CABLE ELECTRICAL SERVICES | S | 13-0273 | 2015-01-01 | 3 | 4 | 4 | 4 | 4 | 3 | 3
CENTRAL FLORIDA SAFETY | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DELACRUZ DRYWALL PLASTERING | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | 2 | 1 | This contractor has been put on notice several times to submit contract and they have not
DRMP INC | S | 13-0273 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 2 | this sub has a new scheduler and this will hopefully help with the scheduling issues.
EAST COAST POURED FLOORS | S | 13-0273 | 2015-01-01 | 2 | 3 | 4 | 4 | N/A | 4 | 3
EVOLUTION POOLS & CONSTRUCTION SERVICES, INC. | S | 13-0273 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLORIDA DOOR SOLUTIONS | S | 13-0273 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
FOX WINDOWS | S | 13-0273 | 2015-01-01 | 4 | 3 | 4 | 4 | N/A | 3 | 3
G&L EXTERIORS | S | 13-0273 | 2015-01-01 | 3 | 4 | 4 | 4 | N/A | 3 | 3
GULF COAST PLUMBING | S | 13-0273 | 2015-01-01 | 4 | 4 | 5 | 4 | 5 | 5 | 4
HAVEN CONTRACTING, INC | S | 13-0273 | 2015-01-01 | 3 | 4 | 4 | 3 | 4 | 3 | 3 | field workers are very good
JEL SITE DEVELOPMENT INC. | S | 13-0273 | 2015-01-01 | 4 | 4 | 3 | 3 | 2 | 4 | 3 | Small operation, apparently capable of doing this but were perform well so far
JL WILSON CONCRETE, INC. | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
KISSIMMEE CONSTRUCTION | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MALIBU FLOORS | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
MASSEY SERVICES | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MASTER WOOD CRAFT CABINETRY | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | 4 | 3 | 3
PRECISION GUTTERS | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
REW LANDSCAPE | S | 13-0273 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SHADES TO YOU | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
SIMPSON ENVIRONMENTAL | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUSA CABINETS | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STONE INSTALLATION | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUNBELT GATED ACCESS SYSTEMS | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE LUCKHARDT GROUP | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0273 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
TRUSSWAY MFG. | S | 13-0273 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNICORN PAINTING INC. | S | 13-0273 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNIVERSAL BUILDING SUPPLY | S | 13-0273 | 2015-01-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNIVERSAL ENGINEERING SCIENCES | S | 13-0273 | 2015-01-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
VALUE LIGHTING | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | 4 | 3 | 4
WALL AND SIGN CONCEPTS | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WATERWATCH CORPORATION | S | 13-0273 | 2015-01-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WAYNE AUTOMATIC SPRINKLERS | S | 13-0273 | 2015-01-01 | 4 | 4 | 5 | 3 | N/A | 3 | 4
WHIRLPOOL CORPORATION | S | 13-0273 | 2015-01-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
ARCI, LTD. | S | 13-0273 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 13-0273 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BARFIELD FENCE & WALL | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BARFIELD FENCE Y FABRICATION | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
BERGERON FRAMING | S | 13-0273 | 2015-02-01 | 3 | 4 | 4 | 4 | N/A | 3 | 4
BERGERON FRAMING - MATERIALS | S | 13-0273 | 2015-02-01 | N/A | 3 | 4 | N/A | N/A | 3 | 3
BERMAN PROPERTY MAINTENANCE Y CONSTRUCTION | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRANT & SON | S | 13-0273 | 2015-02-01 | 3 | 4 | 3 | 4 | N/A | 3 | N/A
CABLE ELECTRICAL SERVICES | S | 13-0273 | 2015-02-01 | 3 | 4 | 4 | 4 | 4 | 3 | 3
CENTRAL FLORIDA SAFETY | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DELACRUZ DRYWALL PLASTERING | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | 2 | 1 | This contractor has been put on notice several times to submit contract and they have not
DRMP INC | S | 13-0273 | 2015-02-01 | 4 | 4 | 4 | 4 | N/A | N/A | 2 | this sub has a new scheduler and this will hopefully help with the scheduling issues.
EAST COAST POURED FLOORS | S | 13-0273 | 2015-02-01 | 2 | 3 | 4 | 4 | N/A | 4 | 3
EVOLUTION POOLS & CONSTRUCTION SERVICES, INC. | S | 13-0273 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLORIDA DOOR SOLUTIONS | S | 13-0273 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4
FOX WINDOWS | S | 13-0273 | 2015-02-01 | 4 | 3 | 4 | 4 | N/A | 3 | 3
G&L EXTERIORS | S | 13-0273 | 2015-02-01 | 3 | 4 | 4 | 4 | N/A | 3 | 3
GULF COAST PLUMBING | S | 13-0273 | 2015-02-01 | 4 | 4 | 5 | 4 | 5 | 5 | 4
HAVEN CONTRACTING, INC | S | 13-0273 | 2015-02-01 | 3 | 4 | 4 | 3 | 4 | 3 | 3 | field workers are very good
JEL SITE DEVELOPMENT INC. | S | 13-0273 | 2015-02-01 | 4 | 4 | 3 | 3 | 2 | 4 | 3 | Small operation, apparently capable of doing this but were perform well so far
JL WILSON CONCRETE, INC. | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | 3 | 4
KISSIMMEE CONSTRUCTION | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MALIBU FLOORS | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
MASSEY SERVICES | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MASTER WOOD CRAFT CABINETRY | S | 13-0273 | 2015-02-01 | N/A | 2 | 2 | N/A | 2 | 2 | 2
PRECISION GUTTERS | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | 3 | 3
REW LANDSCAPE | S | 13-0273 | 2015-02-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SHADES TO YOU | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
SIMPSON ENVIRONMENTAL | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOUSA CABINETS | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STONE INSTALLATION | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUNBELT GATED ACCESS SYSTEMS | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE LUCKHARDT GROUP | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THYSSENKRUPP ELEVATOR | S | 13-0273 | 2015-02-01 | 4 | 4 | 4 | 4 | N/A | 3 | 4
TRUSSWAY MFG. | S | 13-0273 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNICORN PAINTING INC. | S | 13-0273 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNIVERSAL BUILDING SUPPLY | S | 13-0273 | 2015-02-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
UNIVERSAL ENGINEERING SCIENCES | S | 13-0273 | 2015-02-01 | 4 | 4 | 4 | 4 | N/A | N/A | 4
VALUE LIGHTING | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | 4 | 3 | 4
WALL AND SIGN CONCEPTS | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WATERWATCH CORPORATION | S | 13-0273 | 2015-02-01 | N/A | N/A | N/A | N/A | N/A | 4 | 4
WAYNE AUTOMATIC SPRINKLERS | S | 13-0273 | 2015-02-01 | 4 | 4 | 5 | 3 | N/A | 3 | 4
WHIRLPOOL CORPORATION | S | 13-0273 | 2015-02-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
104 CONTRACTORS INC. | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0305 | 2015-09-01 | 4 | 4 | 4 | 4 | N/A | 4 | 3
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2015-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACPRODUCTS, INC | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | supplier
AIIA CONSTRUCTION COMPANY, INC | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIED MECHANICAL | S | 15-0305 | 2015-09-01 | 4 | 5 | 4 | 5 | 3 | 3 | 3
ALPHA IRON WORKS, LLC | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BALTZ CONCRETE CONST., INC | S | 15-0305 | 2015-09-01 | 5 | 5 | 4 | 4 | 5 | N/A | 5
BILLONE MECHANICAL CONTRACTORS | S | 15-0305 | 2015-09-01 | 5 | 5 | 4 | 4 | N/A | 5 | 5
BUFFALO CONCRETE ACCESSORIES | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAPITIAL FENCE CO., INC | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATALANO CONTRACTING, INC | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DESIGN POOL & SPA LTD. | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENERGY INSULATION SYSTEMS, INC | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FISHER CONCRETE, INC | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J Y R SPECIALITIES, INC | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2015-09-01 | 5 | 5 | 4 | 4 | 3 | 2 | 2 | Office is difficult to work with
KLEIN REINFORCING SERVICES | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.J. QUIGLIANO | S | 15-0305 | 2015-09-01 | 4 | 5 | 5 | 5 | 2 | 2 | 4
MAX T. DOLAND | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS & PANEL (PANELS) | S | 15-0305 | 2015-09-01 | 5 | 5 | 5 | 5 | N/A | 4 | 5
ONTARIO EXTERIORS, INC | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PASSERO ASSOCIATES | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2015-09-01 | 4 | 2 | 4 | 2 | 3 | 2 | 3
S.A.B. SPECIALTIES | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNITED MATERIALS, LLC | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 15-0305 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 CONTRACTORS INC. | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0305 | 2015-10-01 | 4 | 4 | 4 | 4 | N/A | 4 | 3
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2015-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACPRODUCTS, INC | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIED MECHANICAL | S | 15-0305 | 2015-10-01 | 4 | 5 | 4 | 5 | 3 | 3 | 3
ALPHA IRON WORKS, LLC | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BALTZ CONCRETE CONST., INC | S | 15-0305 | 2015-10-01 | 5 | 3 | 5 | 5 | 5 | N/A | 5
BILLONE MECHANICAL CONTRACTORS | S | 15-0305 | 2015-10-01 | 5 | 5 | 4 | 4 | N/A | 5 | 5
BUFFALO CONCRETE ACCESSORIES | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAPITIAL FENCE CO., INC | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATALANO CONTRACTING, INC | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DESIGN POOL & SPA LTD. | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENERGY INSULATION SYSTEMS, INC | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FISHER CONCRETE, INC | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GYPSUM SYSTEMS, INC. | S | 15-0305 | 2015-10-01 | 5 | 5 | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J Y R SPECIALITIES, INC | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2015-10-01 | 5 | 5 | 4 | 4 | 3 | 2 | 2
KLEIN REINFORCING SERVICES | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.J. QUIGLIANO | S | 15-0305 | 2015-10-01 | 4 | 5 | 5 | 5 | 2 | 2 | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS & PANEL (PANELS) | S | 15-0305 | 2015-10-01 | 5 | 5 | 5 | 5 | N/A | 4 | N/A
ONTARIO EXTERIORS, INC | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PASSERO ASSOCIATES | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2015-10-01 | 4 | 2 | 4 | 2 | 3 | 2 | 3
S.A.B. SPECIALTIES | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNITED MATERIALS, LLC | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 15-0305 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 CONTRACTORS INC. | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0305 | 2015-11-01 | 1 | 2 | 2 | 2 | N/A | 2 | 2
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2015-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACPRODUCTS, INC | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIED MECHANICAL | S | 15-0305 | 2015-11-01 | 4 | 5 | 4 | 5 | 3 | 3 | 3
ALPHA IRON WORKS, LLC | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BALTZ CONCRETE CONST., INC | S | 15-0305 | 2015-11-01 | 5 | 3 | 5 | 5 | 5 | N/A | 5 | Excellent Safety.
BILLONE MECHANICAL CONTRACTORS | S | 15-0305 | 2015-11-01 | 5 | 5 | 4 | 3 | N/A | 5 | N/A
BUFFALO CONCRETE ACCESSORIES | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAPITIAL FENCE CO., INC | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATALANO CONTRACTING, INC | S | 15-0305 | 2015-11-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0305 | 2015-11-01 | 5 | 4 | 4 | 4 | N/A | 4 | 4
DESIGN POOL & SPA LTD. | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENERGY INSULATION SYSTEMS, INC | S | 15-0305 | 2015-11-01 | 4 | 2 | 3 | 1 | N/A | 4 | 4 | not enough manpower
FISHER CONCRETE, INC | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GYPSUM SYSTEMS, INC. | S | 15-0305 | 2015-11-01 | 4 | 5 | 5 | 4 | N/A | 3 | 3
HENDERSON-JOHNSON CO.INC. | S | 15-0305 | 2015-11-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY E ISAACS QUALITY HOME | S | 15-0305 | 2015-11-01 | 4 | 4 | 4 | 3 | 4 | 4 | 4
J Y R SPECIALITIES, INC | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2015-11-01 | 5 | 5 | 4 | 4 | 3 | 2 | 2 | Office is difficult to work with
KLEIN REINFORCING SERVICES | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.J. QUIGLIANO | S | 15-0305 | 2015-11-01 | 4 | 5 | 5 | 5 | 2 | 2 | 4
LAKEVIEW LAWN & LANDSCAPE | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MIG BUILDING SYSTEMS | S | 15-0305 | 2015-11-01 | 4 | 3 | 3 | 2 | 4 | 3 | 3
MONTGOMERY TRUSS & PANEL (PANELS) | S | 15-0305 | 2015-11-01 | 5 | 5 | 5 | 5 | N/A | 4 | 5
ONTARIO EXTERIORS, INC | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PASSERO ASSOCIATES | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2015-11-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | improved schedule and manpower when asked; they were very willing to work with the team
S.A.B. SPECIALTIES | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNITED MATERIALS, LLC | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 15-0305 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0307 | 2015-09-30 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACCURATE ACOUSTICAL, INC. | S | 15-0307 | 2015-09-30 | 4 | 3 | 3 | 4 | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0307 | 2015-09-30 | N/A | 3 | 4 | N/A | N/A | 3 | 3
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 15-0307 | 2015-09-30 | 4 | 4 | 4 | 4 | 4 | 4 | 4
GENEVA GLASS CENTER | S | 15-0307 | 2015-09-30 | 4 | 3 | 5 | 4 | N/A | 4 | 4
MAX T. DOLAND | S | 15-0307 | 2015-09-30 | N/A | 5 | 5 | N/A | N/A | 3 | 4
MILLCO WOODWORKING, LLC | S | 15-0307 | 2015-09-30 | 4 | 4 | 4 | 4 | 4 | 4 | 4
POSTLER & JAECKLE CORP. | S | 15-0307 | 2015-09-30 | 3 | 2 | 3 | 2 | 4 | 4 | 4
PRO CARPET INC. | S | 15-0307 | 2015-09-30 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 15-0307 | 2015-09-30 | 4 | 4 | 4 | 4 | 4 | 4 | 4
THE PIKE COMPANY | S | 15-0307 | 2015-09-30 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 15-0307 | 2015-09-30 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
B&L WHOLESALE | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | 4 | 3 | N/A
BENEDETTI BUILDERS | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
BSR | S | 14-0289 | 2015-07-01 | 3 | 3 | 3 | 2 | 3 | 3 | 3
CATENARY CONSTRUCTION CORP. | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAYUGA LANDSCAPE | S | 14-0289 | 2015-07-01 | 3 | 4 | 3 | 4 | 2 | 2 | 4
COMFORT SYSTEMS (SYRACUSE) | S | 14-0289 | 2015-07-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
D & R JONES CONSTRUCTION | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | 3 | 4 | 4
EZ WAY | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0289 | 2015-07-01 | N/A | 2 | N/A | N/A | N/A | 2 | 2 | Do not know their scope
GERHARZ EQUIPMENT | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
INNOVATIVE WINDOWEAR | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOHN C. LOWERY | S | 14-0289 | 2015-07-01 | 4 | 4 | 4 | 3 | N/A | N/A | N/A
KELLY BROS. | S | 14-0289 | 2015-07-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 14-0289 | 2015-07-01 | 4 | N/A | N/A | N/A | 2 | 2 | 2
LEMOYNE INTERIORS, INC. | S | 14-0289 | 2015-07-01 | 4 | 4 | N/A | 4 | N/A | 3 | 4
LRS COMPANIES | S | 14-0289 | 2015-07-01 | 2 | 2 | 4 | 3 | 2 | 4 | 2 | Safety isnt a priority for them; lack of man power
MCPHERSON BUILDERS | S | 14-0289 | 2015-07-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3
MOD SPACE | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | 1 | 1 | Unresponsive office
NATIONAL LUMBER | S | 14-0289 | 2015-07-01 | 2 | 3 | 3 | 2 | N/A | 4 | N/A
PLEASANT VALLEY ELEC. | S | 14-0289 | 2015-07-01 | 4 | 4 | 4 | 5 | 4 | 4 | N/A
PREMIER UTILITY SVC. | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
RADEC CORPORATION | S | 14-0289 | 2015-07-01 | 4 | 3 | 4 | 4 | 3 | 2 | 2 | piecemeal submittals; unorganized and incomplete; not following 3wk schedule
RAULLI Y SONS, INC. | S | 14-0289 | 2015-07-01 | 3 | 3 | 3 | 4 | 3 | 2 | 2
SCHINDLER ELEVATOR | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
TG MILLER | S | 14-0289 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Layout only
THE BRAIN DRAIN | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 14-0289 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2015-07-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 15-0303 | 2015-08-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2015-08-06 | 4 | 3 | 4 | 4 | 4 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2015-08-06 | 4 | 2 | N/A | N/A | N/A | N/A | 2 | Poor communication, not returning phone calls or emails
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2015-08-06 | 4 | 4 | 4 | 4 | 4 | 3 | 3
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2015-08-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2015-08-06 | 4 | 2 | 4 | 4 | 4 | 4 | 4 | only concerned with their own work
ES SYSTEMS, INC | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GROVER & BATES ASSOCIATES | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0303 | 2015-08-06 | 4 | 3 | 4 | 4 | N/A | N/A | 4
RAULLI Y SONS, INC. | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHULER-HAAS | S | 15-0303 | 2015-08-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Great foreman- easy to work with- great communication
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILLIAM L. WATSON | S | 15-0303 | 2015-08-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0303 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2015-07-01 | N/A | 2 | N/A | N/A | N/A | N/A | 2 | Poor communication, not returning phone calls or emails
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 3 | 3
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | very good- very proactive
ES SYSTEMS, INC | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GROVER & BATES ASSOCIATES | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2015-07-01 | N/A | 1 | 3 | 1 | 1 | 1 | 1 | Very poor communication- unacceptable with delivery dates, submittals, lead time- will never use again
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0303 | 2015-07-01 | 4 | 3 | 4 | 4 | N/A | N/A | 4
RAULLI Y SONS, INC. | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHULER-HAAS | S | 15-0303 | 2015-07-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Great foreman- easy to work with- great communication
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILLIAM L. WATSON | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GROVER & BATES ASSOCIATES | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0303 | 2015-07-01 | 4 | 3 | 4 | 4 | N/A | N/A | 4
RAULLI Y SONS, INC. | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHULER-HAAS | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILLIAM L. WATSON | S | 15-0303 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0303 | 2015-09-03 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2015-09-03 | 4 | 3 | 4 | 4 | 4 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2015-09-03 | 4 | 2 | N/A | N/A | N/A | N/A | 2 | Poor communication, not returning phone calls or emails
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2015-09-03 | 4 | 4 | 4 | 4 | 4 | 3 | 3
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2015-09-03 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | 2 | unresponsive
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2015-09-03 | 4 | 2 | 4 | 4 | 4 | 4 | 4 | only concerned with their own work
ES SYSTEMS, INC | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GROVER & BATES ASSOCIATES | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | 4 | 4
RADEC CORPORATION | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2015-09-03 | 4 | 3 | 4 | 4 | N/A | 3 | 3
SCHULER-HAAS | S | 15-0303 | 2015-09-03 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Great foreman- easy to work with- great communication
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0303 | 2015-09-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
B&L WHOLESALE | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
BENEDETTI BUILDERS | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
BSR | S | 14-0289 | 2015-09-01 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | office over-promises
CATENARY CONSTRUCTION CORP. | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAYUGA LANDSCAPE | S | 14-0289 | 2015-09-01 | 3 | 4 | 3 | 4 | 3 | 1 | 4
COMFORT SYSTEMS (SYRACUSE) | S | 14-0289 | 2015-09-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
D & R JONES CONSTRUCTION | S | 14-0289 | 2015-09-01 | 3 | 1 | 3 | 1 | 3 | 4 | 2 | do not provide adequate manpower
EZ WAY | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0289 | 2015-09-01 | 2 | 1 | 2 | 3 | N/A | 2 | 2 | Do not know their scope; Having issues with the PM - Mark Webster
GERHARZ EQUIPMENT | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
INNOVATIVE WINDOWEAR | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOHN C. LOWERY | S | 14-0289 | 2015-09-01 | 4 | 4 | 4 | 3 | 3 | 4 | 3
KELLY BROS. | S | 14-0289 | 2015-09-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 14-0289 | 2015-09-01 | 3 | 4 | 4 | 4 | 2 | 3 | 2
LEMOYNE INTERIORS, INC. | S | 14-0289 | 2015-09-01 | 4 | 4 | 3 | 4 | 2 | 3 | 4
LRS COMPANIES | S | 14-0289 | 2015-09-01 | 2 | 3 | 4 | 3 | 4 | 4 | 4 | Safety isnt a priority for them; lack of man power
MCPHERSON BUILDERS | S | 14-0289 | 2015-09-01 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | Very reliable
MOD SPACE | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | 1 | 1 | Unresponsive office
NATIONAL LUMBER | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | offsite
PLEASANT VALLEY ELEC. | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER UTILITY SVC. | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0289 | 2015-09-01 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | pedal for T
RADEC CORPORATION | S | 14-0289 | 2015-09-01 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | piecemeal submittals; unorganized and incomplete; not following 3wk schedule
RAULLI Y SONS, INC. | S | 14-0289 | 2015-09-01 | 4 | 4 | 4 | 4 | N/A | 4 | 5
SCHINDLER ELEVATOR | S | 14-0289 | 2015-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SHEPARDVILLE |  | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TG MILLER | S | 14-0289 | 2015-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Layout only
THE BRAIN DRAIN | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 14-0289 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2015-09-01 | 4 | 3 | 4 | 5 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BENEDETTI BUILDERS | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSR | S | 14-0289 | 2015-12-04 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | office over-promises
CATENARY CONSTRUCTION CORP. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAYUGA LANDSCAPE | S | 14-0289 | 2015-12-04 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0289 | 2015-12-04 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
D & R JONES CONSTRUCTION | S | 14-0289 | 2015-12-04 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | do not provide adequate manpower
EZ WAY | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0289 | 2015-12-04 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | Do not know their scope; Having issues with the PM - Mark Webster
GERHARZ EQUIPMENT | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
INNOVATIVE WINDOWEAR | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOHN C. LOWERY | S | 14-0289 | 2015-12-04 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
KELLY BROS. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0289 | 2015-12-04 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
LEMOYNE INTERIORS, INC. | S | 14-0289 | 2015-12-04 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
LRS COMPANIES | S | 14-0289 | 2015-12-04 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | Safety isnt a priority for them; lack of man power
MCPHERSON BUILDERS | S | 14-0289 | 2015-12-04 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | Very reliable
MOD SPACE | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Unresponsive office
NATIONAL LUMBER | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | offsite
PLEASANT VALLEY ELEC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER UTILITY SVC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0289 | 2015-12-04 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | pedal for T
RADEC CORPORATION | S | 14-0289 | 2015-12-04 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | piecemeal submittals; unorganized and incomplete; not following 3wk schedule
RAULLI Y SONS, INC. | S | 14-0289 | 2015-12-04 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0289 | 2015-12-04 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE |  | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TG MILLER | S | 14-0289 | 2015-12-04 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | Layout only
THE BRAIN DRAIN | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2015-12-04 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BENEDETTI BUILDERS | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSR | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAYUGA LANDSCAPE | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D & R JONES CONSTRUCTION | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EZ WAY | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GERHARZ EQUIPMENT | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
INNOVATIVE WINDOWEAR | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOHN C. LOWERY | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLY BROS. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.A.PAINTING, INC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LEMOYNE INTERIORS, INC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRS COMPANIES | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MCPHERSON BUILDERS | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MOD SPACE | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL LUMBER | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLEASANT VALLEY ELEC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER UTILITY SVC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE |  | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TG MILLER | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE BRAIN DRAIN | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2015-12-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0303 | 2015-10-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2015-10-08 | 4 | 3 | 4 | 4 | 4 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2015-10-08 | 4 | 2 | N/A | N/A | N/A | N/A | 2 | Poor communication, not returning phone calls or emails
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2015-10-08 | 4 | 4 | 4 | 4 | 4 | 3 | 3
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2015-10-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2015-10-08 | 4 | 2 | 4 | 4 | 2 | 4 | 2 | unresponsive
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2015-10-08 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | only concerned with their own work
ES SYSTEMS, INC | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GROVER & BATES ASSOCIATES | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | 4 | 4
RADEC CORPORATION | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2015-10-08 | 4 | 3 | 4 | 4 | 2 | 3 | 2 | slow to respond to COs
SCHULER-HAAS | S | 15-0303 | 2015-10-08 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Great foreman- easy to work with- great communication
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0303 | 2015-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0303 | 2015-11-05 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2015-11-05 | 4 | 2 | N/A | N/A | N/A | N/A | 2 | Poor communication, not returning phone calls or emails
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2015-11-05 | 4 | 2 | 4 | 3 | 4 | 3 | 3
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2015-11-05 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2015-11-05 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | unresponsive
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2015-11-05 | 4 | 2 | 4 | 4 | 4 | 4 | 4 | only concerned with their own work
ES SYSTEMS, INC | S | 15-0303 | 2015-11-05 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | 2 | 2
GROVER & BATES ASSOCIATES | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | Buffalo office
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0303 | 2015-11-05 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | offsite
RAULLI Y SONS, INC. | S | 15-0303 | 2015-11-05 | 4 | 4 | 4 | 4 | 3 | 3 | 4
SCHULER-HAAS | S | 15-0303 | 2015-11-05 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | Great foreman- easy to work with- great communication
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILLIAM L. WATSON | S | 15-0303 | 2015-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | 4 | 3
BENEDETTI BUILDERS | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSR | S | 14-0289 | 2015-10-01 | 3 | 3 | 3 | 2 | 3 | 3 | 3
CATENARY CONSTRUCTION CORP. | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAYUGA LANDSCAPE | S | 14-0289 | 2015-10-01 | 3 | 4 | 3 | 4 | 3 | 2 | 4
COMFORT SYSTEMS (SYRACUSE) | S | 14-0289 | 2015-10-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
D & R JONES CONSTRUCTION | S | 14-0289 | 2015-10-01 | 3 | 3 | 3 | 1 | 3 | 4 | 2 | do not provide adequate manpower but provided it after veing pushed
EZ WAY | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0289 | 2015-10-01 | 2 | 1 | 3 | 3 | N/A | 2 | 2 | Do not know their scope; Having issues with the PM - Mark Webster
GERHARZ EQUIPMENT | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0289 | 2015-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
INNOVATIVE WINDOWEAR | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOHN C. LOWERY | S | 14-0289 | 2015-10-01 | 4 | 4 | 4 | 3 | 3 | 4 | 3
KELLY BROS. | S | 14-0289 | 2015-10-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 14-0289 | 2015-10-01 | 3 | 4 | 4 | 4 | 2 | 3 | 2
LEMOYNE INTERIORS, INC. | S | 14-0289 | 2015-10-01 | 4 | 4 | 4 | 4 | 2 | 3 | 4
LRS COMPANIES | S | 14-0289 | 2015-10-01 | 2 | 3 | 4 | 3 | 4 | 4 | 4
MCPHERSON BUILDERS | S | 14-0289 | 2015-10-01 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | Very reliable
MOD SPACE | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL LUMBER | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLEASANT VALLEY ELEC. | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER UTILITY SVC. | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0289 | 2015-10-01 | 3 | 3 | 3 | 2 | 3 | 4 | 3 | pedal for TM tickets
RADEC CORPORATION | S | 14-0289 | 2015-10-01 | 4 | 3 | 4 | 4 | 3 | 2 | 3 | piecemeal submittals; unorganized and incomplete; not following 3wk schedule
RAULLI Y SONS, INC. | S | 14-0289 | 2015-10-01 | 4 | 4 | 4 | 4 | N/A | 4 | 5
SCHINDLER ELEVATOR | S | 14-0289 | 2015-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SHEPARDVILLE |  | 14-0289 | 2015-10-01 | 3 | 3 | 3 | 3 | 3 | N/A | 3
TG MILLER | S | 14-0289 | 2015-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Layout only
THE BRAIN DRAIN | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 14-0289 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2015-10-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
84 LUMBER COMPANY | S | 15-0306 | 2015-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 15-0306 | 2015-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 15-0306 | 2015-08-07 | 4 | 3 | 3 | 2 | N/A | 4 | 4 | lie about manpower
DESIGN SPECIALISTS INC. | S | 15-0306 | 2015-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRIETTA BUILDING SUPPLIES, INC. | S | 15-0306 | 2015-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0306 | 2015-08-07 | N/A | 1 | 3 | 3 | 3 | 3 | 3 | unresponsive and behind schedule
INDEPENDENT COMMERCIAL | S | 15-0306 | 2015-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY GLASS AND WINDOW INC. | S | 15-0306 | 2015-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LOWE'S (CORPORATE ACCOUNT) | S | 15-0306 | 2015-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEOLA ENTERPRISES LLC | S | 15-0306 | 2015-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0306 | 2015-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PURCELL CONSTRUCTION CORP. | S | 15-0306 | 2015-08-07 | 3 | 3 | 3 | 3 | 3 | 3 | 3
R.E. WOODSON, INC | S | 15-0306 | 2015-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAYMOND E. KELLEY INC. | S | 15-0306 | 2015-08-07 | 3 | 4 | 4 | 4 | 4 | 4 | 4
RUSTON PAVING CO., INC. | S | 15-0306 | 2015-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPARACINO CONSTRUCTION, INC. | S | 15-0306 | 2015-08-07 | 3 | 3 | 4 | 3 | 4 | 3 | 4
UNICO FINISHING SYSTEMS | S | 15-0306 | 2015-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VP SUPPLY | S | 15-0306 | 2015-08-07 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WHITE'S LUMBER, INC | S | 15-0306 | 2015-08-07 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 15-0306 | 2015-08-07 | 4 | 4 | 4 | 4 | 4 | 4 | 4
84 LUMBER COMPANY | S | 15-0306 | 2015-09-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | lie about manpower
AGAPE WHOLESALE FURNITURE | S | 15-0306 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 15-0306 | 2015-09-01 | 4 | 3 | 3 | 2 | N/A | 4 | 4
DESIGN SPECIALISTS INC. | S | 15-0306 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRIETTA BUILDING SUPPLIES, INC. | S | 15-0306 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0306 | 2015-09-01 | N/A | 1 | 3 | 3 | 3 | 3 | 3 | unresponsive and behind schedule
INDEPENDENT COMMERCIAL | S | 15-0306 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY GLASS AND WINDOW INC. | S | 15-0306 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LOWE'S (CORPORATE ACCOUNT) | S | 15-0306 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Do not use Lowes! Wont provide insurances
MEOLA ENTERPRISES LLC | S | 15-0306 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0306 | 2015-09-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | pedal for T
PURCELL CONSTRUCTION CORP. | S | 15-0306 | 2015-09-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
R.E. WOODSON, INC | S | 15-0306 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAYMOND E. KELLEY INC. | S | 15-0306 | 2015-09-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
RUSTON PAVING CO., INC. | S | 15-0306 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPARACINO CONSTRUCTION, INC. | S | 15-0306 | 2015-09-01 | 3 | 3 | 4 | 3 | 4 | 3 | 4
UNICO FINISHING SYSTEMS | S | 15-0306 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VP SUPPLY | S | 15-0306 | 2015-09-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WHITE'S LUMBER, INC | S | 15-0306 | 2015-09-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 15-0306 | 2015-09-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
84 LUMBER COMPANY | S | 14-0295 | 2015-06-01 | N/A | 4 | 4 | 4 | 3 | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALPHA IRON WORKS, LLC | S | 14-0295 | 2015-06-01 | 4 | 4 | 4 | 3 | N/A | 4 | 4
AMERICAN PLUMBING, INC | S | 14-0295 | 2015-06-01 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | Manpower issues, office is not responsive, schedule and quality concerns with meeting first milestone
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0295 | 2015-06-01 | N/A | 5 | N/A | N/A | N/A | 4 | 4 | Vendor
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0295 | 2015-06-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5
DDS CONSTRUCTORS, LLC | S | 14-0295 | 2015-06-01 | 4 | 4 | 5 | 3 | 3 | 4 | 3
FLOWER CITY GLASS | S | 14-0295 | 2015-06-01 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 14-0295 | 2015-06-01 | 3 | 2 | 3 | 1 | 3 | 2 | 2
IAQ TECHNOLOGIES | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KAPPER LANDSCAPING INC. | S | 14-0295 | 2015-06-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
KSP PAINTING OF SYRACUSE | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARACLE BUILDERS | S | 14-0295 | 2015-06-01 | 3 | 4 | 4 | 5 | 2 | N/A | 3 | Impressed and would use them again
MAX T. DOLAND | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEIER SUPPLY CO | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONTGOMERY TRUSS | S | 14-0295 | 2015-06-01 | N/A | 4 | N/A | N/A | N/A | 4 | 4
POSTLER & JAECKLE CORP. | S | 14-0295 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 14-0295 | 2015-06-01 | 4 | 4 | 4 | 4 | 4 | 2 | 3
RUSS & KATHY RAWLEIGH | S | 14-0295 | 2015-06-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
SCHINDLER ELEVATOR | S | 14-0295 | 2015-06-01 | 5 | N/A | N/A | N/A | N/A | 4 | N/A
SERWAY BROTHERS INC. | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | 2 | 2
SPECIAL CARE SYSTEMS, LLC | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRUAX & HOVEY | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 14-0295 | 2015-06-01 | 4 | 4 | 4 | 3 | 3 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0295 | 2015-06-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0306 | 2015-10-09 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AGAPE WHOLESALE FURNITURE | S | 15-0306 | 2015-10-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | supplier
DEMCO NEW YORK CORP. | S | 15-0306 | 2015-10-09 | 4 | 3 | 3 | 3 | N/A | 4 | 4 | lie about manpower
DESIGN SPECIALISTS INC. | S | 15-0306 | 2015-10-09 | 4 | 4 | 4 | 4 | N/A | 4 | 4
HENRIETTA BUILDING SUPPLIES, INC. | S | 15-0306 | 2015-10-09 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
HENRY E ISAACS QUALITY HOME | S | 15-0306 | 2015-10-09 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | unresponsive and behind schedule
INDEPENDENT COMMERCIAL | S | 15-0306 | 2015-10-09 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LIBERTY GLASS AND WINDOW INC. | S | 15-0306 | 2015-10-09 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LOWE'S (CORPORATE ACCOUNT) | S | 15-0306 | 2015-10-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Do not use Lowes! Wont provide insurances
MEOLA ENTERPRISES LLC | S | 15-0306 | 2015-10-09 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 15-0306 | 2015-10-09 | 4 | 3 | 3 | 3 | 4 | 4 | 4
PURCELL CONSTRUCTION CORP. | S | 15-0306 | 2015-10-09 | 3 | 3 | 3 | 3 | 3 | 3 | 3
R.E. WOODSON, INC | S | 15-0306 | 2015-10-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAYMOND E. KELLEY INC. | S | 15-0306 | 2015-10-09 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RUSTON PAVING CO., INC. | S | 15-0306 | 2015-10-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPARACINO CONSTRUCTION, INC. | S | 15-0306 | 2015-10-09 | 3 | 3 | 4 | 3 | 2 | 3 | 3 | over-price COs
UNICO FINISHING SYSTEMS | S | 15-0306 | 2015-10-09 | 3 | 3 | 3 | 3 | 4 | 4 | 4
VP SUPPLY | S | 15-0306 | 2015-10-09 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WHITE'S LUMBER, INC | S | 15-0306 | 2015-10-09 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 15-0306 | 2015-10-09 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | very professional
84 LUMBER COMPANY | S | 15-0306 | 2015-11-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 15-0306 | 2015-11-11 | 4 | 4 | 3 | 4 | N/A | N/A | 2 | supplier
DEMCO NEW YORK CORP. | S | 15-0306 | 2015-11-11 | 4 | 3 | 3 | 4 | N/A | 4 | 4 | subcontractor
DESIGN SPECIALISTS INC. | S | 15-0306 | 2015-11-11 | 4 | 4 | 4 | 4 | N/A | 4 | 4 | subcontractor
HENRIETTA BUILDING SUPPLIES, INC. | S | 15-0306 | 2015-11-11 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
HENRY E ISAACS QUALITY HOME | S | 15-0306 | 2015-11-11 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | unresponsive and behind schedule
INDEPENDENT COMMERCIAL | S | 15-0306 | 2015-11-11 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LIBERTY GLASS AND WINDOW INC. | S | 15-0306 | 2015-11-11 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LOWE'S (CORPORATE ACCOUNT) | S | 15-0306 | 2015-11-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Do not use Lowes! Wont provide insurances
MEOLA ENTERPRISES LLC | S | 15-0306 | 2015-11-11 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 15-0306 | 2015-11-11 | 4 | 3 | 3 | 3 | 4 | 4 | 4
PURCELL CONSTRUCTION CORP. | S | 15-0306 | 2015-11-11 | 3 | 3 | 3 | 3 | 3 | 3 | 3
R.E. WOODSON, INC | S | 15-0306 | 2015-11-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAYMOND E. KELLEY INC. | S | 15-0306 | 2015-11-11 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RUSTON PAVING CO., INC. | S | 15-0306 | 2015-11-11 | 4 | 3 | 3 | 4 | N/A | 3 | 3
UNICO FINISHING SYSTEMS | S | 15-0306 | 2015-11-11 | 3 | 3 | 3 | 3 | 4 | 4 | 4
VP SUPPLY | S | 15-0306 | 2015-11-11 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WHITE'S LUMBER, INC | S | 15-0306 | 2015-11-11 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 15-0306 | 2015-11-11 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | very professional
84 LUMBER COMPANY | S | 14-0295 | 2015-08-01 | N/A | 4 | 4 | 4 | 3 | 4 | 4
AIIA CONSTRUCTION COMPANY, INC | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0295 | 2015-08-01 | N/A | 4 | 4 | N/A | N/A | 4 | 4
ALPHA IRON WORKS, LLC | S | 14-0295 | 2015-08-01 | 4 | 4 | 4 | 3 | N/A | 4 | 4
AMERICAN PLUMBING, INC | S | 14-0295 | 2015-08-01 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | Manpower issues, office is not responsive, schedule and quality concerns with meeting first milestone
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0295 | 2015-08-01 | N/A | 5 | N/A | N/A | N/A | 4 | 4 | Vendor
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0295 | 2015-08-01 | 4 | 4 | 5 | 3 | 3 | 4 | 3 | Not pricing, just changed PM on project
FLOWER CITY GLASS | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 14-0295 | 2015-08-01 | 3 | 2 | 3 | 1 | 3 | 2 | 2 | Staffing issues which are causing schedule issues
IAQ TECHNOLOGIES | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KAPPER LANDSCAPING INC. | S | 14-0295 | 2015-08-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
KSP PAINTING OF SYRACUSE | S | 14-0295 | 2015-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MARACLE BUILDERS | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEIER SUPPLY CO | S | 14-0295 | 2015-08-01 | N/A | 5 | 4 | N/A | N/A | N/A | 3
MONTGOMERY TRUSS | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POSTLER & JAECKLE CORP. | S | 14-0295 | 2015-08-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 14-0295 | 2015-08-01 | 4 | 4 | 4 | 4 | 4 | 2 | 3
RUSS & KATHY RAWLEIGH | S | 14-0295 | 2015-08-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
SCHINDLER ELEVATOR | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERWAY BROTHERS INC. | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRUAX & HOVEY | S | 14-0295 | 2015-08-01 | 4 | 4 | 2 | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 14-0295 | 2015-08-01 | 4 | 4 | 4 | 3 | 3 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0295 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 14-0298 | 2015-07-22 | 4 | 3 | 4 | 3 | 2 | 3 | 3
AIIA CONSTRUCTION COMPANY, INC | S | 14-0298 | 2015-07-22 | 4 | 3 | 4 | 3 | 3 | 4 | 4
ALLIANCE DOOR & HARDWARE | S | 14-0298 | 2015-07-22 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | supplier
ALPHA IRON WORKS, LLC | S | 14-0298 | 2015-07-22 | 4 | 3 | 4 | 4 | 4 | 4 | 4
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0298 | 2015-07-22 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 14-0298 | 2015-07-22 | 4 | 4 | 5 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 14-0298 | 2015-07-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0298 | 2015-07-22 | 4 | 4 | 5 | 4 | 4 | 3 | 4
DEMCO NEW YORK CORP. | S | 14-0298 | 2015-07-22 | 4 | 3 | 3 | 3 | 4 | 4 | 4
ERIE MATERIALS INC. | S | 14-0298 | 2015-07-22 | N/A | 4 | N/A | N/A | N/A | N/A | N/A | supplier
FLOWER CITY GLASS | S | 14-0298 | 2015-07-22 | 4 | 2 | 2 | 3 | N/A | 3 | 3
HENDERSON-JOHNSON CO.INC. | S | 14-0298 | 2015-07-22 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HIGHLAND QUALITY CONSTRUCTION | S | 14-0298 | 2015-07-22 | 4 | 4 | 3 | 4 | 4 | N/A | 4
J&R SPECIALTIES | S | 14-0298 | 2015-07-22 | 4 | 4 | 4 | 4 | 4 | 4 | 4
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0298 | 2015-07-22 | 4 | 3 | 4 | 3 | N/A | N/A | 3
KENNEDY MECHANICAL PLUMBING DIV. | S | 14-0298 | 2015-07-22 | 4 | 3 | 4 | 3 | 4 | 4 | 4
KJW ASSOCIATES | S | 14-0298 | 2015-07-22 | 4 | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 14-0298 | 2015-07-22 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LAKEVIEW LAWN & LANDSCAPE | S | 14-0298 | 2015-07-22 | 4 | 3 | 4 | 3 | 4 | 4 | 4
MAX T. DOLAND | S | 14-0298 | 2015-07-22 | N/A | 4 | N/A | 4 | N/A | 4 | 4 | supplier
MONTGOMERY TRUSS | S | 14-0298 | 2015-07-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PARKITECTS | S | 14-0298 | 2015-07-22 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 14-0298 | 2015-07-22 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHACHTLER CONTRACTING | S | 14-0298 | 2015-07-22 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHINDLER ELEVATOR | S | 14-0298 | 2015-07-22 | 4 | 3 | 4 | 4 | 4 | 4 | 3
SERWAY BROTHERS INC. | S | 14-0298 | 2015-07-22 | N/A | 3 | 3 | 4 | 4 | 4 | 4
SESSLER EXCAVATING | S | 14-0298 | 2015-07-22 | 5 | 5 | 5 | 5 | 5 | 5 | 5
TG MILLER | S | 14-0298 | 2015-07-22 | 4 | 4 | 4 | 4 | 4 | 4 | 4
TOWER ROOFING | S | 14-0298 | 2015-07-22 | 4 | 2 | 4 | 3 | N/A | 3 | 3 | Didn?t start ontime
TRUAX & HOVEY | S | 14-0298 | 2015-07-22 | 4 | 3 | 4 | 4 | N/A | 4 | 4
WHITMORE FENCE | S | 14-0298 | 2015-07-22 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WM. B. MORSE LUMBER CO. | S | 14-0298 | 2015-07-22 | 4 | 4 | N/A | N/A | N/A | N/A | 4 | supplier
711 NEW YORK PAINTING | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SYSTEMS MAINTENANCE | S | 14-0299 | 2015-07-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
ALLEN BOULEVARD INTERIORS | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | supplier
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | not yet onsite; unresponsive office
AUFIERO PAINTING INDUSTRIES | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0299 | 2015-07-01 | N/A | 4 | N/A | N/A | N/A | 4 | 4 | supplier
BGI INTERIORS | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0299 | 2015-07-01 | 3 | 3 | 3 | 3 | 4 | 4 | 4
COMMERCIAL FENCE AND RAILING | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWN WATERPROOFING | S | 14-0299 | 2015-07-01 | 4 | 4 | 4 | 3 | 4 | 5 | 3
D.V. BROWN & ASSOCIATES | S | 14-0299 | 2015-07-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
DEMCO NEW YORK CORP. | S | 14-0299 | 2015-07-01 | 4 | 2 | 4 | 3 | 4 | 3 | 3
DESIGN CONCRETE CORP. | S | 14-0299 | 2015-07-01 | 3 | 2 | 4 | 3 | 4 | 4 | 4
EZ WAY | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESH MEADOW MECHANICAL CORP | S | 14-0299 | 2015-07-01 | 4 | 5 | 4 | 4 | 4 | 4 | 4
GCSI, LLC | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GE APPLIANCES | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HARTCORN PLUMBING & HEAT | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOCKENBERGS EQPT. & SUPPLY | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
K&P FACILITIES MAINTENANCE | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY MASONRY | S | 14-0299 | 2015-07-01 | 4 | 2 | 4 | 4 | N/A | 3 | 3
LUDWIG J FURTHNER III | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPOLITANO DISTRIBUTING | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 14-0299 | 2015-07-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NATIONAL LUMBER | S | 14-0299 | 2015-07-01 | 3 | 3 | 3 | 3 | 3 | 4 | 3
NEW YORK GYPSUM FLOORS | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 14-0299 | 2015-07-01 | 3 | 3 | 3 | 4 | 3 | 4 | 3
OVERHEAD DOOR CO OF GLENS FALL | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLASTER MATERIAL | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER BUILDING & RENOVATIONS | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RALPH W. PLOTKE | S | 14-0299 | 2015-07-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3
SCHINDLER ELEVATOR | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMART ENERGY SPRAY FOAM | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STERLING FLOOR DESIGN | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYR BEAUTY | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRY CONTRACTING & MATERIALS | S | 14-0299 | 2015-07-01 | 3 | 3 | 4 | 3 | 3 | 3 | 2 | office unresponsive
TRIPOINT STONE | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW TREATMENTS BY JEM | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNG & YOUNG | S | 14-0299 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | surveyor
84 LUMBER COMPANY | S | 14-0295 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 14-0295 | 2015-10-01 | 4 | 3 | 4 | 3 | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0295 | 2015-10-01 | N/A | 4 | 4 | N/A | N/A | 4 | 4
ALPHA IRON WORKS, LLC | S | 14-0295 | 2015-10-01 | 4 | 4 | 4 | 3 | N/A | 4 | 4
AMERICAN PLUMBING, INC | S | 14-0295 | 2015-10-01 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | The worst subcontractor team has ever dealt with.
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0295 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0295 | 2015-10-01 | N/A | 5 | N/A | N/A | N/A | 4 | 4
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 14-0295 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0295 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0295 | 2015-10-01 | 4 | 2 | 2 | 3 | 3 | 4 | 3 | have been behind
FLOWER CITY GLASS | S | 14-0295 | 2015-10-01 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | Do not know their scope; Having issues with the PM - Mark Webster
HENRY ISAACS HOME REMODELING | S | 14-0295 | 2015-10-01 | 3 | 2 | 3 | 1 | 3 | 2 | 2 | Staffing issues which are causing schedule issues
IAQ TECHNOLOGIES | S | 14-0295 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 14-0295 | 2015-10-01 | 4 | 3 | 4 | 4 | N/A | 1 | 2 | inconsistent office
JACHLES IMPERIAL LTD | S | 14-0295 | 2015-10-01 | 4 | 3 | 3 | 4 | N/A | N/A | 4
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0295 | 2015-10-01 | 4 | 5 | 4 | 4 | N/A | N/A | 3
KAPPER LANDSCAPING INC. | S | 14-0295 | 2015-10-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
KSP PAINTING OF SYRACUSE | S | 14-0295 | 2015-10-01 | 4 | 3 | 3 | 4 | 4 | 4 | 4
MARACLE BUILDERS | S | 14-0295 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Impressed and would use them again
MAX T. DOLAND | S | 14-0295 | 2015-10-01 | 5 | 5 | 5 | N/A | 5 | 5 | 5
MEIER SUPPLY CO | S | 14-0295 | 2015-10-01 | N/A | 5 | 4 | N/A | N/A | N/A | 3
MONTGOMERY TRUSS | S | 14-0295 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POSTLER & JAECKLE CORP. | S | 14-0295 | 2015-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 14-0295 | 2015-10-01 | 4 | 4 | 4 | 4 | 4 | 2 | 3
RUSS & KATHY RAWLEIGH | S | 14-0295 | 2015-10-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
SCHINDLER ELEVATOR | S | 14-0295 | 2015-10-01 | 4 | 4 | 4 | N/A | N/A | 4 | N/A
SERWAY BROTHERS INC. | S | 14-0295 | 2015-10-01 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | closing forever
SPECIAL CARE SYSTEMS, LLC | S | 14-0295 | 2015-10-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
TRUAX & HOVEY | S | 14-0295 | 2015-10-01 | 4 | 4 | 2 | 4 | N/A | N/A | N/A
US CEILING CORP. | S | 14-0295 | 2015-10-01 | 4 | 4 | 4 | 3 | 3 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0295 | 2015-10-01 | N/A | 3 | 4 | N/A | N/A | 4 | N/A | rep is difficult to reach.
WM. B. MORSE LUMBER CO. | S | 14-0295 | 2015-10-01 | 4 | 3 | 4 | N/A | N/A | N/A | 4
84 LUMBER COMPANY | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 14-0295 | 2015-11-01 | 4 | 3 | 4 | 3 | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0295 | 2015-11-01 | N/A | 4 | 4 | N/A | N/A | 4 | 4
ALPHA IRON WORKS, LLC | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AMERICAN PLUMBING, INC | S | 14-0295 | 2015-11-01 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | The worst subcontractor team has ever dealt with.
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Vendor
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0295 | 2015-11-01 | 4 | 2 | 2 | 3 | 3 | 4 | 3
FLOWER CITY GLASS | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 14-0295 | 2015-11-01 | 3 | 2 | 3 | 1 | 3 | 2 | 2 | Staffing issues which are causing schedule issues
IAQ TECHNOLOGIES | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 14-0295 | 2015-11-01 | 4 | 3 | 4 | 4 | N/A | 1 | 2 | inconsistent office
JACHLES IMPERIAL LTD | S | 14-0295 | 2015-11-01 | 4 | 3 | 3 | 4 | N/A | N/A | 4
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0295 | 2015-11-01 | 4 | 5 | 4 | 4 | N/A | N/A | 3
KAPPER LANDSCAPING INC. | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KSP PAINTING OF SYRACUSE | S | 14-0295 | 2015-11-01 | 4 | 3 | 2 | 4 | 4 | 4 | 4 | Quality went down in last month to rush to make punchlist
MARACLE BUILDERS | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0295 | 2015-11-01 | 5 | 5 | 5 | N/A | 5 | 5 | 5
MEIER SUPPLY CO | S | 14-0295 | 2015-11-01 | N/A | 5 | 4 | N/A | N/A | N/A | 3
MONTGOMERY TRUSS | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POSTLER & JAECKLE CORP. | S | 14-0295 | 2015-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 14-0295 | 2015-11-01 | 4 | 4 | 4 | 3 | 4 | 2 | 3 | improved schedule and manpower when asked; they were very willing to work with the team
RUSS & KATHY RAWLEIGH | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0295 | 2015-11-01 | 4 | 4 | 4 | N/A | N/A | 4 | N/A
SERWAY BROTHERS INC. | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 14-0295 | 2015-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
TRUAX & HOVEY | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 14-0295 | 2015-11-01 | 4 | 4 | 4 | 3 | 3 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0295 | 2015-11-01 | N/A | 3 | 4 | N/A | N/A | 4 | N/A | rep is difficult to reach.
WM. B. MORSE LUMBER CO. | S | 14-0295 | 2015-11-01 | 4 | 3 | 4 | N/A | N/A | N/A | 4
84 LUMBER COMPANY | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | never had enough manpower- do not want to use again
DESIGN SPECIALISTS INC. | S | 15-0306 | 2015-07-01 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
HENRIETTA BUILDING SUPPLIES, INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
INDEPENDENT COMMERCIAL | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY GLASS AND WINDOW INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LOWE'S (CORPORATE ACCOUNT) | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEOLA ENTERPRISES LLC | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PURCELL CONSTRUCTION CORP. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R.E. WOODSON, INC | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAYMOND E. KELLEY INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RUSTON PAVING CO., INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPARACINO CONSTRUCTION, INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. |  | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VP SUPPLY | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITE'S LUMBER, INC | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DESIGN SPECIALISTS INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRIETTA BUILDING SUPPLIES, INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
INDEPENDENT COMMERCIAL | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY GLASS AND WINDOW INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LOWE'S (CORPORATE ACCOUNT) | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEOLA ENTERPRISES LLC | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PURCELL CONSTRUCTION CORP. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R.E. WOODSON, INC | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAYMOND E. KELLEY INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RUSTON PAVING CO., INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPARACINO CONSTRUCTION, INC. | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. |  | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VP SUPPLY | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITE'S LUMBER, INC | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 15-0306 | 2015-07-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 14-0295 | 2015-11-01 | 4 | 3 | 4 | 3 | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0295 | 2015-11-01 | N/A | 4 | 4 | N/A | N/A | 4 | 4
ALPHA IRON WORKS, LLC | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AMERICAN PLUMBING, INC | S | 14-0295 | 2015-11-01 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | The worst subcontractor team has ever dealt with.
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Vendor
BUFFALO HOTEL SUPPLY COMPANY, INC. | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 14-0295 | 2015-11-01 | 4 | 2 | 2 | 3 | 3 | 4 | 3
FLOWER CITY GLASS | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY ISAACS HOME REMODELING | S | 14-0295 | 2015-11-01 | 3 | 2 | 3 | 1 | 3 | 2 | 2 | Staffing issues which are causing schedule issues
IAQ TECHNOLOGIES | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 14-0295 | 2015-11-01 | 4 | 3 | 4 | 4 | N/A | 1 | 2 | inconsistent office
JACHLES IMPERIAL LTD | S | 14-0295 | 2015-11-01 | 4 | 3 | 3 | 4 | N/A | N/A | 4
JOSEPHINE'S CLEANING SERVICE, LLC | S | 14-0295 | 2015-11-01 | 4 | 5 | 4 | 4 | N/A | N/A | 3
KAPPER LANDSCAPING INC. | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KSP PAINTING OF SYRACUSE | S | 14-0295 | 2015-11-01 | 4 | 3 | 2 | 4 | 4 | 4 | 4 | Quality went down in last month to rush to make punchlist
MARACLE BUILDERS | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0295 | 2015-11-01 | 5 | 5 | 5 | N/A | 5 | 5 | 5
MEIER SUPPLY CO | S | 14-0295 | 2015-11-01 | N/A | 5 | 4 | N/A | N/A | N/A | 3
MONTGOMERY TRUSS | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POSTLER & JAECKLE CORP. | S | 14-0295 | 2015-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 14-0295 | 2015-11-01 | 4 | 4 | 4 | 3 | 4 | 2 | 3 | improved schedule and manpower when asked; they were very willing to work with the team
RUSS & KATHY RAWLEIGH | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0295 | 2015-11-01 | 4 | 4 | 4 | N/A | N/A | 4 | N/A
SERWAY BROTHERS INC. | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPECIAL CARE SYSTEMS, LLC | S | 14-0295 | 2015-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
TRUAX & HOVEY | S | 14-0295 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
US CEILING CORP. | S | 14-0295 | 2015-11-01 | 4 | 4 | 4 | 3 | 3 | 4 | 4
WHIRLPOOL CORPORATION | S | 14-0295 | 2015-11-01 | N/A | 3 | 4 | N/A | N/A | 4 | N/A | rep is difficult to reach.
WM. B. MORSE LUMBER CO. | S | 14-0295 | 2015-11-01 | 4 | 3 | 4 | N/A | N/A | N/A | 4
711 NEW YORK PAINTING | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SYSTEMS MAINTENANCE | S | 14-0299 | 2015-08-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
ALLEN BOULEVARD INTERIORS | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | supplier
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | not yet onsite; unresponsive office
AUFIERO PAINTING INDUSTRIES | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0299 | 2015-08-01 | N/A | 4 | N/A | N/A | N/A | 4 | 4 | supplier
BGI INTERIORS | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0299 | 2015-08-01 | 3 | 3 | 3 | 3 | 4 | 4 | 4
COMMERCIAL FENCE AND RAILING | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWN WATERPROOFING | S | 14-0299 | 2015-08-01 | 4 | 4 | 4 | 3 | 4 | 5 | 3
D.V. BROWN & ASSOCIATES | S | 14-0299 | 2015-08-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
DEMCO NEW YORK CORP. | S | 14-0299 | 2015-08-01 | 4 | 2 | 4 | 3 | 4 | 3 | 3
DESIGN CONCRETE CORP. | S | 14-0299 | 2015-08-01 | 3 | 2 | 4 | 3 | 4 | 4 | 4
EZ WAY | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESH MEADOW MECHANICAL CORP | S | 14-0299 | 2015-08-01 | 4 | 5 | 4 | 4 | 4 | 4 | 4
GCSI, LLC | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GE APPLIANCES | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HARTCORN PLUMBING & HEAT | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOCKENBERGS EQPT. & SUPPLY | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
K&P FACILITIES MAINTENANCE | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY MASONRY | S | 14-0299 | 2015-08-01 | 4 | 2 | 4 | 4 | N/A | 3 | 3
LUDWIG J FURTHNER III | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPOLITANO DISTRIBUTING | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 14-0299 | 2015-08-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NATIONAL LUMBER | S | 14-0299 | 2015-08-01 | 3 | 3 | 3 | 3 | 3 | 4 | 3
NEW YORK GYPSUM FLOORS | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 14-0299 | 2015-08-01 | 3 | 3 | 3 | 4 | 3 | 4 | 3
OVERHEAD DOOR CO OF GLENS FALL | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLASTER MATERIAL | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER BUILDING & RENOVATIONS | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RALPH W. PLOTKE | S | 14-0299 | 2015-08-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3
SCHINDLER ELEVATOR | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMART ENERGY SPRAY FOAM | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STERLING FLOOR DESIGN | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYR BEAUTY | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRY CONTRACTING & MATERIALS | S | 14-0299 | 2015-08-01 | 3 | 3 | 4 | 3 | 3 | 3 | 2 | office unresponsive
TRIPOINT STONE | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW TREATMENTS BY JEM | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNG & YOUNG | S | 14-0299 | 2015-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | surveyor
84 LUMBER COMPANY | S | 15-0306 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 15-0306 | 2015-11-01 | 4 | 4 | 3 | 4 | N/A | N/A | 2
ART PARTS SIGNS | S | 15-0306 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 15-0306 | 2015-11-01 | 4 | 3 | 3 | 4 | N/A | 4 | 4
DESIGN SPECIALISTS INC. | S | 15-0306 | 2015-11-01 | 4 | 4 | 4 | 4 | N/A | 4 | 4
HENRIETTA BUILDING SUPPLIES, INC. | S | 15-0306 | 2015-11-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4
HENRY E ISAACS QUALITY HOME | S | 15-0306 | 2015-11-01 | 2 | 1 | 2 | 2 | 2 | 2 | 2
INDEPENDENT COMMERCIAL | S | 15-0306 | 2015-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LIBERTY GLASS AND WINDOW INC. | S | 15-0306 | 2015-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LOWE'S (CORPORATE ACCOUNT) | S | 15-0306 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Do not use Lowes! Wont provide
MEOLA ENTERPRISES LLC | S | 15-0306 | 2015-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 15-0306 | 2015-11-01 | 4 | 3 | 3 | 3 | 4 | 4 | 4
PURCELL CONSTRUCTION CORP. | S | 15-0306 | 2015-11-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
R.E. WOODSON, INC | S | 15-0306 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAYMOND E. KELLEY INC. | S | 15-0306 | 2015-11-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RUSTON PAVING CO., INC. | S | 15-0306 | 2015-11-01 | 4 | 3 | 3 | 4 | N/A | 3 | 3
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. |  | 15-0306 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0306 | 2015-11-01 | 3 | 3 | 3 | 3 | 4 | 4 | 4
VP SUPPLY | S | 15-0306 | 2015-11-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WHITE'S LUMBER, INC | S | 15-0306 | 2015-11-01 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 15-0306 | 2015-11-01 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | very professional
711 NEW YORK PAINTING | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACPRODUCTS, INC | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SYSTEMS MAINTENANCE | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLEN BOULEVARD INTERIORS | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUFIERO PAINTING INDUSTRIES | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL FENCE AND RAILING | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWN WATERPROOFING | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D.V. BROWN & ASSOCIATES | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DESIGN CONCRETE CORP. | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EZ WAY | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESH MEADOW MECHANICAL CORP | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GCSI, LLC | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GE APPLIANCES | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HARTCORN PLUMBING & HEAT | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOCKENBERGS EQPT. & SUPPLY | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
K&P FACILITIES MAINTENANCE | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY MASONRY | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LUDWIG J FURTHNER III | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPOLITANO DISTRIBUTING | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL LUMBER | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK GYPSUM FLOORS | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERHEAD DOOR CO OF GLENS FALL | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLASTER MATERIAL | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER BUILDING & RENOVATIONS | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RALPH W. PLOTKE | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMART ENERGY SPRAY FOAM | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STERLING FLOOR DESIGN | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYR BEAUTY | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRY CONTRACTING & MATERIALS | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRIPOINT STONE | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW TREATMENTS BY JEM | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNG & YOUNG | S | 14-0299 | 2015-06-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
711 NEW YORK PAINTING | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACPRODUCTS, INC | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SYSTEMS MAINTENANCE | S | 14-0299 | 2015-09-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
ALLEN BOULEVARD INTERIORS | S | 14-0299 | 2015-09-01 | 3 | 3 | 3 | 3 | 3 | 2 | 3
ALLIANCE DOOR & HARDWARE | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | supplier
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | not yet onsite; unresponsive office
AUFIERO PAINTING INDUSTRIES | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | suplier
BGI INTERIORS | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0299 | 2015-09-01 | 3 | 3 | 3 | 3 | 4 | 4 | 4
COMMERCIAL FENCE AND RAILING | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWN WATERPROOFING | S | 14-0299 | 2015-09-01 | 4 | 4 | 4 | 3 | 4 | 5 | 3
D.V. BROWN & ASSOCIATES | S | 14-0299 | 2015-09-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
DEMCO NEW YORK CORP. | S | 14-0299 | 2015-09-01 | 4 | 2 | 4 | 3 | 4 | 3 | 3
DESIGN CONCRETE CORP. | S | 14-0299 | 2015-09-01 | 3 | 2 | 4 | 3 | 4 | 4 | 4
EZ WAY | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESH MEADOW MECHANICAL CORP | S | 14-0299 | 2015-09-01 | 4 | 5 | 4 | 4 | 4 | 4 | 4
GCSI, LLC | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GE APPLIANCES | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HARTCORN PLUMBING & HEAT | S | 14-0299 | 2015-09-01 | 4 | 4 | 4 | 4 | 3 | 4 | 3
HOCKENBERGS EQPT. & SUPPLY | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
K&P FACILITIES MAINTENANCE | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY MASONRY | S | 14-0299 | 2015-09-01 | 4 | 2 | 4 | 4 | N/A | 3 | 3
LUDWIG J FURTHNER III | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPOLITANO DISTRIBUTING | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 14-0299 | 2015-09-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NATIONAL LUMBER | S | 14-0299 | 2015-09-01 | 3 | 2 | 3 | 3 | 3 | 4 | 3 | areas are incomplete
NEW YORK GYPSUM FLOORS | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 14-0299 | 2015-09-01 | 3 | 3 | 3 | 4 | 3 | 4 | 3
OVERHEAD DOOR CO OF GLENS FALL | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLASTER MATERIAL | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER BUILDING & RENOVATIONS | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RALPH W. PLOTKE | S | 14-0299 | 2015-09-01 | 4 | 4 | 4 | 4 | 3 | 3 | 3
SCHINDLER ELEVATOR | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMART ENERGY SPRAY FOAM | S | 14-0299 | 2015-09-01 | 3 | 3 | 3 | 4 | 3 | 3 | 3
STERLING FLOOR DESIGN | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYR BEAUTY | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRY CONTRACTING & MATERIALS | S | 14-0299 | 2015-09-01 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | office unresponsive
TRIPOINT STONE | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW TREATMENTS BY JEM | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | supplier
YOUNG & YOUNG | S | 14-0299 | 2015-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | surveyor
711 NEW YORK PAINTING | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACPRODUCTS, INC | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SYSTEMS MAINTENANCE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLEN BOULEVARD INTERIORS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUFIERO PAINTING INDUSTRIES | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL FENCE AND RAILING | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWN WATERPROOFING | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D.V. BROWN & ASSOCIATES | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DESIGN CONCRETE CORP. | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EZ WAY | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESH MEADOW MECHANICAL CORP | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GCSI, LLC | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GE APPLIANCES | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HARTCORN PLUMBING & HEAT | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOCKENBERGS EQPT. & SUPPLY | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
K&P FACILITIES MAINTENANCE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY MASONRY | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LUDWIG J FURTHNER III | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPOLITANO DISTRIBUTING | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL LUMBER | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK GYPSUM FLOORS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERHEAD DOOR CO OF GLENS FALL | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLASTER MATERIAL | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER BUILDING & RENOVATIONS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RALPH W. PLOTKE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMART ENERGY SPRAY FOAM | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STERLING FLOOR DESIGN | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYR BEAUTY | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRY CONTRACTING & MATERIALS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRIPOINT STONE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW TREATMENTS BY JEM | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNG & YOUNG | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
711 NEW YORK PAINTING | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACPRODUCTS, INC | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SYSTEMS MAINTENANCE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLEN BOULEVARD INTERIORS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUFIERO PAINTING INDUSTRIES | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL FENCE AND RAILING | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWN WATERPROOFING | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D.V. BROWN & ASSOCIATES | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DESIGN CONCRETE CORP. | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EZ WAY | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESH MEADOW MECHANICAL CORP | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GCSI, LLC | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GE APPLIANCES | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HARTCORN PLUMBING & HEAT | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOCKENBERGS EQPT. & SUPPLY | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
K&P FACILITIES MAINTENANCE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY MASONRY | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LUDWIG J FURTHNER III | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPOLITANO DISTRIBUTING | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL LUMBER | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK GYPSUM FLOORS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERHEAD DOOR CO OF GLENS FALL | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLASTER MATERIAL | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER BUILDING & RENOVATIONS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RALPH W. PLOTKE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMART ENERGY SPRAY FOAM | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STERLING FLOOR DESIGN | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYR BEAUTY | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRY CONTRACTING & MATERIALS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRIPOINT STONE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW TREATMENTS BY JEM | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNG & YOUNG | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
711 NEW YORK PAINTING | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACPRODUCTS, INC | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SYSTEMS MAINTENANCE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLEN BOULEVARD INTERIORS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUFIERO PAINTING INDUSTRIES | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL FENCE AND RAILING | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWN WATERPROOFING | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D.V. BROWN & ASSOCIATES | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DESIGN CONCRETE CORP. | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EZ WAY | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESH MEADOW MECHANICAL CORP | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GCSI, LLC | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GE APPLIANCES | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HARTCORN PLUMBING & HEAT | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOCKENBERGS EQPT. & SUPPLY | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
K&P FACILITIES MAINTENANCE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY MASONRY | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LUDWIG J FURTHNER III | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPOLITANO DISTRIBUTING | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL LUMBER | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK GYPSUM FLOORS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERHEAD DOOR CO OF GLENS FALL | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLASTER MATERIAL | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER BUILDING & RENOVATIONS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RALPH W. PLOTKE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMART ENERGY SPRAY FOAM | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STERLING FLOOR DESIGN | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYR BEAUTY | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRY CONTRACTING & MATERIALS | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRIPOINT STONE | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW TREATMENTS BY JEM | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNG & YOUNG | S | 14-0299 | 2015-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
711 NEW YORK PAINTING | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACPRODUCTS, INC | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SYSTEMS MAINTENANCE | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLEN BOULEVARD INTERIORS | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUFIERO PAINTING INDUSTRIES | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL FENCE AND RAILING | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWN WATERPROOFING | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D.V. BROWN & ASSOCIATES | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DESIGN CONCRETE CORP. | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EZ WAY | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESH MEADOW MECHANICAL CORP | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GCSI, LLC | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GE APPLIANCES | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HARTCORN PLUMBING & HEAT | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HOCKENBERGS EQPT. & SUPPLY | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
K&P FACILITIES MAINTENANCE | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY MASONRY | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LUDWIG J FURTHNER III | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPOLITANO DISTRIBUTING | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL LUMBER | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK GYPSUM FLOORS | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OLDCASTLE PRECAST | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERHEAD DOOR CO OF GLENS FALL | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLASTER MATERIAL | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER BUILDING & RENOVATIONS | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RALPH W. PLOTKE | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMART ENERGY SPRAY FOAM | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STERLING FLOOR DESIGN | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYR BEAUTY | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRY CONTRACTING & MATERIALS | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRIPOINT STONE | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW TREATMENTS BY JEM | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNG & YOUNG | S | 14-0299 | 2015-11-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 CONTRACTORS INC. | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2016-04-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACPRODUCTS, INC | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | supplier
AIIA CONSTRUCTION COMPANY, INC | S | 15-0305 | 2016-04-28 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | Reached out to office to try to improve PCO process.
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2016-04-28 | 4 | 4 | 4 | 4 | 4 | 4 | 3
ALLIED MECHANICAL | S | 15-0305 | 2016-04-28 | 4 | 5 | 4 | 5 | 3 | 3 | 3
ALPHA IRON WORKS, LLC | S | 15-0305 | 2016-04-28 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BALTZ CONCRETE CONST., INC | S | 15-0305 | 2016-04-28 | 5 | 3 | 5 | 5 | 5 | N/A | 5 | Excellent Safety. Great all around.
BILLONE MECHANICAL CONTRACTORS | S | 15-0305 | 2016-04-28 | 5 | 5 | 4 | 3 | N/A | 5 | 5
BUFFALO CONCRETE ACCESSORIES | S | 15-0305 | 2016-04-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CAPITIAL FENCE CO., INC | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATALANO CONTRACTING, INC | S | 15-0305 | 2016-04-28 | 4 | 4 | 4 | 4 | N/A | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0305 | 2016-04-28 | 5 | 4 | 4 | 4 | N/A | 4 | 4
DESIGN POOL & SPA LTD. | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENERGY INSULATION SYSTEMS, INC | S | 15-0305 | 2016-04-28 | 4 | 2 | 3 | 3 | N/A | 4 | 4
FISHER CONCRETE, INC | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GYPSUM SYSTEMS, INC. | S | 15-0305 | 2016-04-28 | 4 | 5 | 5 | 4 | N/A | 3 | 3
HENDERSON-JOHNSON CO.INC. | S | 15-0305 | 2016-04-28 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY E ISAACS QUALITY HOME | S | 15-0305 | 2016-04-28 | 4 | 4 | 4 | 3 | 4 | 4 | 4
J Y R SPECIALITIES, INC | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J.B. HUNT | S | 15-0305 | 2016-04-28 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 40 installs with at least 20 different install crews. We voiced that we wanted the consistent. Only incident on the project was with this sub. Still scratched floors. No office leadership.
JOHNSON & JOHNSON CONSTRUCTION | S | 15-0305 | 2016-04-28 | 3 | 3 | 3 | 3 | 3 | N/A | 1 | Actual in-house crews are good. Did improve after we voiced our discontent
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2016-04-28 | 5 | 5 | 4 | 4 | 3 | 2 | 5 | New contact in office; very proactive
KLEIN REINFORCING SERVICES | S | 15-0305 | 2016-04-28 | 4 | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 15-0305 | 2016-04-28 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | Unacceptable. Never want to work with again
L.J. QUIGLIANO | S | 15-0305 | 2016-04-28 | 4 | 5 | 5 | 5 | 2 | 2 | 4 | Fantactic. They follow our plan and are very helpful. Small office so slow on follow up
LAKEVIEW LAWN & LANDSCAPE | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 15-0305 | 2016-04-28 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MIG BUILDING SYSTEMS | S | 15-0305 | 2016-04-28 | 4 | 3 | 3 | 2 | 4 | 3 | 3
MONTGOMERY TRUSS & PANEL (PANELS) | S | 15-0305 | 2016-04-28 | 5 | 5 | 5 | 5 | N/A | 4 | 5
ONTARIO EXTERIORS, INC | S | 15-0305 | 2016-04-28 | 4 | 3 | 4 | 4 | 4 | 4 | 3
PASSERO ASSOCIATES | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2016-04-28 | 4 | 4 | 4 | 4 | 3 | 2 | 3
S.A.B. SPECIALTIES | S | 15-0305 | 2016-04-28 | 2 | 4 | 4 | 5 | 4 | N/A | 4
SUPERIOR CONTRACTING, INC. | S | 15-0305 | 2016-04-28 | 4 | 4 | 4 | 4 | 4 | 4 | 3
UNICO FINISHING SYSTEMS | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNITED MATERIALS, LLC | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0305 | 2016-04-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 15-0305 | 2016-04-28 | 4 | 4 | 4 | N/A | 4 | 4 | 4
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0313 | 2016-04-06 | 2 | 4 | 4 | 3 | N/A | 4 | 4
CABLE ELECTRICAL SERVICES | S | 15-0313 | 2016-04-06 | 2 | 4 | 4 | 3 | N/A | 4 | 4
HAVEN CONTRACTING, INC | S | 15-0313 | 2016-04-06 | 3 | 3 | 4 | 3 | N/A | 3 | 3 | multiple changes in field crew
NATIONAL CONSTRUCTION RENTALS | S | 15-0313 | 2016-04-06 | 4 | 3 | 4 | 4 | N/A | N/A | 3
PEC SURVEYING AND MAPPING | S | 15-0313 | 2016-04-06 | 4 | 4 | 5 | 5 | N/A | N/A | 5
QP CONSTRUCTION | S | 15-0313 | 2016-04-06 | 3 | 4 | 4 | 3 | N/A | 4 | 4 | need real foreman
SUNSHINE STATE PLUMBING | S | 15-0313 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | 3 | 3
UNIVERSAL ENGINEERING SCIENCES | S | 15-0313 | 2016-04-06 | N/A | N/A | 4 | N/A | N/A | 3 | 4
WATERWATCH CORPORATION | S | 15-0313 | 2016-04-06 | 3 | 3 | 3 | 3 | N/A | N/A | 3
WLW CONSTRUCTION | S | 15-0313 | 2016-04-06 | 4 | 4 | 4 | 5 | N/A | 2 | 2 | very weak on providing paper
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0313 | 2016-05-06 | 2 | 4 | 4 | 3 | N/A | 4 | 4
CABLE ELECTRICAL SERVICES | S | 15-0313 | 2016-05-06 | 2 | 4 | 4 | 3 | N/A | 4 | 4
HAVEN CONTRACTING, INC | S | 15-0313 | 2016-05-06 | 3 | 2 | 4 | 3 | N/A | 3 | 3 | multiple changes in field crew
NATIONAL CONSTRUCTION RENTALS | S | 15-0313 | 2016-05-06 | 4 | 3 | 4 | 4 | N/A | N/A | 3
PEC SURVEYING AND MAPPING | S | 15-0313 | 2016-05-06 | 4 | 4 | 5 | 5 | N/A | N/A | 5
QP CONSTRUCTION | S | 15-0313 | 2016-05-06 | 3 | 4 | 4 | 3 | N/A | 4 | 4 | need real foreman
SUNSHINE STATE PLUMBING | S | 15-0313 | 2016-05-06 | 4 | 3 | 4 | N/A | N/A | 3 | 3
UNIVERSAL ENGINEERING SCIENCES | S | 15-0313 | 2016-05-06 | N/A | 3 | 3 | 2 | N/A | 3 | 4
WATERWATCH CORPORATION | S | 15-0313 | 2016-05-06 | 3 | 3 | 3 | 3 | N/A | N/A | 3
WLW CONSTRUCTION | S | 15-0313 | 2016-05-06 | 4 | 3 | 4 | 4 | N/A | 2 | 2 | very weak on providing paper
AAC CONTRACTING, INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GROVER & BATES ASSOCIATES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MESSNER FLOORING RESOURCE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCK ENVIRONMENTAL | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHULER-HAAS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILLIAM L. WATSON | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2016-05-04 | 3 | 4 | 4 | 4 | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GROVER & BATES ASSOCIATES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MESSNER FLOORING RESOURCE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCK ENVIRONMENTAL | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHULER-HAAS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILLIAM L. WATSON | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2016-05-04 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2016-05-04 | 4 | 4 | 4 | 4 | 3 | 4 | N/A
BGI INTERIORS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GROVER & BATES ASSOCIATES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MESSNER FLOORING RESOURCE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCK ENVIRONMENTAL | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHULER-HAAS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILLIAM L. WATSON | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2016-05-04 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2016-05-04 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2016-05-04 | N/A | 3 | 4 | N/A | N/A | 4 | N/A | getting materials here on time trouble here
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GROVER & BATES ASSOCIATES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MESSNER FLOORING RESOURCE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCK ENVIRONMENTAL | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHULER-HAAS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILLIAM L. WATSON | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2016-05-04 | 3 | 4 | 4 | 4 | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2016-05-04 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | getting materials here on time trouble here
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GROVER & BATES ASSOCIATES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MESSNER FLOORING RESOURCE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCK ENVIRONMENTAL | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHULER-HAAS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILLIAM L. WATSON | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2016-05-04 | 3 | 4 | 4 | 4 | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2016-05-04 | 4 | 4 | 4 | 4 | 3 | 4 | N/A
BGI INTERIORS | S | 15-0303 | 2016-05-04 | N/A | 3 | 4 | N/A | N/A | 4 | N/A | getting materials here on time trouble here
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2016-05-04 | 4 | 3 | 3 | 3 | 2 | 3 | 3 | New PM added and were not impressed
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2016-05-04 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0303 | 2016-05-04 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 15-0303 | 2016-05-04 | 4 | 4 | 4 | 4 | N/A | 3 | 2
GROVER & BATES ASSOCIATES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site anymore
HENRY E ISAACS QUALITY HOME | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | 2 | 2
J&R SPECIALTIES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2016-05-04 | N/A | 4 | N/A | N/A | N/A | 4 | 4
KELLEY BROS. LLC | S | 15-0303 | 2016-05-04 | N/A | 3 | 3 | N/A | N/A | 2 | 2
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2016-05-04 | 4 | 2 | 4 | 4 | 4 | 2 | 4 | Missing material for Reno
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MESSNER FLOORING RESOURCE | S | 15-0303 | 2016-05-04 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NEW YORK STATE FENCE, INC | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2016-05-04 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OTIS ELEVATOR, USA | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2016-05-04 | 4 | 4 | 4 | 4 | 3 | 3 | 4
ROCK ENVIRONMENTAL | S | 15-0303 | 2016-05-04 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHULER-HAAS | S | 15-0303 | 2016-05-04 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | Great foreman- easy to work with- great communication
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2016-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | 1
UNICO FINISHING SYSTEMS | S | 15-0303 | 2016-05-04 | 4 | 4 | 4 | 4 | 2 | 4 | 4
WILLIAM L. WATSON | S | 15-0303 | 2016-05-04 | 4 | 4 | N/A | 4 | N/A | 3 | N/A
ABJ FIRE PROTECTION CO. | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACPRODUCTS, INC | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIED MECHANICAL | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ANNAS CLEANING SERVICE NY | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B.R. JOHNSON | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BARRY STEEL FABRICATIONS | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRAWDY CONSTRUCTION | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CITY FENCE | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D.C.B. ELEVATOR | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D.V. BROWN & ASSOCIATES | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DESIGN SPECIALISTS INC. | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FERRARO PILE & SHORING |  | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FSR CONTRACTING | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GPI ENGINEERING AND SURVEYING | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRAYCO CORP OF UPSTATE NY | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GYPSUM SYSTEMS, INC. | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J Y R SPECIALITIES, INC | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAIN FORD GEN. SUPPLY | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MURRAY ROOFING COMPANY | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHLAND CONTRACTING | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTIS ELEVATOR, USA | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THE R.E. KRUG CORP | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABJ FIRE PROTECTION CO. | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
ACPRODUCTS, INC | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
ALLIED MECHANICAL | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
ANNAS CLEANING SERVICE NY | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
B.R. JOHNSON | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
BARRY STEEL FABRICATIONS | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
BGI INTERIORS | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
BRAWDY CONSTRUCTION | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
CITY FENCE | S | 15-0314 | 2016-05-06 | 4 | 4 | 4 | 4 | 2 | 3 | 2 | Inexperienced
D.C.B. ELEVATOR | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
D.V. BROWN & ASSOCIATES | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
DDS CONSTRUCTORS, LLC | S | 15-0314 | 2016-05-06 | 5 | 3 | 4 | 3 | 2 | 2 | 2 | overbill on items, communication is OK, no partnership
DESIGN SPECIALISTS INC. | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
FERRARO PILE & SHORING |  | 15-0314 | 2016-05-06 | 5 | 4 | 4 | 4 | 5 | 5 | 5
FLOWER CITY GLASS | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
FSR CONTRACTING | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
GPI ENGINEERING AND SURVEYING | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRAYCO CORP OF UPSTATE NY | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
GYPSUM SYSTEMS, INC. | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
J Y R SPECIALITIES, INC | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J&R SPECIALTIES | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
MAIN FORD GEN. SUPPLY | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
MAX T. DOLAND | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
MURRAY ROOFING COMPANY | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
NORTHLAND CONTRACTING | S | 15-0314 | 2016-05-06 | 5 | 5 | 5 | 5 | 3 | 4 | 4
OTIS ELEVATOR, USA | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
RADEC CORPORATION | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
THE R.E. KRUG CORP | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
WM. B. MORSE LUMBER CO. | S | 15-0314 | 2016-05-06 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
AAC CONTRACTING, INC. | S | 15-0303 | 2016-04-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2016-04-06 | 3 | 4 | 4 | 4 | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2016-04-06 | 4 | 4 | 4 | 4 | N/A | 4 | 4
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2016-04-06 | 4 | 4 | 4 | 4 | 3 | 4 | N/A
BGI INTERIORS | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2016-04-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2016-04-06 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | unresponsive
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0303 | 2016-04-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 15-0303 | 2016-04-06 | 4 | 4 | 4 | 4 | N/A | 3 | 2
GROVER & BATES ASSOCIATES | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site anymore
HENRY E ISAACS QUALITY HOME | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | 2 | 2
J&R SPECIALTIES | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2016-04-06 | N/A | 4 | N/A | N/A | N/A | 4 | 4
KELLEY BROS. LLC | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | Buffalo office
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2016-04-06 | 4 | 2 | 4 | 4 | 4 | 2 | 4 | Missing material for Reno
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MASA ARCHITECTURAL CANOPIES | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MESSNER FLOORING RESOURCE | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2016-04-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OTIS ELEVATOR, USA | S | 15-0303 | 2016-04-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Not on site anymore
RADEC CORPORATION | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2016-04-06 | 4 | 4 | 4 | 4 | 3 | 3 | 4
ROCK ENVIRONMENTAL | S | 15-0303 | 2016-04-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHULER-HAAS | S | 15-0303 | 2016-04-06 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | Great foreman- easy to work with- great communication
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | 1
UNICO FINISHING SYSTEMS | S | 15-0303 | 2016-04-06 | 4 | 4 | 4 | 4 | 2 | 4 | 4
WILLIAM L. WATSON | S | 15-0303 | 2016-04-06 | 4 | 4 | N/A | 4 | N/A | 3 | N/A
84 LUMBER COMPANY | S | 15-0315 | 2016-04-01 | 3 | 3 | 4 | 4 | 4 | 4 | 4
ABJ FIRE PROTECTION CO. | S | 15-0315 | 2016-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 15-0315 | 2016-04-01 | 4 | 4 | 3 | 4 | 4 | 4 | 4
HENRY E ISAACS QUALITY HOME | S | 15-0315 | 2016-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0315 | 2016-04-01 | 4 | 3 | 4 | 4 | 4 | 4 | 4
LANDMARK ELECTRIC INC | S | 15-0315 | 2016-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RAMAR STEEL SALES, INC | S | 15-0315 | 2016-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WOODSTONE EARTH CONSTRUCTION, INC | S | 15-0315 | 2016-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 15-0312 | 2016-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 15-0312 | 2016-04-01 | 4 | 3 | 3 | 4 | 3 | 4 | 4
ES SYSTEMS, INC | S | 15-0312 | 2016-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 15-0312 | 2016-04-01 | 3 | 4 | 4 | 4 | 4 | 4 | 4
IMAGE CITY | S | 15-0312 | 2016-04-01 | 4 | 4 | 4 | 4 | 4 | 4 | 4
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0312 | 2016-04-01 | 4 | 3 | 4 | 3 | 3 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 15-0312 | 2016-04-01 | 4 | 4 | 5 | 4 | 2 | 2 | 2 | Bad at re-submittal process
ADAMS GROUP | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | 3 | 3 | 3
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0310 | 2016-04-06 | 2 | N/A | N/A | N/A | 3 | 3 | 3
BELVEDERE USA | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | 3 | 3 | 4
CLARY'S SITEWORK & DEVELOPMENT | S | 15-0310 | 2016-04-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
COLONIAL CONSTRUCTION CONCRETE | S | 15-0310 | 2016-04-06 | 3 | 4 | 4 | 4 | 4 | 4 | 4
COMMERCIAL PLUMBING SOLUTIONS | S | 15-0310 | 2016-04-06 | 4 | 3 | 3 | 3 | 4 | 3 | 3
COMPREHENSIVE BUILDING ENVELOPE | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | 3
CREATIVE DOOR & MILLWORK | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | 3 | 2 | 2 | PM is overextended. Have gotten district manager to assist
CROWTHER ROOFING & SHEET METAL | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | 4 | 3 | 5
DEKSCAPE | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD SON & COMPANY | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4
EXTREME CARE | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINYL SALES | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FORTUNE ELECTRICAL | S | 15-0310 | 2016-04-06 | 5 | 4 | 4 | 4 | 3 | 4 | 4
FUSION WELDING OF SWFL | S | 15-0310 | 2016-04-06 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Sub was put in default and has been supplemented
GFA INTERNATIONAL | S | 15-0310 | 2016-04-06 | 4 | 4 | 4 | 4 | N/A | N/A | 4
GRATE FIREPLACE AND OUTDOOR | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4
HAMMER FIREPROOFING | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | 3 | 3 | 3
LEE DRYWALL | S | 15-0310 | 2016-04-06 | 4 | 4 | 4 | 4 | 4 | 4 | 5
LIBERTY ALUMINUM | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | 3
MARDALE SPECIALTIES DIRECT | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | 4 | 4 | 4
NAPLES CONCRETE & MASONRY | S | 15-0310 | 2016-04-06 | 4 | 5 | 4 | 5 | 4 | 4 | 4
NATIONAL CONSTRUCTION RENTALS | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | 4
RICE CONTRACTING ENTERPRISES | S | 15-0310 | 2016-04-06 | 4 | 4 | 4 | 4 | 5 | 5 | 5
SAFE SITE CONSULTING | S | 15-0310 | 2016-04-06 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SCHINDLER ELEVATOR | S | 15-0310 | 2016-04-06 | N/A | 2 | N/A | N/A | N/A | 3 | 2 | unresponsive
SERVICE PAINTING OF FLORIDA | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | 3 | 4 | 4
SPRAGGINS MULTI FAMILY | S | 15-0310 | 2016-04-06 | 4 | 4 | 4 | N/A | 3 | N/A | 3
STANLEY ACCESS TECHNOLOGIES | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | 4 | 3
STOUTEN CRAMER | S | 15-0310 | 2016-04-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SUPERIOR FABRICATION | S | 15-0310 | 2016-04-06 | 4 | 5 | 4 | 4 | N/A | N/A | 4
TAILORED FOAM OF FLORIDA | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TERRICK CONSTRUCTION COMPANY | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TROPIX MARBLE COMPANY | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TRUSSWAY MFG. | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | 4 | 3
UNICORN PAINTING INC. | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | 3 | N/A | 4
UNIWASHER | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | 4 | 5 | 5
VALIANT PRODUCTS | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | 4 | 4
VIKING CONSTRUCTION | S | 15-0310 | 2016-04-06 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WARMING TRENDS | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | 4
WAYNE AUTOMATIC FIRE | S | 15-0310 | 2016-04-06 | 4 | 4 | 4 | 4 | N/A | 4 | 4
WHIRLPOOL CORPORATION | S | 15-0310 | 2016-04-06 | N/A | N/A | N/A | N/A | N/A | N/A | 3
711 NEW YORK PAINTING | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACPRODUCTS, INC | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SYSTEMS MAINTENANCE | S | 14-0299 | 2015-12-10 | 4 | 3 | 4 | 4 | 4 | 4 | 4
ALLEN BOULEVARD INTERIORS | S | 14-0299 | 2015-12-10 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | manpower issues
ALLIANCE DOOR & HARDWARE | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | not yet onsite; unresponsive office
AUFIERO PAINTING INDUSTRIES | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0299 | 2015-12-10 | 3 | 3 | 3 | 3 | 4 | 4 | 4
COMMERCIAL FENCE AND RAILING | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWN WATERPROOFING | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D.V. BROWN & ASSOCIATES | S | 14-0299 | 2015-12-10 | 3 | 3 | 3 | 3 | 3 | 3 | 3
DEMCO NEW YORK CORP. | S | 14-0299 | 2015-12-10 | 4 | 2 | 4 | 2 | 4 | 3 | 3 | manpower concerns
DESIGN CONCRETE CORP. | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EZ WAY | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESH MEADOW MECHANICAL CORP | S | 14-0299 | 2015-12-10 | 4 | 5 | 4 | 4 | 4 | 4 | 4
GCSI, LLC | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GE APPLIANCES | S | 14-0299 | 2015-12-10 | 3 | 3 | 3 | 3 | 3 | 3 | 3
HARTCORN PLUMBING & HEAT | S | 14-0299 | 2015-12-10 | 4 | 4 | 4 | 4 | 3 | 4 | 3
HOCKENBERGS EQPT. & SUPPLY | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J.B. HUNT |  | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
K&P FACILITIES MAINTENANCE | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY MASONRY | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LUDWIG J FURTHNER III | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPOLITANO DISTRIBUTING | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 14-0299 | 2015-12-10 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NATIONAL LUMBER | S | 14-0299 | 2015-12-10 | 3 | 2 | 3 | 2 | 3 | 4 | 3 | areas are incomplete
NEW YORK GYPSUM FLOORS | S | 14-0299 | 2015-12-10 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | vehicle safety issues
OLDCASTLE PRECAST | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERHEAD DOOR CO OF GLENS FALL | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLASTER MATERIAL | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER BUILDING & RENOVATIONS | S | 14-0299 | 2015-12-10 | 4 | 3 | 4 | 3 | 3 | 3 | 3
RALPH W. PLOTKE | S | 14-0299 | 2015-12-10 | 3 | 4 | 4 | 4 | 3 | 3 | 3
SCHINDLER ELEVATOR | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 14-0299 | 2015-12-10 | 4 | 4 | 3 | 4 | 4 | N/A | 4
SMART ENERGY SPRAY FOAM | S | 14-0299 | 2015-12-10 | 3 | 3 | 3 | 4 | 3 | 3 | 3
STERLING FLOOR DESIGN | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYR BEAUTY | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRY CONTRACTING & MATERIALS | S | 14-0299 | 2015-12-10 | 3 | 3 | 4 | 3 | 3 | 3 | 2 | office unresponsive
TRIPOINT STONE | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW TREATMENTS BY JEM | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNG & YOUNG | S | 14-0299 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0312 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 15-0312 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0312 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 15-0312 | 2015-12-10 | 3 | 4 | 4 | 4 | 4 | 4 | 4
IMAGE CITY | S | 15-0312 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0312 | 2015-12-10 | 4 | 3 | 4 | 3 | 3 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 15-0312 | 2015-12-10 | 4 | 4 | 5 | 4 | 2 | 2 | 2 | Bad at re-submittal process
84 LUMBER COMPANY | S | 15-0306 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 15-0306 | 2015-12-10 | 4 | 4 | 3 | 4 | N/A | N/A | 2
ART PARTS SIGNS | S | 15-0306 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 15-0306 | 2015-12-10 | 4 | 4 | 3 | 4 | N/A | 4 | 4
DESIGN SPECIALISTS INC. | S | 15-0306 | 2015-12-10 | 4 | 4 | 4 | 4 | N/A | 4 | 4
HENRIETTA BUILDING SUPPLIES, INC. | S | 15-0306 | 2015-12-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
HENRY E ISAACS QUALITY HOME | S | 15-0306 | 2015-12-10 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | have begun to meet target dates. These rating do not reflect sidig grew who is doing great.
INDEPENDENT COMMERCIAL | S | 15-0306 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LIBERTY GLASS AND WINDOW INC. | S | 15-0306 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LOWE'S (CORPORATE ACCOUNT) | S | 15-0306 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Do not use Lowes! Wont provide
MEOLA ENTERPRISES LLC | S | 15-0306 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 15-0306 | 2015-12-10 | 4 | 3 | 3 | 3 | 4 | 4 | 4
PURCELL CONSTRUCTION CORP. | S | 15-0306 | 2015-12-10 | 3 | 4 | 3 | 3 | 3 | 3 | 3
R.E. WOODSON, INC | S | 15-0306 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAYMOND E. KELLEY INC. | S | 15-0306 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RUSTON PAVING CO., INC. | S | 15-0306 | 2015-12-10 | 4 | 3 | 3 | 4 | N/A | 3 | 3
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. |  | 15-0306 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0306 | 2015-12-10 | 3 | 3 | 3 | 3 | 4 | 4 | 4
VP SUPPLY | S | 15-0306 | 2015-12-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WHITE'S LUMBER, INC | S | 15-0306 | 2015-12-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 15-0306 | 2015-12-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | very professional
AAC CONTRACTING, INC. | S | 15-0303 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2015-12-10 | 4 | 2 | N/A | N/A | N/A | N/A | 2 | Poor communication, not returning phone calls or emails
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2015-12-10 | 4 | 2 | 4 | 3 | 4 | 3 | 3
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2015-12-10 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | unresponsive
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2015-12-10 | 4 | 2 | 4 | 4 | 4 | 4 | 4 | only concerned with their own work
ES SYSTEMS, INC | S | 15-0303 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | 2 | 2
GROVER & BATES ASSOCIATES | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site anymore
HENRY E ISAACS QUALITY HOME | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | 2 | 2
J&R SPECIALTIES | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | Buffalo office
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MASA ARCHITECTURAL CANOPIES | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MESSNER FLOORING RESOURCE | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OTIS ELEVATOR, USA | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site anymore
RADEC CORPORATION | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2015-12-10 | 4 | 4 | 4 | 4 | 3 | 3 | 4
ROCK ENVIRONMENTAL | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHULER-HAAS | S | 15-0303 | 2015-12-10 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | Great foreman- easy to work with- great communication
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Wont sign the short-form contract
UNICO FINISHING SYSTEMS | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILLIAM L. WATSON | S | 15-0303 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ADAMS GROUP | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BELVEDERE USA | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CLARY'S SITEWORK & DEVELOPMENT | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COLONIAL CONSTRUCTION CONCRETE | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL PLUMBING SOLUTIONS | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMPREHENSIVE BUILDING ENVELOPE | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CREATIVE DOOR & MILLWORK | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWTHER ROOFING & SHEET METAL | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEKSCAPE | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD SON & COMPANY | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EXTREME CARE | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINYL SALES | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FORTUNE ELECTRICAL | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FUSION WELDING OF SWFL | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GFA INTERNATIONAL | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRATE FIREPLACE AND OUTDOOR | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAMMER FIREPROOFING | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HANNULA LANDSCAPING | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LEE DRYWALL | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY ALUMINUM | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARDALE SPECIALTIES DIRECT | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPLES CONCRETE & MASONRY | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 15-0310 | 2015-12-10 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
RICE CONTRACTING ENTERPRISES | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAFE SITE CONSULTING | S | 15-0310 | 2015-12-10 | 5 | 4 | 4 | 4 | N/A | N/A | 4
SCHINDLER ELEVATOR | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | 3 | 2 | unresponsive
SERVICE PAINTING OF FLORIDA | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPRAGGINS MULTI FAMILY | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STANLEY ACCESS TECHNOLOGIES | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STOUTEN CRAMER | S | 15-0310 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SUPERIOR FABRICATION | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TAILORED FOAM OF FLORIDA | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRICK CONSTRUCTION COMPANY | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TROPIX MARBLE COMPANY | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRUSSWAY MFG. | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICORN PAINTING INC. | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIWASHER | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VALIANT PRODUCTS | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VIKING CONSTRUCTION | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WARMING TRENDS | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAYNE AUTOMATIC FIRE | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0310 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CABLE ELECTRICAL SERVICES | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CLARY'S SITEWORK & DEVELOPMENT | S | 15-0313 | 2015-12-10 | 4 | 4 | 4 | 4 | 3 | 3 | 3
COLONIAL CONSTRUCTION CONCRETE | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL PLUMBING SOLUTIONS | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | 3 | 2 | 3 | no work in field yet. Submittals not per spec.
CROWTHER ROOFING & SHEET METAL | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FORTUNE ELECTRICAL | S | 15-0313 | 2015-12-10 | 5 | 4 | 4 | 4 | 3 | 4 | 4
FUSION WELDING OF SWFL | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAVEN CONTRACTING, INC | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPLES CONCRETE & MASONRY | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 15-0313 | 2015-12-10 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
PEC SURVEYING AND MAPPING | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QP CONSTRUCTION | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | unresponsive
SERVICE PAINTING OF FLORIDA | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STOUTEN CRAMER | S | 15-0313 | 2015-12-10 | 4 | N/A | N/A | N/A | N/A | N/A | N/A
SUNSHINE STATE PLUMBING | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIVERSAL ENGINEERING SCIENCES | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VALIANT PRODUCTS | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WATERWATCH CORPORATION | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAYNE AUTOMATIC FIRE | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WLW CONSTRUCTION | S | 15-0313 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 CONTRACTORS INC. | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0305 | 2015-12-10 | 1 | 1 | 1 | 1 | N/A | 1 | 1 | Hope to never work with this company again. See no benefit to using them. An employee vandalized work from other trades. Don?t pass information down to subcontractors. Unresponsive.
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACPRODUCTS, INC | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | supplier
AIIA CONSTRUCTION COMPANY, INC | S | 15-0305 | 2015-12-10 | 3 | 4 | 4 | 4 | 2 | 3 | 3 | have to remind to wear hard hats, bad change management poor with paperwork
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 3
ALLIED MECHANICAL | S | 15-0305 | 2015-12-10 | 4 | 5 | 4 | 5 | 3 | 3 | 3
ALPHA IRON WORKS, LLC | S | 15-0305 | 2015-12-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BALTZ CONCRETE CONST., INC | S | 15-0305 | 2015-12-10 | 5 | 3 | 5 | 5 | 5 | N/A | 5 | Excellent Safety. Great all around.
BILLONE MECHANICAL CONTRACTORS | S | 15-0305 | 2015-12-10 | 5 | 5 | 4 | 3 | N/A | 5 | 5
BUFFALO CONCRETE ACCESSORIES | S | 15-0305 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CAPITIAL FENCE CO., INC | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATALANO CONTRACTING, INC | S | 15-0305 | 2015-12-10 | 4 | 4 | 4 | 4 | N/A | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0305 | 2015-12-10 | 5 | 4 | 4 | 4 | N/A | 4 | 4
DESIGN POOL & SPA LTD. | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENERGY INSULATION SYSTEMS, INC | S | 15-0305 | 2015-12-10 | 4 | 2 | 3 | 3 | N/A | 4 | 4
FISHER CONCRETE, INC | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GYPSUM SYSTEMS, INC. | S | 15-0305 | 2015-12-10 | 4 | 5 | 5 | 4 | N/A | 3 | 3
HENDERSON-JOHNSON CO.INC. | S | 15-0305 | 2015-12-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY E ISAACS QUALITY HOME | S | 15-0305 | 2015-12-10 | 4 | 4 | 4 | 3 | 4 | 4 | 4
J Y R SPECIALITIES, INC | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J.B. HUNT | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2015-12-10 | 5 | 5 | 4 | 4 | 3 | 2 | 2 | Office is difficult to work with
KLEIN REINFORCING SERVICES | S | 15-0305 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.J. QUIGLIANO | S | 15-0305 | 2015-12-10 | 4 | 5 | 5 | 5 | 2 | 2 | 4
LAKEVIEW LAWN & LANDSCAPE | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 15-0305 | 2015-12-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MIG BUILDING SYSTEMS | S | 15-0305 | 2015-12-10 | 4 | 3 | 3 | 2 | 4 | 3 | 3
MONTGOMERY TRUSS & PANEL (PANELS) | S | 15-0305 | 2015-12-10 | 5 | 5 | 5 | 5 | N/A | 4 | 5
ONTARIO EXTERIORS, INC | S | 15-0305 | 2015-12-10 | 4 | 3 | 4 | 4 | 4 | 4 | 3
PASSERO ASSOCIATES | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2015-12-10 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | improved schedule and manpower when asked; they were very willing to work with the team
SUPERIOR CONTRACTING, INC. | S | 15-0305 | 2015-12-10 | 4 | 4 | 4 | 4 | 4 | 4 | 3
UNICO FINISHING SYSTEMS | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNITED MATERIALS, LLC | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0305 | 2015-12-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 15-0305 | 2015-12-10 | 4 | 4 | 4 | N/A | 4 | 4 | 4
104 CONTRACTORS INC. | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0305 | 2016-01-10 | 1 | 1 | 1 | 1 | N/A | 1 | 1 | Hope to never work with this company again. See no benefit to using them. An employee vandalized work from other trades. Don?t pass information down to subcontractors. Unresponsive.
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACPRODUCTS, INC | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | supplier
AIIA CONSTRUCTION COMPANY, INC | S | 15-0305 | 2016-01-10 | 3 | 4 | 4 | 4 | 2 | 3 | 3 | have to remind to wear hard hats, bad change management poor with paperwork
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 3
ALLIED MECHANICAL | S | 15-0305 | 2016-01-10 | 4 | 5 | 4 | 5 | 3 | 3 | 3
ALPHA IRON WORKS, LLC | S | 15-0305 | 2016-01-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BALTZ CONCRETE CONST., INC | S | 15-0305 | 2016-01-10 | 5 | 3 | 5 | 5 | 5 | N/A | 5 | Excellent Safety. Great all around.
BILLONE MECHANICAL CONTRACTORS | S | 15-0305 | 2016-01-10 | 5 | 5 | 4 | 3 | N/A | 5 | 5
BUFFALO CONCRETE ACCESSORIES | S | 15-0305 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CAPITIAL FENCE CO., INC | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATALANO CONTRACTING, INC | S | 15-0305 | 2016-01-10 | 4 | 4 | 4 | 4 | N/A | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0305 | 2016-01-10 | 5 | 4 | 4 | 4 | N/A | 4 | 4
DESIGN POOL & SPA LTD. | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENERGY INSULATION SYSTEMS, INC | S | 15-0305 | 2016-01-10 | 4 | 2 | 3 | 3 | N/A | 4 | 4
FISHER CONCRETE, INC | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GYPSUM SYSTEMS, INC. | S | 15-0305 | 2016-01-10 | 4 | 5 | 5 | 4 | N/A | 3 | 3
HENDERSON-JOHNSON CO.INC. | S | 15-0305 | 2016-01-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY E ISAACS QUALITY HOME | S | 15-0305 | 2016-01-10 | 4 | 4 | 4 | 3 | 4 | 4 | 4
J Y R SPECIALITIES, INC | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J.B. HUNT | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOHNSON & JOHNSON CONSTRUCTION | S | 15-0305 | 2016-01-10 | 3 | 3 | 3 | 3 | 3 | N/A | 1 | Actual in-house crews are good. Did improve after we voiced our discontent
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2016-01-10 | 5 | 5 | 4 | 4 | 3 | 2 | 2 | Office is difficult to work with
KLEIN REINFORCING SERVICES | S | 15-0305 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.J. QUIGLIANO | S | 15-0305 | 2016-01-10 | 4 | 5 | 5 | 5 | 2 | 2 | 4
LAKEVIEW LAWN & LANDSCAPE | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 15-0305 | 2016-01-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MIG BUILDING SYSTEMS | S | 15-0305 | 2016-01-10 | 4 | 3 | 3 | 2 | 4 | 3 | 3
MONTGOMERY TRUSS & PANEL (PANELS) | S | 15-0305 | 2016-01-10 | 5 | 5 | 5 | 5 | N/A | 4 | 5
ONTARIO EXTERIORS, INC | S | 15-0305 | 2016-01-10 | 4 | 3 | 4 | 4 | 4 | 4 | 3
PASSERO ASSOCIATES | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2016-01-10 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | improved schedule and manpower when asked; they were very willing to work with the team
S.A.B. SPECIALTIES | S | 15-0305 | 2016-01-10 | 2 | 4 | 4 | 5 | 4 | N/A | 4
SUPERIOR CONTRACTING, INC. | S | 15-0305 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 3
UNICO FINISHING SYSTEMS | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNITED MATERIALS, LLC | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0305 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 15-0305 | 2016-01-10 | 4 | 4 | 4 | N/A | 4 | 4 | 4
104 CONTRACTORS INC. | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0305 | 2016-02-10 | 1 | 1 | 1 | 1 | N/A | 1 | 1 | Hope to never work with this company again. See no benefit to using them. An employee vandalized work from other trades. Don?t pass information down to subcontractors. Unresponsive.
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2016-02-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACPRODUCTS, INC | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | supplier
AIIA CONSTRUCTION COMPANY, INC | S | 15-0305 | 2016-02-10 | 3 | 4 | 4 | 4 | 2 | 3 | 3 | have to remind to wear hard hats, bad change management poor with paperwork
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2016-02-10 | 4 | 4 | 4 | 4 | 4 | 4 | 3
ALLIED MECHANICAL | S | 15-0305 | 2016-02-10 | 4 | 5 | 4 | 5 | 3 | 3 | 3
ALPHA IRON WORKS, LLC | S | 15-0305 | 2016-02-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BALTZ CONCRETE CONST., INC | S | 15-0305 | 2016-02-10 | 5 | 3 | 5 | 5 | 5 | N/A | 5 | Excellent Safety. Great all around.
BILLONE MECHANICAL CONTRACTORS | S | 15-0305 | 2016-02-10 | 5 | 5 | 4 | 3 | N/A | 5 | 5
BUFFALO CONCRETE ACCESSORIES | S | 15-0305 | 2016-02-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CAPITIAL FENCE CO., INC | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATALANO CONTRACTING, INC | S | 15-0305 | 2016-02-10 | 4 | 4 | 4 | 4 | N/A | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0305 | 2016-02-10 | 5 | 4 | 4 | 4 | N/A | 4 | 4
DESIGN POOL & SPA LTD. | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENERGY INSULATION SYSTEMS, INC | S | 15-0305 | 2016-02-10 | 4 | 2 | 3 | 3 | N/A | 4 | 4
FISHER CONCRETE, INC | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GYPSUM SYSTEMS, INC. | S | 15-0305 | 2016-02-10 | 4 | 5 | 5 | 4 | N/A | 3 | 3
HENDERSON-JOHNSON CO.INC. | S | 15-0305 | 2016-02-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY E ISAACS QUALITY HOME | S | 15-0305 | 2016-02-10 | 4 | 4 | 4 | 3 | 4 | 4 | 4
J Y R SPECIALITIES, INC | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J.B. HUNT | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOHNSON & JOHNSON CONSTRUCTION | S | 15-0305 | 2016-02-10 | 3 | 1 | 3 | 3 | 1 | N/A | N/A | Never want to work with again.
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2016-02-10 | 5 | 5 | 4 | 4 | 3 | 2 | 2 | Office is difficult to work with
KLEIN REINFORCING SERVICES | S | 15-0305 | 2016-02-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 15-0305 | 2016-02-10 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | Clean up and communication is terrible.
L.J. QUIGLIANO | S | 15-0305 | 2016-02-10 | 4 | 5 | 5 | 5 | 2 | 2 | 4
LAKEVIEW LAWN & LANDSCAPE | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 15-0305 | 2016-02-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MIG BUILDING SYSTEMS | S | 15-0305 | 2016-02-10 | 4 | 3 | 3 | 2 | 4 | 3 | 3
MONTGOMERY TRUSS & PANEL (PANELS) | S | 15-0305 | 2016-02-10 | 5 | 5 | 5 | 5 | N/A | 4 | 5
ONTARIO EXTERIORS, INC | S | 15-0305 | 2016-02-10 | 4 | 3 | 4 | 4 | 4 | 4 | 3
PASSERO ASSOCIATES | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2016-02-10 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | improved schedule and manpower when asked; they were very willing to work with the team
S.A.B. SPECIALTIES | S | 15-0305 | 2016-02-10 | 2 | 4 | 4 | 5 | 4 | N/A | 4
SUPERIOR CONTRACTING, INC. | S | 15-0305 | 2016-02-10 | 4 | 4 | 4 | 4 | 4 | 4 | 3
UNICO FINISHING SYSTEMS | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNITED MATERIALS, LLC | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0305 | 2016-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 15-0305 | 2016-02-10 | 4 | 4 | 4 | N/A | 4 | 4 | 4
PETERSON BUILDERS FRAMING | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PASSERO ASSOCIATES | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ONTARIO EXTERIORS, INC | S | 15-0305 | 2016-03-10 | 4 | 3 | 4 | 4 | 4 | 4 | 3
MONTGOMERY TRUSS & PANEL (PANELS) | S | 15-0305 | 2016-03-10 | 5 | 5 | 5 | 5 | N/A | 4 | 5
MAX T. DOLAND | S | 15-0305 | 2016-03-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MIG BUILDING SYSTEMS | S | 15-0305 | 2016-03-10 | 4 | 3 | 3 | 2 | 4 | 3 | 3
LAKEVIEW LAWN & LANDSCAPE | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L.J. QUIGLIANO | S | 15-0305 | 2016-03-10 | 4 | 5 | 5 | 5 | 2 | 2 | 4
L.A.PAINTING, INC. | S | 15-0305 | 2016-03-10 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | Clean up and communication is terrible.
KLEIN REINFORCING SERVICES | S | 15-0305 | 2016-03-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2016-03-10 | 5 | 5 | 4 | 4 | 3 | 2 | 5 | New contact in office; very proactive
JOHNSON & JOHNSON CONSTRUCTION | S | 15-0305 | 2016-03-10 | 3 | 1 | 3 | 3 | 1 | N/A | N/A | Never want to work with again.
J.B. HUNT | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J Y R SPECIALITIES, INC | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0305 | 2016-03-10 | 4 | 4 | 4 | 3 | 4 | 4 | 4
HENDERSON-JOHNSON CO.INC. | S | 15-0305 | 2016-03-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
GYPSUM SYSTEMS, INC. | S | 15-0305 | 2016-03-10 | 4 | 5 | 5 | 4 | N/A | 3 | 3
FISHER CONCRETE, INC | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENERGY INSULATION SYSTEMS, INC | S | 15-0305 | 2016-03-10 | 4 | 2 | 3 | 3 | N/A | 4 | 4
DESIGN POOL & SPA LTD. | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0305 | 2016-03-10 | 5 | 4 | 4 | 4 | N/A | 4 | 4
CATALANO CONTRACTING, INC | S | 15-0305 | 2016-03-10 | 4 | 4 | 4 | 4 | N/A | 4 | 4
CAPITIAL FENCE CO., INC | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUFFALO CONCRETE ACCESSORIES | S | 15-0305 | 2016-03-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
BILLONE MECHANICAL CONTRACTORS | S | 15-0305 | 2016-03-10 | 5 | 5 | 4 | 3 | N/A | 5 | 5
BALTZ CONCRETE CONST., INC | S | 15-0305 | 2016-03-10 | 5 | 3 | 5 | 5 | 5 | N/A | 5 | Excellent Safety. Great all around.
ALPHA IRON WORKS, LLC | S | 15-0305 | 2016-03-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5
ALLIED MECHANICAL | S | 15-0305 | 2016-03-10 | 4 | 5 | 4 | 5 | 3 | 3 | 3
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2016-03-10 | 4 | 4 | 4 | 4 | 4 | 4 | 3
AIIA CONSTRUCTION COMPANY, INC | S | 15-0305 | 2016-03-10 | 3 | 4 | 4 | 4 | 2 | 3 | 3 | have to remind to wear hard hats, bad change management poor with paperwork
ACPRODUCTS, INC | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | supplier
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2016-03-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
84 LUMBER COMPANY | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
104 CONTRACTORS INC. | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2016-03-10 | 4 | 4 | 4 | 4 | 3 | 2 | 3 | improved schedule and manpower when asked; they were very willing to work with the team
S.A.B. SPECIALTIES | S | 15-0305 | 2016-03-10 | 2 | 4 | 4 | 5 | 4 | N/A | 4
SUPERIOR CONTRACTING, INC. | S | 15-0305 | 2016-03-10 | 4 | 4 | 4 | 4 | 4 | 4 | 3
UNICO FINISHING SYSTEMS | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNITED MATERIALS, LLC | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0305 | 2016-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 15-0305 | 2016-03-10 | 4 | 4 | 4 | N/A | 4 | 4 | 4
ADAMS GROUP | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BELVEDERE USA | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CLARY'S SITEWORK & DEVELOPMENT | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COLONIAL CONSTRUCTION CONCRETE | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL PLUMBING SOLUTIONS | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMPREHENSIVE BUILDING ENVELOPE | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CREATIVE DOOR & MILLWORK | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWTHER ROOFING & SHEET METAL | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEKSCAPE | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD SON & COMPANY | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EXTREME CARE | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINYL SALES | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FORTUNE ELECTRICAL | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FUSION WELDING OF SWFL | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GFA INTERNATIONAL | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRATE FIREPLACE AND OUTDOOR | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAMMER FIREPROOFING | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HANNULA LANDSCAPING | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LEE DRYWALL | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY ALUMINUM | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARDALE SPECIALTIES DIRECT | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPLES CONCRETE & MASONRY | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 15-0310 | 2016-01-10 | 3 | N/A | N/A | N/A | N/A | N/A | N/A
RICE CONTRACTING ENTERPRISES | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAFE SITE CONSULTING | S | 15-0310 | 2016-01-10 | 5 | 4 | 4 | 4 | N/A | N/A | 4
SCHINDLER ELEVATOR | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | 3 | 2 | unresponsive
SERVICE PAINTING OF FLORIDA | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPRAGGINS MULTI FAMILY | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STANLEY ACCESS TECHNOLOGIES | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STOUTEN CRAMER | S | 15-0310 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SUPERIOR FABRICATION | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TAILORED FOAM OF FLORIDA | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRICK CONSTRUCTION COMPANY | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TROPIX MARBLE COMPANY | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRUSSWAY MFG. | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICORN PAINTING INC. | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIWASHER | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VALIANT PRODUCTS | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VIKING CONSTRUCTION | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WARMING TRENDS | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAYNE AUTOMATIC FIRE | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0310 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AAC CONTRACTING, INC. | S | 15-0303 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2016-01-10 | 4 | 2 | N/A | N/A | N/A | N/A | 2 | Poor communication, not returning phone calls or emails
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2016-01-10 | 4 | 2 | 4 | 3 | 4 | 3 | 3
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2016-01-10 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | unresponsive
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2016-01-10 | 4 | 2 | 4 | 4 | 4 | 4 | 4 | only concerned with their own work
ES SYSTEMS, INC | S | 15-0303 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | 2 | 2
GROVER & BATES ASSOCIATES | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site anymore
HENRY E ISAACS QUALITY HOME | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | 2 | 2
J&R SPECIALTIES | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | Buffalo office
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MASA ARCHITECTURAL CANOPIES | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MESSNER FLOORING RESOURCE | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OTIS ELEVATOR, USA | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Not on site anymore
RADEC CORPORATION | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2016-01-10 | 4 | 4 | 4 | 4 | 3 | 3 | 4
ROCK ENVIRONMENTAL | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHULER-HAAS | S | 15-0303 | 2016-01-10 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | Great foreman- easy to work with- great communication
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Wont sign the short-form contract
UNICO FINISHING SYSTEMS | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WILLIAM L. WATSON | S | 15-0303 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0315 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABJ FIRE PROTECTION CO. | S | 15-0315 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 15-0315 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0315 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0315 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LANDMARK ELECTRIC INC | S | 15-0315 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAMAR STEEL SALES, INC | S | 15-0315 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODSTONE EARTH CONSTRUCTION, INC | S | 15-0315 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0306 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 15-0306 | 2016-01-10 | 4 | 4 | 3 | 4 | N/A | N/A | 2
ART PARTS SIGNS | S | 15-0306 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 15-0306 | 2016-01-10 | 4 | 4 | 3 | 4 | N/A | 4 | 4
DESIGN SPECIALISTS INC. | S | 15-0306 | 2016-01-10 | 4 | 4 | 4 | 4 | N/A | 4 | 4
HENRIETTA BUILDING SUPPLIES, INC. | S | 15-0306 | 2016-01-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
HENRY E ISAACS QUALITY HOME | S | 15-0306 | 2016-01-10 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | have begun to meet target dates. These rating do not reflect sidig grew who is doing great.
INDEPENDENT COMMERCIAL | S | 15-0306 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LIBERTY GLASS AND WINDOW INC. | S | 15-0306 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LOWE'S (CORPORATE ACCOUNT) | S | 15-0306 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Do not use Lowes! Wont provide
MEOLA ENTERPRISES LLC | S | 15-0306 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 15-0306 | 2016-01-10 | 4 | 3 | 3 | 3 | 4 | 4 | 4
PURCELL CONSTRUCTION CORP. | S | 15-0306 | 2016-01-10 | 3 | 4 | 3 | 3 | 3 | 3 | 3
R.E. WOODSON, INC | S | 15-0306 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAYMOND E. KELLEY INC. | S | 15-0306 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RUSTON PAVING CO., INC. | S | 15-0306 | 2016-01-10 | 4 | 3 | 3 | 4 | N/A | 3 | 3
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. |  | 15-0306 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0306 | 2016-01-10 | 3 | 3 | 3 | 3 | 4 | 4 | 4
VP SUPPLY | S | 15-0306 | 2016-01-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WHITE'S LUMBER, INC | S | 15-0306 | 2016-01-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 15-0306 | 2016-01-10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | very professional
AAC CONTRACTING, INC. | S | 15-0312 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 15-0312 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0312 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 15-0312 | 2016-01-10 | 3 | 4 | 4 | 4 | 4 | 4 | 4
IMAGE CITY | S | 15-0312 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0312 | 2016-01-10 | 4 | 3 | 4 | 3 | 3 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 15-0312 | 2016-01-10 | 4 | 4 | 5 | 4 | 2 | 2 | 2 | Bad at re-submittal process
AAC CONTRACTING, INC. | S | 14-0289 | 2016-01-10 | N/A | N/A | N/A | 4 | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0289 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
B&L WHOLESALE | S | 14-0289 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | 4 | 3
BENEDETTI BUILDERS | S | 14-0289 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
BSR | S | 14-0289 | 2016-01-10 | 2 | 2 | 3 | 1 | 3 | 3 | 3 | office over-promises; company should not be used for siding
CATENARY CONSTRUCTION CORP. | S | 14-0289 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAYUGA LANDSCAPE | S | 14-0289 | 2016-01-10 | 3 | 4 | 3 | 4 | 3 | 2 | 4
COMFORT SYSTEMS (SYRACUSE) | S | 14-0289 | 2016-01-10 | 4 | 3 | 4 | 4 | 4 | 4 | 4
D & R JONES CONSTRUCTION | S | 14-0289 | 2016-01-10 | 3 | 3 | 4 | 4 | 3 | 4 | 2 | do not provide adequate manpower but provided it after veing pushed
EZ WAY | S | 14-0289 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0289 | 2016-01-10 | 2 | 1 | 3 | 3 | N/A | 2 | 2 | Do not know their scope; Having issues with the PM - Mark Webster
GERHARZ EQUIPMENT | S | 14-0289 | 2016-01-10 | 2 | 2 | 3 | 2 | N/A | 2 | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0289 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
INNOVATIVE WINDOWEAR | S | 14-0289 | 2016-01-10 | 3 | 3 | 3 | 3 | N/A | 3 | 3
JOHN C. LOWERY | S | 14-0289 | 2016-01-10 | 4 | 4 | 4 | 3 | 3 | 4 | 3
KELLY BROS. | S | 14-0289 | 2016-01-10 | N/A | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 14-0289 | 2016-01-10 | 3 | 4 | 4 | 4 | 2 | 3 | 2
LEMOYNE INTERIORS, INC. | S | 14-0289 | 2016-01-10 | 4 | 4 | 4 | 4 | 2 | 3 | 4
LRS COMPANIES | S | 14-0289 | 2016-01-10 | 2 | 3 | 4 | 3 | 4 | 4 | 4
MCPHERSON BUILDERS | S | 14-0289 | 2016-01-10 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | Very reliable
MOD SPACE | S | 14-0289 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL LUMBER | S | 14-0289 | 2016-01-10 | 1 | 1 | 2 | 2 | N/A | N/A | N/A | offsite
PLEASANT VALLEY ELEC. | S | 14-0289 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER UTILITY SVC. | S | 14-0289 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0289 | 2016-01-10 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | pedal for TM tickets
RADEC CORPORATION | S | 14-0289 | 2016-01-10 | 4 | 3 | 4 | 3 | 3 | 2 | 3 | piecemeal submittals; unorganized and incomplete; not following 3wk schedule
RAULLI Y SONS, INC. | S | 14-0289 | 2016-01-10 | 4 | 4 | 4 | 4 | N/A | 4 | 5
SCHINDLER ELEVATOR | S | 14-0289 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SHEPARDVILLE |  | 14-0289 | 2016-01-10 | 3 | 3 | 3 | 3 | 3 | N/A | 3
TG MILLER | S | 14-0289 | 2016-01-10 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Layout only
THE BRAIN DRAIN | S | 14-0289 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 14-0289 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2016-01-10 | 3 | 3 | 3 | 3 | 3 | 3 | 3
711 NEW YORK PAINTING | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACPRODUCTS, INC | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SYSTEMS MAINTENANCE | S | 14-0299 | 2016-01-10 | 4 | 3 | 4 | 4 | 4 | 4 | 4
ALLEN BOULEVARD INTERIORS | S | 14-0299 | 2016-01-10 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | manpower issues
ALLIANCE DOOR & HARDWARE | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | not yet onsite; unresponsive office
AUFIERO PAINTING INDUSTRIES | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0299 | 2016-01-10 | 3 | 3 | 3 | 3 | 4 | 4 | 4
COMMERCIAL FENCE AND RAILING | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWN WATERPROOFING | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D.V. BROWN & ASSOCIATES | S | 14-0299 | 2016-01-10 | 3 | 3 | 3 | 3 | 3 | 3 | 3
DEMCO NEW YORK CORP. | S | 14-0299 | 2016-01-10 | 4 | 2 | 4 | 2 | 4 | 3 | 3 | manpower concerns
DESIGN CONCRETE CORP. | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EZ WAY | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESH MEADOW MECHANICAL CORP | S | 14-0299 | 2016-01-10 | 4 | 5 | 4 | 4 | 4 | 4 | 4
GCSI, LLC | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GE APPLIANCES | S | 14-0299 | 2016-01-10 | 3 | 3 | 3 | 3 | 3 | 3 | 3
HARTCORN PLUMBING & HEAT | S | 14-0299 | 2016-01-10 | 4 | 4 | 4 | 4 | 3 | 4 | 3
HOCKENBERGS EQPT. & SUPPLY | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J.B. HUNT |  | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
K&P FACILITIES MAINTENANCE | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY MASONRY | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LUDWIG J FURTHNER III | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPOLITANO DISTRIBUTING | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 14-0299 | 2016-01-10 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NATIONAL LUMBER | S | 14-0299 | 2016-01-10 | 3 | 2 | 3 | 2 | 3 | 4 | 3 | areas are incomplete
NEW YORK GYPSUM FLOORS | S | 14-0299 | 2016-01-10 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | vehicle safety issues
OLDCASTLE PRECAST | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERHEAD DOOR CO OF GLENS FALL | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLASTER MATERIAL | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER BUILDING & RENOVATIONS | S | 14-0299 | 2016-01-10 | 4 | 3 | 4 | 3 | 3 | 3 | 3
RALPH W. PLOTKE | S | 14-0299 | 2016-01-10 | 3 | 4 | 4 | 4 | 3 | 3 | 3
SCHINDLER ELEVATOR | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 14-0299 | 2016-01-10 | 4 | 4 | 3 | 4 | 4 | N/A | 4
SMART ENERGY SPRAY FOAM | S | 14-0299 | 2016-01-10 | 3 | 3 | 3 | 4 | 3 | 3 | 3
STERLING FLOOR DESIGN | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYR BEAUTY | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRY CONTRACTING & MATERIALS | S | 14-0299 | 2016-01-10 | 3 | 3 | 4 | 3 | 3 | 3 | 2 | office unresponsive
TRIPOINT STONE | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW TREATMENTS BY JEM | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNG & YOUNG | S | 14-0299 | 2016-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CABLE ELECTRICAL SERVICES | S | 15-0313 | 2016-02-13 | 2 | 4 | 4 | 3 | N/A | 4 | 4
CLARY'S SITEWORK & DEVELOPMENT | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COLONIAL CONSTRUCTION CONCRETE | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL PLUMBING SOLUTIONS | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWTHER ROOFING & SHEET METAL | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FORTUNE ELECTRICAL | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FUSION WELDING OF SWFL | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAVEN CONTRACTING, INC | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPLES CONCRETE & MASONRY | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PEC SURVEYING AND MAPPING | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QP CONSTRUCTION | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERVICE PAINTING OF FLORIDA | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STOUTEN CRAMER | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUNSHINE STATE PLUMBING | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIVERSAL ENGINEERING SCIENCES | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VALIANT PRODUCTS | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WATERWATCH CORPORATION | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAYNE AUTOMATIC FIRE | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0313 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WLW CONSTRUCTION | S | 15-0313 | 2016-02-13 | 4 | 4 | 4 | 5 | N/A | 2 | 2 | very weak on providing paper
ADAMS GROUP | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | 3 | 3 | 3
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | 3 | 3 | 3
BELVEDERE USA | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | 3 | 3 | 3
CLARY'S SITEWORK & DEVELOPMENT | S | 15-0310 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 3
COLONIAL CONSTRUCTION CONCRETE | S | 15-0310 | 2016-02-13 | 3 | 4 | 4 | 4 | 4 | 4 | 4
COMMERCIAL PLUMBING SOLUTIONS | S | 15-0310 | 2016-02-13 | 4 | 3 | 3 | 3 | 3 | 3 | 3
COMPREHENSIVE BUILDING ENVELOPE | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | 3
CREATIVE DOOR & MILLWORK | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | 3 | 2 | 2 | PM is overextended. Have gotten district manager to assist
CROWTHER ROOFING & SHEET METAL | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | 4 | 3 | 5
DEKSCAPE | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD SON & COMPANY | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | 4 | 4
EXTREME CARE | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINYL SALES | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FORTUNE ELECTRICAL | S | 15-0310 | 2016-02-13 | 5 | 4 | 4 | 4 | 3 | 4 | 4
FUSION WELDING OF SWFL | S | 15-0310 | 2016-02-13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Sub was put in default and has been supplemented
GFA INTERNATIONAL | S | 15-0310 | 2016-02-13 | 4 | 4 | 4 | 4 | N/A | N/A | 4
GRATE FIREPLACE AND OUTDOOR | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | 4 | 4
HAMMER FIREPROOFING | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | 3 | 3 | 3
LEE DRYWALL | S | 15-0310 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 5
LIBERTY ALUMINUM | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | 3
MARDALE SPECIALTIES DIRECT | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | 4 | 4 | 4
NAPLES CONCRETE & MASONRY | S | 15-0310 | 2016-02-13 | 4 | 5 | 4 | 5 | 4 | 4 | 4
NATIONAL CONSTRUCTION RENTALS | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | 4
RICE CONTRACTING ENTERPRISES | S | 15-0310 | 2016-02-13 | 4 | 4 | 4 | 4 | 5 | 5 | 5
SAFE SITE CONSULTING | S | 15-0310 | 2016-02-13 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SCHINDLER ELEVATOR | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | 3 | 2 | unresponsive
SERVICE PAINTING OF FLORIDA | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | 3 | 4 | 4
SPRAGGINS MULTI FAMILY | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | 3 | N/A | 3
STANLEY ACCESS TECHNOLOGIES | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | 4 | 3
STOUTEN CRAMER | S | 15-0310 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SUPERIOR FABRICATION | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TAILORED FOAM OF FLORIDA | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TERRICK CONSTRUCTION COMPANY | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TROPIX MARBLE COMPANY | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TRUSSWAY MFG. | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | 4 | 3
UNICORN PAINTING INC. | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | 3 | N/A | 4
UNIWASHER | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | 4 | 5 | 5
VALIANT PRODUCTS | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | 4 | 4
VIKING CONSTRUCTION | S | 15-0310 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WARMING TRENDS | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | 4
WAYNE AUTOMATIC FIRE | S | 15-0310 | 2016-02-13 | 4 | 4 | 4 | 4 | N/A | 4 | 4
WHIRLPOOL CORPORATION | S | 15-0310 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | 3
AAC CONTRACTING, INC. | S | 15-0303 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2016-02-13 | 4 | 4 | 3 | 4 | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2016-02-13 | 4 | 2 | 3 | 3 | N/A | N/A | 2
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2016-02-13 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | unresponsive
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2016-02-13 | 4 | 2 | 4 | 4 | 4 | 4 | 4 | only concerned with their own work
ES SYSTEMS, INC | S | 15-0303 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | 2 | 2
GROVER & BATES ASSOCIATES | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | 2 | 2
J&R SPECIALTIES | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | Buffalo office
KELLEY BROS. LLC | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | no longer onsite
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MASA ARCHITECTURAL CANOPIES | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MESSNER FLOORING RESOURCE | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OTIS ELEVATOR, USA | S | 15-0303 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2016-02-13 | 4 | 4 | 4 | 4 | 3 | 3 | 4
ROCK ENVIRONMENTAL | S | 15-0303 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHULER-HAAS | S | 15-0303 | 2016-02-13 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | Great foreman- easy to work with- great communication
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Wont sign the short-form contract
UNICO FINISHING SYSTEMS | S | 15-0303 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WILLIAM L. WATSON | S | 15-0303 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0315 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABJ FIRE PROTECTION CO. | S | 15-0315 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 15-0315 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HENRY E ISAACS QUALITY HOME | S | 15-0315 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0315 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LANDMARK ELECTRIC INC | S | 15-0315 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAMAR STEEL SALES, INC | S | 15-0315 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WOODSTONE EARTH CONSTRUCTION, INC | S | 15-0315 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
84 LUMBER COMPANY | S | 15-0306 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGAPE WHOLESALE FURNITURE | S | 15-0306 | 2016-02-13 | 4 | 4 | 3 | 4 | N/A | N/A | 2
ART PARTS SIGNS | S | 15-0306 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEMCO NEW YORK CORP. | S | 15-0306 | 2016-02-13 | 4 | 4 | 3 | 4 | N/A | 4 | 4
DESIGN SPECIALISTS INC. | S | 15-0306 | 2016-02-13 | 4 | 4 | 4 | 4 | N/A | 4 | 4
HENRIETTA BUILDING SUPPLIES, INC. | S | 15-0306 | 2016-02-13 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
HENRY E ISAACS QUALITY HOME | S | 15-0306 | 2016-02-13 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | have begun to meet target dates. These rating do not reflect sidig grew who is doing great.
INDEPENDENT COMMERCIAL | S | 15-0306 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LIBERTY GLASS AND WINDOW INC. | S | 15-0306 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LOWE'S (CORPORATE ACCOUNT) | S | 15-0306 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Do not use Lowes! Wont provide insurances
MEOLA ENTERPRISES LLC | S | 15-0306 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
PRO CARPET INC. | S | 15-0306 | 2016-02-13 | 4 | 3 | 3 | 3 | 4 | 4 | 4
PURCELL CONSTRUCTION CORP. | S | 15-0306 | 2016-02-13 | 3 | 4 | 3 | 3 | 3 | 3 | 3
R.E. WOODSON, INC | S | 15-0306 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAYMOND E. KELLEY INC. | S | 15-0306 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RUSTON PAVING CO., INC. | S | 15-0306 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUSQUEHANNA SHEET METAL ERECTION SERVICES INC. |  | 15-0306 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0306 | 2016-02-13 | 3 | 3 | 3 | 3 | 4 | 4 | 4
VP SUPPLY | S | 15-0306 | 2016-02-13 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WHITE'S LUMBER, INC | S | 15-0306 | 2016-02-13 | N/A | 4 | 4 | 4 | 4 | 4 | 4 | supplier
WOODCOCK & ARMANI MECHANICAL CONTRACTORS | S | 15-0306 | 2016-02-13 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | very professional
AAC CONTRACTING, INC. | S | 15-0312 | 2016-02-13 | N/A | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 15-0312 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0312 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 15-0312 | 2016-02-13 | 3 | 4 | 4 | 4 | 4 | 4 | 4
IMAGE CITY | S | 15-0312 | 2016-02-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0312 | 2016-02-13 | 4 | 3 | 4 | 3 | 3 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 15-0312 | 2016-02-13 | 4 | 4 | 5 | 4 | 3 | 2 | 2 | Bad at re-submittal process
711 NEW YORK PAINTING | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ACPRODUCTS, INC | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALL SYSTEMS MAINTENANCE | S | 14-0299 | 2016-02-13 | 4 | 3 | 4 | 4 | 4 | 4 | 4
ALLEN BOULEVARD INTERIORS | S | 14-0299 | 2016-02-13 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | manpower issues
ALLIANCE DOOR & HARDWARE | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | not yet onsite; unresponsive office
AUFIERO PAINTING INDUSTRIES | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B&L WHOLESALE | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGI INTERIORS | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMFORT SYSTEMS (SYRACUSE) | S | 14-0299 | 2016-02-13 | 3 | 3 | 3 | 3 | 4 | 4 | 4
COMMERCIAL FENCE AND RAILING | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWN WATERPROOFING | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D.V. BROWN & ASSOCIATES | S | 14-0299 | 2016-02-13 | 3 | 3 | 3 | 3 | 3 | 3 | 3
DEMCO NEW YORK CORP. | S | 14-0299 | 2016-02-13 | 4 | 2 | 4 | 2 | 4 | 3 | 3 | manpower concerns
DESIGN CONCRETE CORP. | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EZ WAY | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FRESH MEADOW MECHANICAL CORP | S | 14-0299 | 2016-02-13 | 4 | 5 | 4 | 4 | 4 | 4 | 4
GCSI, LLC | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GE APPLIANCES | S | 14-0299 | 2016-02-13 | 3 | 3 | 3 | 3 | 3 | 3 | 3
HARTCORN PLUMBING & HEAT | S | 14-0299 | 2016-02-13 | 4 | 4 | 4 | 4 | 3 | 4 | 3
HOCKENBERGS EQPT. & SUPPLY | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J.B. HUNT |  | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
K&P FACILITIES MAINTENANCE | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIBERTY MASONRY | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LUDWIG J FURTHNER III | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPOLITANO DISTRIBUTING | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 14-0299 | 2016-02-13 | 3 | 3 | 3 | 3 | 3 | 3 | 3
NATIONAL LUMBER | S | 14-0299 | 2016-02-13 | 3 | 2 | 3 | 2 | 3 | 4 | 3 | areas are incomplete
NEW YORK GYPSUM FLOORS | S | 14-0299 | 2016-02-13 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | vehicle safety issues
OLDCASTLE PRECAST | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERHEAD DOOR CO OF GLENS FALL | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLASTER MATERIAL | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PREMIER BUILDING & RENOVATIONS | S | 14-0299 | 2016-02-13 | 4 | 3 | 4 | 3 | 3 | 3 | 3
RALPH W. PLOTKE | S | 14-0299 | 2016-02-13 | 3 | 4 | 4 | 4 | 3 | 3 | 3
SCHINDLER ELEVATOR | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHEPARDVILLE | S | 14-0299 | 2016-02-13 | 4 | 4 | 3 | 4 | 4 | N/A | 4
SMART ENERGY SPRAY FOAM | S | 14-0299 | 2016-02-13 | 3 | 3 | 3 | 4 | 3 | 3 | 3
STERLING FLOOR DESIGN | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYR BEAUTY | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TERRY CONTRACTING & MATERIALS | S | 14-0299 | 2016-02-13 | 3 | 3 | 4 | 3 | 3 | 3 | 2 | office unresponsive
TRIPOINT STONE | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WINDOW TREATMENTS BY JEM | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WM. B. MORSE LUMBER CO. | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YOUNG & YOUNG | S | 14-0299 | 2016-02-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0313 | 2016-03-13 | 2 | 4 | 4 | 3 | N/A | 4 | 4
CABLE ELECTRICAL SERVICES | S | 15-0313 | 2016-03-13 | 2 | 4 | 4 | 3 | N/A | 4 | 4
CLARY'S SITEWORK & DEVELOPMENT | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COLONIAL CONSTRUCTION CONCRETE | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL PLUMBING SOLUTIONS | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWTHER ROOFING & SHEET METAL | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FORTUNE ELECTRICAL | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FUSION WELDING OF SWFL | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAVEN CONTRACTING, INC | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAPLES CONCRETE & MASONRY | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PEC SURVEYING AND MAPPING | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QP CONSTRUCTION | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERVICE PAINTING OF FLORIDA | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STOUTEN CRAMER | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUNSHINE STATE PLUMBING | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNIVERSAL ENGINEERING SCIENCES | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VALIANT PRODUCTS | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WATERWATCH CORPORATION | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAYNE AUTOMATIC FIRE | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0313 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WLW CONSTRUCTION | S | 15-0313 | 2016-03-13 | 4 | 4 | 4 | 5 | N/A | 2 | 2 | very weak on providing paper
ADAMS GROUP | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | 3 | 3 | 3
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | 3 | 3 | 3
BELVEDERE USA | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | 3 | 3 | 3
CLARY'S SITEWORK & DEVELOPMENT | S | 15-0310 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 3
COLONIAL CONSTRUCTION CONCRETE | S | 15-0310 | 2016-03-13 | 3 | 4 | 4 | 4 | 4 | 4 | 4
COMMERCIAL PLUMBING SOLUTIONS | S | 15-0310 | 2016-03-13 | 4 | 3 | 3 | 3 | 3 | 3 | 3
COMPREHENSIVE BUILDING ENVELOPE | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | 3
CREATIVE DOOR & MILLWORK | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | 3 | 2 | 2 | PM is overextended. Have gotten district manager to assist
CROWTHER ROOFING & SHEET METAL | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | 4 | 3 | 5
DEKSCAPE | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD SON & COMPANY | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 4 | 4
EXTREME CARE | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINYL SALES | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FORTUNE ELECTRICAL | S | 15-0310 | 2016-03-13 | 5 | 4 | 4 | 4 | 3 | 4 | 4
FUSION WELDING OF SWFL | S | 15-0310 | 2016-03-13 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Sub was put in default and has been supplemented
GFA INTERNATIONAL | S | 15-0310 | 2016-03-13 | 4 | 4 | 4 | 4 | N/A | N/A | 4
GRATE FIREPLACE AND OUTDOOR | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 4 | 4
HAMMER FIREPROOFING | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | 3 | 3 | 3
HANNULA LANDSCAPING | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LEE DRYWALL | S | 15-0310 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 5
LIBERTY ALUMINUM | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | 3
MARDALE SPECIALTIES DIRECT | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | 4 | 4 | 4
NAPLES CONCRETE & MASONRY | S | 15-0310 | 2016-03-13 | 4 | 5 | 4 | 5 | 4 | 4 | 4
NATIONAL CONSTRUCTION RENTALS | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | 4
RICE CONTRACTING ENTERPRISES | S | 15-0310 | 2016-03-13 | 4 | 4 | 4 | 4 | 5 | 5 | 5
SAFE SITE CONSULTING | S | 15-0310 | 2016-03-13 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SCHINDLER ELEVATOR | S | 15-0310 | 2016-03-13 | N/A | 2 | N/A | N/A | N/A | 3 | 2 | unresponsive
SERVICE PAINTING OF FLORIDA | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | 3 | 4 | 4
SPRAGGINS MULTI FAMILY | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | 3 | N/A | 3
STANLEY ACCESS TECHNOLOGIES | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 4 | 3
STOUTEN CRAMER | S | 15-0310 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SUPERIOR FABRICATION | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TAILORED FOAM OF FLORIDA | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TERRICK CONSTRUCTION COMPANY | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TROPIX MARBLE COMPANY | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TRUSSWAY MFG. | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 4 | 3
UNICORN PAINTING INC. | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | 3 | N/A | 4
UNIWASHER | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | 4 | 5 | 5
VALIANT PRODUCTS | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 4 | 4
VIKING CONSTRUCTION | S | 15-0310 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WARMING TRENDS | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | 4
WAYNE AUTOMATIC FIRE | S | 15-0310 | 2016-03-13 | 4 | 4 | 4 | 4 | N/A | 4 | 4
WHIRLPOOL CORPORATION | S | 15-0310 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | 3
AAC CONTRACTING, INC. | S | 15-0303 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2016-03-13 | 3 | 4 | 4 | 4 | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2016-03-13 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
BGI INTERIORS | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2016-03-13 | 4 | 2 | 4 | 4 | 2 | 2 | 2 | unresponsive
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0303 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FLOWER CITY GLASS | S | 15-0303 | 2016-03-13 | 4 | 4 | 4 | 4 | N/A | 3 | 2
GROVER & BATES ASSOCIATES | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 2 | 2
J&R SPECIALTIES | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
JACHLES IMPERIAL LTD | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KELLEY BROS. LLC | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 2 | 2 | Buffalo office
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | no longer onsite
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MASA ARCHITECTURAL CANOPIES | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MESSNER FLOORING RESOURCE | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEW YORK STATE FENCE, INC | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OTIS ELEVATOR, USA | S | 15-0303 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RADEC CORPORATION | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2016-03-13 | 4 | 4 | 4 | 4 | 3 | 3 | 4
ROCK ENVIRONMENTAL | S | 15-0303 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHULER-HAAS | S | 15-0303 | 2016-03-13 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | Great foreman- easy to work with- great communication
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | Wont sign the short-form contract
UNICO FINISHING SYSTEMS | S | 15-0303 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WILLIAM L. WATSON | S | 15-0303 | 2016-03-13 | 4 | 4 | N/A | 4 | N/A | 3 | N/A
84 LUMBER COMPANY | S | 15-0315 | 2016-03-13 | 4 | 3 | 4 | 4 | 4 | 4 | 4
ABJ FIRE PROTECTION CO. | S | 15-0315 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATENARY CONSTRUCTION CORP. | S | 15-0315 | 2016-03-13 | 4 | 4 | 3 | 4 | 4 | 4 | 4
HENRY E ISAACS QUALITY HOME | S | 15-0315 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0315 | 2016-03-13 | 4 | 3 | 4 | 4 | 4 | 4 | 4
LANDMARK ELECTRIC INC | S | 15-0315 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RAMAR STEEL SALES, INC | S | 15-0315 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WOODSTONE EARTH CONSTRUCTION, INC | S | 15-0315 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 15-0312 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 15-0312 | 2016-03-13 | 4 | 3 | 3 | 4 | 3 | 4 | 4
ES SYSTEMS, INC | S | 15-0312 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 15-0312 | 2016-03-13 | 3 | 4 | 4 | 4 | 4 | 4 | 4
IMAGE CITY | S | 15-0312 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0312 | 2016-03-13 | 4 | 3 | 4 | 3 | 3 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 15-0312 | 2016-03-13 | 4 | 4 | 5 | 4 | 3 | 2 | 2 | Bad at re-submittal process
AAC CONTRACTING, INC. | S | 14-0289 | 2016-03-13 | 4 | 5 | 5 | 4 | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0289 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
B&L WHOLESALE | S | 14-0289 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 4 | 3
BENEDETTI BUILDERS | S | 14-0289 | 2016-03-13 | 4 | 4 | 4 | 4 | N/A | 4 | N/A
BSR | S | 14-0289 | 2016-03-13 | 2 | 2 | 3 | 1 | 3 | 3 | 3 | office over-promises; company should not be used for siding
CATENARY CONSTRUCTION CORP. | S | 14-0289 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAYUGA LANDSCAPE | S | 14-0289 | 2016-03-13 | 3 | 4 | 3 | 4 | 3 | 2 | 4
Clean Tech | S | 14-0289 | 2016-03-13 | 5 | 5 | 3 | 5 | N/A | N/A | 4
COMFORT SYSTEMS (SYRACUSE) | S | 14-0289 | 2016-03-13 | 3 | 2 | 3 | 2 | 4 | 4 | 2 | Plumbing foreman is not cooperative, trustworthy, or competent. Office is problematic. They are behind schedule and not concerned. They complain about safety, yet are the worst offenders
D & R JONES CONSTRUCTION | S | 14-0289 | 2016-03-13 | 3 | 3 | 4 | 4 | 3 | 4 | 2 | do not provide adequate manpower but provided it after veing pushed
EZ WAY | S | 14-0289 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0289 | 2016-03-13 | 2 | 1 | 3 | 3 | N/A | 2 | 2 | Do not know their scope; Having issues with the PM - Mark Webster
GERHARZ EQUIPMENT | S | 14-0289 | 2016-03-13 | 2 | 2 | 3 | 2 | N/A | 2 | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0289 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
INNOVATIVE WINDOWEAR | S | 14-0289 | 2016-03-13 | 3 | 3 | 3 | 3 | N/A | 3 | 3
JOHN C. LOWERY | S | 14-0289 | 2016-03-13 | 4 | 4 | 4 | 3 | 3 | 4 | 3
KELLY BROS. | S | 14-0289 | 2016-03-13 | N/A | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 14-0289 | 2016-03-13 | 3 | 4 | 4 | 4 | 2 | 3 | 2
LEMOYNE INTERIORS, INC. | S | 14-0289 | 2016-03-13 | 4 | 4 | 4 | 4 | 2 | 3 | 4
Life Maid Heavenly | S | 14-0289 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRS COMPANIES | S | 14-0289 | 2016-03-13 | 2 | 3 | 4 | 3 | 4 | 4 | 4 | Safety isnt a priority for them; lack of man power
MASCO BUILDER SERV GROUP | S | 14-0289 | 2016-03-13 | 3 | 1 | 3 | 3 | 2 | 4 | 4
MCPHERSON BUILDERS | S | 14-0289 | 2016-03-13 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | Very reliable
MOD SPACE | S | 14-0289 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | 1 | 1 | Unresponsive office
NATIONAL LUMBER | S | 14-0289 | 2016-03-13 | 1 | 1 | 2 | 2 | N/A | N/A | N/A | offsite
PLEASANT VALLEY ELEC. | S | 14-0289 | 2016-03-13 | 5 | 5 | 5 | 5 | N/A | N/A | N/A | offsite
PREMIER UTILITY SVC. | S | 14-0289 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0289 | 2016-03-13 | 3 | 4 | 4 | 4 | 3 | 4 | 3 | pedal for T
RADEC CORPORATION | S | 14-0289 | 2016-03-13 | 4 | 3 | 4 | 3 | 3 | 2 | 3 | piecemeal submittals; unorganized and incomplete; not following 3wk schedule
RAULLI Y SONS, INC. | S | 14-0289 | 2016-03-13 | 4 | 4 | 4 | 4 | N/A | 4 | 5
ROSCOE BROTHERS MILLWORK | S | 14-0289 | 2016-03-13 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | High Maintenance
SCHINDLER ELEVATOR | S | 14-0289 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Sears Roebuck | S | 14-0289 | 2016-03-13 | 4 | 3 | 3 | 3 | N/A | N/A | 4 | new rep = better service than last month
SHEPARDVILLE |  | 14-0289 | 2016-03-13 | 3 | 3 | 3 | 3 | 3 | N/A | 3
TG MILLER | S | 14-0289 | 2016-03-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Layout only
THE BRAIN DRAIN | S | 14-0289 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 14-0289 | 2016-03-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2016-03-13 | 3 | 3 | 3 | 3 | 3 | 3 | 3
WILCOX BUILDING SPECIALTIES | S | 14-0289 | 2016-03-13 | 3 | 4 | 4 | 4 | 3 | 2 | 3
AAC CONTRACTING, INC. | S | 14-0289 | 2016-05-13 | 4 | 5 | 5 | 4 | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0289 | 2016-05-13 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
B&L WHOLESALE | S | 14-0289 | 2016-05-13 | N/A | N/A | N/A | N/A | N/A | 4 | 3
BENEDETTI BUILDERS | S | 14-0289 | 2016-05-13 | 4 | 4 | 2 | 4 | N/A | 4 | N/A
BSR | S | 14-0289 | 2016-05-13 | 2 | 2 | 3 | 1 | 3 | 3 | 3 | office over-promises; company should not be used for siding
CATENARY CONSTRUCTION CORP. | S | 14-0289 | 2016-05-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAYUGA LANDSCAPE | S | 14-0289 | 2016-05-13 | 3 | 4 | 3 | 4 | 3 | 2 | 4
Clean Tech | S | 14-0289 | 2016-05-13 | 5 | 5 | 3 | 5 | N/A | N/A | 4
COMFORT SYSTEMS (SYRACUSE) | S | 14-0289 | 2016-05-13 | 3 | 2 | 2 | 2 | 4 | 4 | 2 | Plumbing foreman is not cooperative, trustworthy, or competent. Office is problematic. They are behind schedule and not concerned. They complain about safety, yet are the worst offenders
D & R JONES CONSTRUCTION | S | 14-0289 | 2016-05-13 | 3 | 3 | 4 | 4 | 3 | 4 | 2 | do not provide adequate manpower but provided it after veing pushed
EZ WAY | S | 14-0289 | 2016-05-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0289 | 2016-05-13 | 2 | 1 | 3 | 3 | N/A | 2 | 2 | Do not know their scope; Having issues with the PM - Mark Webster
GERHARZ EQUIPMENT | S | 14-0289 | 2016-05-13 | 2 | 2 | 3 | 2 | N/A | 2 | N/A
HENDERSON-JOHNSON CO.INC. | S | 14-0289 | 2016-05-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
INNOVATIVE WINDOWEAR | S | 14-0289 | 2016-05-13 | 3 | 3 | 3 | 3 | N/A | 3 | 3
JOHN C. LOWERY | S | 14-0289 | 2016-05-13 | 4 | 4 | 4 | 3 | 3 | 4 | 3
KELLY BROS. | S | 14-0289 | 2016-05-13 | N/A | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 14-0289 | 2016-05-13 | 3 | 4 | 4 | 4 | 2 | 3 | 2
LEMOYNE INTERIORS, INC. | S | 14-0289 | 2016-05-13 | 4 | 4 | 4 | 4 | 2 | 3 | 4
Life Maid Heavenly | S | 14-0289 | 2016-05-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRS COMPANIES | S | 14-0289 | 2016-05-13 | 2 | 3 | 4 | 3 | 4 | 4 | 4 | Safety isnt a priority for them; lack of man power
MASCO BUILDER SERV GROUP | S | 14-0289 | 2016-05-13 | 3 | 3 | 3 | 3 | 2 | 4 | 4
MCPHERSON BUILDERS | S | 14-0289 | 2016-05-13 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | Very reliable
MOD SPACE | S | 14-0289 | 2016-05-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2016-05-13 | N/A | N/A | N/A | N/A | N/A | 1 | 1 | Unresponsive office
NATIONAL LUMBER | S | 14-0289 | 2016-05-13 | 1 | 1 | 2 | 2 | N/A | N/A | N/A | offsite
PLEASANT VALLEY ELEC. | S | 14-0289 | 2016-05-13 | 5 | 5 | 5 | 5 | N/A | N/A | N/A | offsite
PREMIER UTILITY SVC. | S | 14-0289 | 2016-05-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0289 | 2016-05-13 | 3 | 4 | 4 | 4 | 3 | 4 | 3 | pedal for T
RADEC CORPORATION | S | 14-0289 | 2016-05-13 | 4 | 3 | 4 | 3 | 3 | 2 | 3 | piecemeal submittals; unorganized and incomplete; not following 3wk schedule
RAULLI Y SONS, INC. | S | 14-0289 | 2016-05-13 | 4 | 4 | 4 | 4 | N/A | 4 | 5
ROSCOE BROTHERS MILLWORK | S | 14-0289 | 2016-05-13 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | High Maintenance
SCHINDLER ELEVATOR | S | 14-0289 | 2016-05-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Sears Roebuck | S | 14-0289 | 2016-05-13 | 4 | 3 | 2 | 3 | N/A | N/A | 4 | new rep = better service than last month
SHEPARDVILLE |  | 14-0289 | 2016-05-13 | 3 | 3 | 3 | 3 | 3 | N/A | 3
TG MILLER | S | 14-0289 | 2016-05-13 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Layout only
THE BRAIN DRAIN | S | 14-0289 | 2016-05-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 14-0289 | 2016-05-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2016-05-13 | 3 | 3 | 3 | 3 | 3 | 3 | 3
WILCOX BUILDING SPECIALTIES | S | 14-0289 | 2016-05-13 | 3 | 4 | 4 | 4 | 3 | 2 | 3
104 CONTRACTORS INC. | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACPRODUCTS, INC | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | supplier
AIIA CONSTRUCTION COMPANY, INC | S | 15-0305 | 2016-05-15 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | Reached out to office to try to improve PCO process.
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 3
ALLIED MECHANICAL | S | 15-0305 | 2016-05-15 | 4 | 5 | 4 | 5 | 3 | 3 | 3
ALPHA IRON WORKS, LLC | S | 15-0305 | 2016-05-15 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BALTZ CONCRETE CONST., INC | S | 15-0305 | 2016-05-15 | 5 | 3 | 5 | 5 | 5 | N/A | 5 | Excellent Safety. Great all around.
BILLONE MECHANICAL CONTRACTORS | S | 15-0305 | 2016-05-15 | 5 | 5 | 4 | 3 | N/A | 5 | 5
BUFFALO CONCRETE ACCESSORIES | S | 15-0305 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CAPITIAL FENCE CO., INC | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATALANO CONTRACTING, INC | S | 15-0305 | 2016-05-15 | 4 | 4 | 4 | 4 | N/A | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0305 | 2016-05-15 | 5 | 4 | 4 | 4 | N/A | 4 | 4
DESIGN POOL & SPA LTD. | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENERGY INSULATION SYSTEMS, INC | S | 15-0305 | 2016-05-15 | 4 | 2 | 3 | 3 | N/A | 4 | 4
FISHER CONCRETE, INC | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GYPSUM SYSTEMS, INC. | S | 15-0305 | 2016-05-15 | 4 | 5 | 5 | 4 | N/A | 3 | 3
HENDERSON-JOHNSON CO.INC. | S | 15-0305 | 2016-05-15 | 5 | 5 | 5 | 5 | 5 | 5 | 5
HENRY E ISAACS QUALITY HOME | S | 15-0305 | 2016-05-15 | 4 | 4 | 4 | 3 | 4 | 4 | 4
J Y R SPECIALITIES, INC | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
J.B. HUNT | S | 15-0305 | 2016-05-15 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 40 installs with at least 20 different install crews. We voiced that we wanted the consistent. Only incident on the project was with this sub. Still scratched floors. No office leadership.
JOHNSON & JOHNSON CONSTRUCTION | S | 15-0305 | 2016-05-15 | 3 | 3 | 3 | 3 | 3 | N/A | 1 | Actual in-house crews are good. Did improve after we voiced our discontent
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2016-05-15 | 5 | 5 | 4 | 4 | 3 | 2 | 5 | New contact in office; very proactive
KLEIN REINFORCING SERVICES | S | 15-0305 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 15-0305 | 2016-05-15 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | Unacceptable. Never want to work with again
L.J. QUIGLIANO | S | 15-0305 | 2016-05-15 | 4 | 5 | 5 | 5 | 2 | 2 | 4 | Fantactic. They follow our plan and are very helpful. Small office so slow on follow up
LAKEVIEW LAWN & LANDSCAPE | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 15-0305 | 2016-05-15 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MIG BUILDING SYSTEMS | S | 15-0305 | 2016-05-15 | 4 | 3 | 3 | 2 | 4 | 3 | 3
MONTGOMERY TRUSS & PANEL (PANELS) | S | 15-0305 | 2016-05-15 | 5 | 5 | 5 | 5 | N/A | 4 | 5
ONTARIO EXTERIORS, INC | S | 15-0305 | 2016-05-15 | 4 | 3 | 4 | 4 | 4 | 4 | 3
PASSERO ASSOCIATES | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0305 | 2016-05-15 | 4 | 4 | 4 | 4 | 3 | 2 | 3
S.A.B. SPECIALTIES | S | 15-0305 | 2016-05-15 | 2 | 4 | 4 | 5 | 4 | N/A | 4
SUPERIOR CONTRACTING, INC. | S | 15-0305 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 3
UNICO FINISHING SYSTEMS | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNITED MATERIALS, LLC | S | 15-0305 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0305 | 2016-05-15 | 2 | 1 | 1 | 1 | 1 | 1 | N/A | Whirlpool/JB Hunt unaccpetable. NEVER want to use again
WM. B. MORSE LUMBER CO. | S | 15-0305 | 2016-05-15 | 4 | 4 | 4 | N/A | 4 | 4 | 4
ADAMS GROUP | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | 3 | 3 | 3
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | 3 | 3 | 3
BELVEDERE USA | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | 3 | 3 | 3
CLARY'S SITEWORK & DEVELOPMENT | S | 15-0310 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
COLONIAL CONSTRUCTION CONCRETE | S | 15-0310 | 2016-05-15 | 3 | 4 | 4 | 4 | 4 | 4 | 4
COMMERCIAL PLUMBING SOLUTIONS | S | 15-0310 | 2016-05-15 | 4 | 3 | 3 | 3 | 4 | 3 | 3
COMPREHENSIVE BUILDING ENVELOPE | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | 3
CREATIVE DOOR & MILLWORK | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | 3 | 2 | 2 | PM is overextended. Have gotten district manager to assist
CROWTHER ROOFING & SHEET METAL | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | 4 | 3 | 5
DEKSCAPE | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD SON & COMPANY | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | 4 | 4
EXTREME CARE | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINYL SALES | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FORTUNE ELECTRICAL | S | 15-0310 | 2016-05-15 | 5 | 4 | 4 | 4 | 3 | 4 | 4
FUSION WELDING OF SWFL | S | 15-0310 | 2016-05-15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Sub was put in default and has been supplemented
GFA INTERNATIONAL | S | 15-0310 | 2016-05-15 | 4 | 4 | 4 | 4 | N/A | N/A | 4
GRATE FIREPLACE AND OUTDOOR | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | 4 | 4
HAMMER FIREPROOFING | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | 3 | 3 | 3
HANNULA LANDSCAPING | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LEE DRYWALL | S | 15-0310 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 5
LIBERTY ALUMINUM | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | 3
MARDALE SPECIALTIES DIRECT | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | 4 | 4 | 4
NAPLES CONCRETE & MASONRY | S | 15-0310 | 2016-05-15 | 4 | 5 | 4 | 5 | 4 | 4 | 4
NATIONAL CONSTRUCTION RENTALS | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | 4
RICE CONTRACTING ENTERPRISES | S | 15-0310 | 2016-05-15 | 4 | 4 | 4 | 4 | 5 | 5 | 5
SAFE SITE CONSULTING | S | 15-0310 | 2016-05-15 | 4 | 4 | 4 | 4 | N/A | N/A | 4
SCHINDLER ELEVATOR | S | 15-0310 | 2016-05-15 | N/A | 2 | N/A | N/A | N/A | 3 | 2 | unresponsive
SERVICE PAINTING OF FLORIDA | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | 3 | 4 | 4
SPRAGGINS MULTI FAMILY | S | 15-0310 | 2016-05-15 | 4 | 4 | 4 | N/A | 3 | N/A | 3
STANLEY ACCESS TECHNOLOGIES | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | 4 | 3
STOUTEN CRAMER | S | 15-0310 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SUPERIOR FABRICATION | S | 15-0310 | 2016-05-15 | 4 | 5 | 4 | 4 | N/A | N/A | 4
TAILORED FOAM OF FLORIDA | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TERRICK CONSTRUCTION COMPANY | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TROPIX MARBLE COMPANY | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TRUSSWAY MFG. | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | 4 | 3
UNICORN PAINTING INC. | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | 3 | N/A | 4
UNIWASHER | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | 4 | 5 | 5
VALIANT PRODUCTS | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | 4 | 4
VIKING CONSTRUCTION | S | 15-0310 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WARMING TRENDS | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | 4
WAYNE AUTOMATIC FIRE | S | 15-0310 | 2016-05-15 | 4 | 4 | 4 | 4 | N/A | 4 | 4
WHIRLPOOL CORPORATION | S | 15-0310 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | 3
84 LUMBER COMPANY | S | 15-0315 | 2016-05-15 | 4 | 4 | 3 | 4 | 4 | 4 | 4
ABJ FIRE PROTECTION CO. | S | 15-0315 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CATENARY CONSTRUCTION CORP. | S | 15-0315 | 2016-05-15 | 4 | 4 | 3 | 4 | 4 | 4 | 4
HENRY E ISAACS QUALITY HOME | S | 15-0315 | 2016-05-15 | 3 | 4 | 4 | 4 | 4 | 4 | 4
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0315 | 2016-05-15 | 4 | 3 | 4 | 4 | 4 | 4 | 4
LANDMARK ELECTRIC INC | S | 15-0315 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
RAMAR STEEL SALES, INC | S | 15-0315 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WOODSTONE EARTH CONSTRUCTION, INC | S | 15-0315 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 15-0312 | 2016-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CATENARY CONSTRUCTION CORP. | S | 15-0312 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES SYSTEMS, INC | S | 15-0312 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINGER LAKES PAINTING & WALLCOVERING, LLC | S | 15-0312 | 2016-05-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IMAGE CITY | S | 15-0312 | 2016-05-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0312 | 2016-05-15 | 4 | 3 | 4 | 3 | 3 | 4 | 4
O'CONNELL ELECTRIC COMPANY, INC | S | 15-0312 | 2016-05-15 | 4 | 4 | 5 | 4 | 2 | 2 | 2 | Bad at re-submittal process
104 CONTRACTORS INC. | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
84 LUMBER COMPANY | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABJ FIRE PROTECTION CO. | S | 15-0305 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ACPRODUCTS, INC | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AIIA CONSTRUCTION COMPANY, INC | S | 15-0305 | 2016-06-15 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | Reached out to office to try to improve PCO process. Has made our site relationship better really actually trying these
ALLIANCE DOOR & HARDWARE | S | 15-0305 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 3
ALLIED MECHANICAL | S | 15-0305 | 2016-06-15 | 4 | 5 | 4 | 5 | 3 | 3 | 3
ALPHA IRON WORKS, LLC | S | 15-0305 | 2016-06-15 | 5 | 5 | 5 | 5 | 5 | 5 | 5
BALTZ CONCRETE CONST., INC | S | 15-0305 | 2016-06-15 | 5 | 3 | 5 | 5 | 5 | N/A | 5 | Excellent Safety. Great all around.
BILLONE MECHANICAL CONTRACTORS | S | 15-0305 | 2016-06-15 | 5 | 5 | 4 | 3 | N/A | 5 | 5
BUFFALO CONCRETE ACCESSORIES | S | 15-0305 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
CAPITIAL FENCE CO., INC | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATALANO CONTRACTING, INC | S | 15-0305 | 2016-06-15 | 4 | 4 | 4 | 4 | N/A | 4 | 4
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0305 | 2016-06-15 | 5 | 4 | 4 | 4 | N/A | 4 | 4
DESIGN POOL & SPA LTD. | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ENERGY INSULATION SYSTEMS, INC | S | 15-0305 | 2016-06-15 | 4 | 2 | 3 | 3 | N/A | 4 | 4
FAIRWAY FLOOR COVERING, INC. | S | 15-0305 | 2016-06-15 | 4 | 4 | 4 | 4 | 0 | 0 | 2 | Prompt get their work done. Self-reliant
FISHER CONCRETE, INC | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GYPSUM SYSTEMS, INC. | S | 15-0305 | 2016-06-15 | 4 | 5 | 5 | 4 | N/A | 3 | 3
HENDERSON-JOHNSON CO.INC. | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0305 | 2016-06-15 | 3 | 4 | 4 | 3 | 4 | 4 | 4 | Henry Issac is overwhelmed but they are putting in the effort. Safety can be inconsistent.
J Y R SPECIALITIES, INC | S | 15-0305 | 2016-06-15 | 4 | 2 | 4 | 3 | 4 | N/A | 2 | Field was good. Don?t necessarily believe the office in terms of scheduling
J.B. HUNT | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOHNSON & JOHNSON CONSTRUCTION | S | 15-0305 | 2016-06-15 | 3 | 3 | 3 | 3 | 3 | N/A | 1 | Actual in-house crews are good. Did improve after we voiced our discontent
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0305 | 2016-06-15 | 5 | 5 | 4 | 4 | 3 | 2 | 5 | New contact in office; very proactive
KLEIN REINFORCING SERVICES | S | 15-0305 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 15-0305 | 2016-06-15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Unacceptable. Never want to work with again
L.J. QUIGLIANO | S | 15-0305 | 2016-06-15 | 4 | 5 | 5 | 5 | 2 | 2 | 4 | Fantactic. They follow our plan and are very helpful. Small office so slow on follow up
LAKEVIEW LAWN & LANDSCAPE | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MAX T. DOLAND | S | 15-0305 | 2016-06-15 | 5 | 5 | 5 | 5 | 5 | 5 | 5
MIG BUILDING SYSTEMS | S | 15-0305 | 2016-06-15 | 4 | 3 | 3 | 2 | 4 | 3 | 3
MONTGOMERY TRUSS & PANEL (PANELS) | S | 15-0305 | 2016-06-15 | 5 | 5 | 5 | 5 | N/A | 4 | 5
ONTARIO EXTERIORS, INC | S | 15-0305 | 2016-06-15 | 4 | 3 | 4 | 4 | 4 | 4 | 3
PASSERO ASSOCIATES | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PETERSON BUILDERS FRAMING | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 15-0305 | 2016-06-15 | 5 | 5 | 5 | 5 | 5 | 5 | 5
RADEC CORPORATION | S | 15-0305 | 2016-06-15 | 4 | 4 | 4 | 4 | 3 | 2 | 3
S.A.B. SPECIALTIES | S | 15-0305 | 2016-06-15 | 2 | 4 | 4 | 5 | 4 | N/A | 4
SUPERIOR CONTRACTING, INC. | S | 15-0305 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 3
UNICO FINISHING SYSTEMS | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNITED MATERIALS, LLC | S | 15-0305 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0305 | 2016-06-15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | PPE is terrible; 0 onsite management; no accountability for JB Hunt issues, never even come out to site 55 days to make a repair. JB HUNT WE NEVER WANT TO USE AGAIN
WM. B. MORSE LUMBER CO. | S | 15-0305 | 2016-06-15 | 4 | 4 | 4 | N/A | 4 | 4 | 4
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0313 | 2016-06-15 | 2 | 4 | 4 | 3 | 0 | 4 | 4
CABLE ELECTRICAL SERVICES | S | 15-0313 | 2016-06-15 | 2 | 2 | 4 | 3 | N/A | 4 | 4
CLARY'S SITEWORK & DEVELOPMENT | S | 15-0313 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COLONIAL CONSTRUCTION CONCRETE | S | 15-0313 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL PLUMBING SOLUTIONS | S | 15-0313 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CROWTHER ROOFING & SHEET METAL | S | 15-0313 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FORTUNE ELECTRICAL | S | 15-0313 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FUSION WELDING OF SWFL | S | 15-0313 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAVEN CONTRACTING, INC | S | 15-0313 | 2016-06-15 | 3 | 2 | 4 | 3 | N/A | 3 | 3 | multiple changes in field crew
NAPLES CONCRETE & MASONRY | S | 15-0313 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATIONAL CONSTRUCTION RENTALS | S | 15-0313 | 2016-06-15 | 4 | 3 | 4 | 4 | N/A | N/A | 3
PEC SURVEYING AND MAPPING | S | 15-0313 | 2016-06-15 | 4 | 4 | 5 | 5 | N/A | N/A | 5
QP CONSTRUCTION | S | 15-0313 | 2016-06-15 | 3 | 4 | 4 | 3 | N/A | 4 | 4 | need real foreman
SCHINDLER ELEVATOR | S | 15-0313 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SERVICE PAINTING OF FLORIDA | S | 15-0313 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STOUTEN CRAMER | S | 15-0313 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUNBELT METALS | S | 15-0313 | 2016-06-15 | 3 | 3 | 0 | 0 | 0 | 3 | 3
SUNSHINE STATE PLUMBING | S | 15-0313 | 2016-06-15 | 4 | 3 | 4 | 3 | N/A | 3 | 3
TRUSSWAY MFG. | S | 15-0313 | 2016-06-15 | 4 | 4 | N/A | N/A | N/A | 3 | 4
UNIVERSAL ENGINEERING SCIENCES | S | 15-0313 | 2016-06-15 | N/A | 3 | 3 | 2 | N/A | 3 | 4
VALIANT PRODUCTS | S | 15-0313 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WATERWATCH CORPORATION | S | 15-0313 | 2016-06-15 | 3 | 3 | 3 | 3 | N/A | N/A | 3
WAYNE AUTOMATIC FIRE | S | 15-0313 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHIRLPOOL CORPORATION | S | 15-0313 | 2016-06-15 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | PPE is terrible; 0 onsite management; no accountability for JB Hunt issues, never even come out to site 55 days to make a repair. JB HUNT WE NEVER WANT TO USE AGAIN
WHR HOLDINGS | S | 15-0313 | 2016-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WLW CONSTRUCTION | S | 15-0313 | 2016-06-15 | 4 | 3 | 4 | 4 | N/A | 2 | 2 | very weak on providing paper
ABJ FIRE PROTECTION CO. | S | 15-0314 | 2016-06-15 | N/A | 0 | 0 | 0 | 0 | 3 | 0
ACPRODUCTS, INC | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
ALLIED MECHANICAL | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
ANNAS CLEANING SERVICE NY | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
B.R. JOHNSON | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
BARRY STEEL FABRICATIONS | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
BGI INTERIORS | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
BILLONE MECHANICAL CONTRACTORS | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | 3 | 3 | 4
BRAWDY CONSTRUCTION | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0314 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Good, available when you need them
CITY FENCE | S | 15-0314 | 2016-06-15 | 4 | 4 | 4 | 4 | 2 | 3 | 2 | Inexperienced
D.C.B. ELEVATOR | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
D.V. BROWN & ASSOCIATES | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
DDS CONSTRUCTORS, LLC | S | 15-0314 | 2016-06-15 | 5 | 3 | 4 | 3 | 3 | 2 | 2 | overbill on items, seem to be coming around
DESIGN SPECIALISTS INC. | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
FAIRWAY FLOOR COVERING, INC. | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
FERRARO PILE & SHORING |  | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
FSR CONTRACTING | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
GPI ENGINEERING AND SURVEYING | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GRAYCO CORP OF UPSTATE NY | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
GYPSUM SYSTEMS, INC. | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
J Y R SPECIALITIES, INC | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A | Field was good. Don?t necessarily believe the office in terms of scheduling
J&R SPECIALTIES | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
MAIN FORD GEN. SUPPLY | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
MAX T. DOLAND | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
MURRAY ROOFING COMPANY | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
NORTHLAND CONTRACTING | S | 15-0314 | 2016-06-15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | Excellent!
OTIS ELEVATOR, USA | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
RADEC CORPORATION | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
THE R.E. KRUG CORP | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICO FINISHING SYSTEMS | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 2 | N/A
WM. B. MORSE LUMBER CO. | S | 15-0314 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 3 | N/A
ADAMS GROUP | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | 3 | 3 | 3
ARMSTRONG AIR AND HEATING OF CENTRAL FLORIDA INC | S | 15-0310 | 2016-06-14 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | Have started to be more responsive in the office
BELVEDERE USA | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | 3 | 3 | 4
CLARY'S SITEWORK & DEVELOPMENT | S | 15-0310 | 2016-06-14 | 4 | 3 | 4 | 3 | 4 | 4 | 4 | stretched to other sites and not focused on our project
COLONIAL CONSTRUCTION CONCRETE | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COMMERCIAL PLUMBING SOLUTIONS | S | 15-0310 | 2016-06-14 | 4 | 3 | 3 | 3 | 4 | 3 | 3
COMPREHENSIVE BUILDING ENVELOPE | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | 3
CREATIVE DOOR & MILLWORK | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | 2 | 3 | 2 | Have gotten district manager to assist
CROWTHER ROOFING & SHEET METAL | S | 15-0310 | 2016-06-14 | 5 | 4 | 5 | 4 | 4 | 3 | 5
DEKSCAPE | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDWARD SON & COMPANY | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | 4 | 4
EXTREME CARE | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FINYL SALES | S | 15-0310 | 2016-06-14 | 3 | 3 | 3 | 3 | N/A | N/A | N/A
FORTUNE ELECTRICAL | S | 15-0310 | 2016-06-14 | 5 | 4 | 4 | 4 | 3 | 4 | 4
FUSION WELDING OF SWFL | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GFA INTERNATIONAL | S | 15-0310 | 2016-06-14 | 4 | 4 | 4 | 4 | N/A | N/A | 4
GRATE FIREPLACE AND OUTDOOR | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | 4 | 4
HAMMER FIREPROOFING | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HANNULA LANDSCAPING | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LEE DRYWALL | S | 15-0310 | 2016-06-14 | 4 | 4 | 4 | 4 | 4 | 4 | 5
LIBERTY ALUMINUM | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | 4 | 4
MARDALE SPECIALTIES DIRECT | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | 4 | 4 | 4
NAPLES CONCRETE & MASONRY | S | 15-0310 | 2016-06-14 | 4 | 5 | 4 | 5 | 4 | 4 | 4
NATIONAL CONSTRUCTION RENTALS | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | 4
PROTECTIVE BARRIERS | S | 15-0310 | 2016-06-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QP CONSTRUCTION | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RENFROE & JACKSON | S | 15-0310 | 2016-06-14 | 0 | 0 | 0 | 0 | 3 | 5 | 4 | too early to rate
RICE CONTRACTING ENTERPRISES | S | 15-0310 | 2016-06-14 | 3 | 3 | 3 | 3 | 5 | 4 | 5
SAFE SITE CONSULTING | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHINDLER ELEVATOR | S | 15-0310 | 2016-06-14 | N/A | 2 | N/A | N/A | N/A | 3 | 2 | unresponsive
SERVICE PAINTING OF FLORIDA | S | 15-0310 | 2016-06-14 | 4 | 4 | 4 | 4 | 3 | 4 | 4
SPRAGGINS MULTI FAMILY | S | 15-0310 | 2016-06-14 | 4 | 4 | 4 | N/A | 3 | N/A | 3
STANLEY ACCESS TECHNOLOGIES | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STOUTEN CRAMER | S | 15-0310 | 2016-06-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SUPERIOR FABRICATION | S | 15-0310 | 2016-06-14 | 4 | 5 | 4 | 4 | N/A | N/A | 4
TAILORED FOAM OF FLORIDA | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TERRICK CONSTRUCTION COMPANY | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | 3
TROPIX MARBLE COMPANY | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | 3 | 3 | 3
TRUSSWAY MFG. | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNICORN PAINTING INC. | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | 3 | N/A | 4
UNIWASHER | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | 4 | 5 | 5
VALIANT PRODUCTS | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VIKING CONSTRUCTION | S | 15-0310 | 2016-06-14 | 4 | 4 | 4 | 4 | 4 | 4 | 4
WARMING TRENDS | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | 4
WAYNE AUTOMATIC FIRE | S | 15-0310 | 2016-06-14 | 4 | 4 | 4 | 4 | N/A | 4 | 4
WHIRLPOOL CORPORATION | S | 15-0310 | 2016-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | 3
AAC CONTRACTING, INC. | S | 15-0303 | 2016-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ACCURATE ACOUSTICAL, INC. | S | 15-0303 | 2016-06-15 | 3 | 4 | 4 | 4 | 3 | N/A | N/A | PCO are nickeled and dimed; T
ALEXANDER MITCHELL & SON | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ALLIANCE DOOR & HARDWARE | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUBURN CRANE AND RIGGING, INC | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BAY TILE MARBLE & TERRAZZO | S | 15-0303 | 2016-06-15 | 4 | 4 | 4 | 4 | 3 | 4 | N/A
BGI INTERIORS | S | 15-0303 | 2016-06-15 | N/A | 3 | 4 | N/A | N/A | 4 | N/A | getting materials here on time trouble here
BILLONE MECHANICAL CONTRACTORS | S | 15-0303 | 2016-06-15 | 4 | 3 | 3 | 3 | 2 | 3 | 2 | Field is great office is poor: increasing T
CATENARY CONSTRUCTION CORP. | S | 15-0303 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Dave Powers has been great (foreman)
CHARLES T DRISCOLL MASONRY RESTORATION CO. INC. | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDS CONSTRUCTORS, LLC | S | 15-0303 | 2016-06-15 | 4 | 3 | 4 | 4 | 3 | N/A | N/A | Having Matt Clark on the job is challenging - Nickel and dimes the PCOs
ES SYSTEMS, INC | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FIREPLACE FASHIONS | S | 15-0303 | 2016-06-15 | 0 | 0 | 0 | 0 | 0 | 3 | 0
FLOWER CITY GLASS | S | 15-0303 | 2016-06-15 | 4 | 4 | 4 | 4 | N/A | 3 | 2 | Lead times are not what they say it will be
GROVER & BATES ASSOCIATES | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HENRY E ISAACS QUALITY HOME | S | 15-0303 | 2016-06-15 | 4 | 3 | 4 | 4 | N/A | N/A | 2
J&R SPECIALTIES | S | 15-0303 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
JACHLES IMPERIAL LTD | S | 15-0303 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
JOSEPHINE'S CLEANING SERVICE, LLC | S | 15-0303 | 2016-06-15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | Care about their work Outstanding.
KELLEY BROS. LLC | S | 15-0303 | 2016-06-15 | N/A | 3 | 3 | N/A | N/A | 2 | 2 | 10 of 14 doors had issues (out of Buffalo)- incorrectly prepped or not prepped at all. Supplier argued with Jamie that they were prepped properly
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0303 | 2016-06-15 | 4 | 2 | 4 | 4 | 4 | 4 | 4 | Still need vents. But went above and beyond when we needed pro-press when Billone would nto provide
LAKELANDS CONCRETE PRODUCTS | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAKEVIEW LAWN & LANDSCAPE | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MASA ARCHITECTURAL CANOPIES | S | 15-0303 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MESSNER FLOORING RESOURCE | S | 15-0303 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
NEW YORK STATE FENCE, INC | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NORTHEASTERN INSULATION | S | 15-0303 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
OTIS ELEVATOR, USA | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RADEC CORPORATION | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAULLI Y SONS, INC. | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROCHESTER COLONIAL MANUFACTURING | S | 15-0303 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
ROCK ENVIRONMENTAL | S | 15-0303 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
SCHULER-HAAS | S | 15-0303 | 2016-06-15 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | Great foreman- easy to work with- great communication. Stack of T
SPORT SURFACE SPECIALTIES | S | 15-0303 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | 3
UNICO FINISHING SYSTEMS | S | 15-0303 | 2016-06-15 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | Pcos: Needs to document extra work better
WILLIAM L. WATSON | S | 15-0303 | 2016-06-15 | 3 | 4 | N/A | 4 | N/A | 3 | 3 | Needs to wear hard hats
84 LUMBER COMPANY | S | 15-0315 | 2016-06-15 | N/A | 0 | 0 | 0 | 0 | 0 | 0
ABJ FIRE PROTECTION CO. | S | 15-0315 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AGAPE WHOLESALE FURNITURE | S | 15-0315 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | 4 | Just starting out
AIIA CONSTRUCTION COMPANY, INC | S | 15-0315 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | 4
ALLIANCE DOOR & HARDWARE | S | 15-0315 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | 4
ARCHWOOD, INC | S | 15-0315 | 2016-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 4
BME ASSOCIATES | S | 15-0315 | 2016-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 4
CATENARY CONSTRUCTION CORP. | S | 15-0315 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 15-0315 | 2016-06-15 | 4 | 4 | 3 | 4 | 4 | 4 | 4 | Windows
HENDERSON-JOHNSON CO.INC. | S | 15-0315 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
HENRY E ISAACS QUALITY HOME | S | 15-0315 | 2016-06-15 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | Has been Issued a few fine for safety. (fall protection)
KENNEDY MECHANICAL PLUMBING DIV. | S | 15-0315 | 2016-06-15 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | Plumbing and HVAC. Working long hours to complete their job.
LANDMARK ELECTRIC INC | S | 15-0315 | 2016-06-15 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | Needs more manpower.
RAMAR STEEL SALES, INC | S | 15-0315 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
US CEILING CORP. | S | 15-0315 | 2016-06-15 | 4 | 3 | 3 | 4 | 4 | 4 | 4
WOODSTONE EARTH CONSTRUCTION, INC | S | 15-0315 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4
AAC CONTRACTING, INC. | S | 14-0289 | 2016-06-15 | 4 | 5 | 5 | 4 | N/A | N/A | N/A
ASSA ABLOY ENTRANCE SYSTEMS | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 4 | N/A
B&L WHOLESALE | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 4 | 3
BENEDETTI BUILDERS | S | 14-0289 | 2016-06-15 | 4 | 2 | 2 | 2 | N/A | 4 | N/A | Own in-house personnel do not seem qualified to do commercial work. Do not know how to read drawings. Show up unprepared with no problem solving skills- this is the case for the entire company, not just select workers
BSR | S | 14-0289 | 2016-06-15 | 2 | 2 | 3 | 1 | 3 | 3 | 3 | office over-promises; company should not be used for siding
CATENARY CONSTRUCTION CORP. | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAYUGA LANDSCAPE | S | 14-0289 | 2016-06-15 | 3 | 4 | 3 | 4 | 3 | 2 | 4
Clean Tech | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No longer working due to complaints from customer regarding quality of work and refusal to sign a new contract without terms
COMFORT SYSTEMS (SYRACUSE) | S | 14-0289 | 2016-06-15 | 3 | 1 | 1 | 1 | 4 | 4 | 2 | Plumbing foreman is not cooperative, trustworthy, or competent. Office is problematic. They are behind schedule and not concerned. They complain about safety, yet are the worst offenders. Quality: Constant problems with everything inside their scope
D & R JONES CONSTRUCTION | S | 14-0289 | 2016-06-15 | 3 | 2 | 4 | 4 | 3 | 4 | 2 | do not provide adequate manpower but provided it after veing pushed; inconsistent ; poor communication
EZ WAY | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLOWER CITY GLASS | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GERHARZ EQUIPMENT | S | 14-0289 | 2016-06-15 | 2 | 1 | 2 | 2 | N/A | 2 | N/A | Constantly unable to deliver (on time, level of quality). Providing poor service to owner and to LECESSE. His reputation for poor communication and poor service goes beyond our project to other customers we have spoken to.
HENDERSON-JOHNSON CO.INC. | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
INNOVATIVE WINDOWEAR | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOHN C. LOWERY | S | 14-0289 | 2016-06-15 | 4 | 4 | 4 | 3 | 3 | 4 | 3
KELLY BROS. | S | 14-0289 | 2016-06-15 | N/A | 4 | 4 | 4 | 4 | 4 | 4
L.A.PAINTING, INC. | S | 14-0289 | 2016-06-15 | 3 | 3 | 4 | 4 | 2 | 3 | 2
LEMOYNE INTERIORS, INC. | S | 14-0289 | 2016-06-15 | 4 | 4 | 4 | 4 | 2 | 3 | 4
Life Maid Heavenly | S | 14-0289 | 2016-06-15 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Provide best service despite being small company
LRS COMPANIES | S | 14-0289 | 2016-06-15 | 2 | 3 | 4 | 3 | 4 | 4 | 4 | Safety isnt a priority for them; lack of man power
MASCO BUILDER SERV GROUP | S | 14-0289 | 2016-06-15 | 3 | 3 | 3 | 3 | 2 | 4 | 4
MCPHERSON BUILDERS | S | 14-0289 | 2016-06-15 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | Very reliable
MOD SPACE | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MODULAR SPACE CORPORATION | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | 1 | 1 | Unresponsive office
NATIONAL LUMBER | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | offsite
PLEASANT VALLEY ELEC. | S | 14-0289 | 2016-06-15 | 5 | 5 | 5 | 5 | 5 | 5 | 5
PREMIER UTILITY SVC. | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRO CARPET INC. | S | 14-0289 | 2016-06-15 | 3 | 4 | 4 | 4 | 3 | 4 | 3 | Have been dependable and predictable
RADEC CORPORATION | S | 14-0289 | 2016-06-15 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | piecemeal submittals; unorganized and incomplete; not following 3wk schedule
RAULLI Y SONS, INC. | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROSCOE BROTHERS MILLWORK | S | 14-0289 | 2016-06-15 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Absolutely no capabilities of delivering materials when needed
SCHINDLER ELEVATOR | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Sears Roebuck | S | 14-0289 | 2016-06-15 | 4 | 3 | 1 | 3 | N/A | N/A | 4 | Based on number of warranty calls related to appliances, we should never consider using Sears on a project.
SHEPARDVILLE |  | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TG MILLER | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Layout only
THE BRAIN DRAIN | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UPSTATE ROOFING & PAINTING, INC. | S | 14-0289 | 2016-06-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHITMORE FENCE | S | 14-0289 | 2016-06-15 | 3 | 3 | 3 | 3 | 3 | 3 | 3
WILCOX BUILDING SPECIALTIES | S | 14-0289 | 2016-06-15 | 3 | 4 | 4 | 4 | 3 | N/A | 3